## Index
Ê´É¹ÉªÉ ´ÉºiÉÖ INDEX
Gò¨É ºÉÆ. SR.NO | Ê´É¹ÉªÉ C O N T E N T S | {ÉÞ¹`öºÉÆ.PAGE NO.
1 | =kÉ®ú IÉäjÉÒªÉ Ê´ÉtÖiÉ ¦ÉhÉÉ±ÉÒ Eäò ¨ÉÖJªÉ ±ÉIÉhÉ | 1
Salient Features Of Northern Regional Power Grid
2 | ÖÏÖ±ú; ÃÖÓÃ£ÖÖ×¯ÖŸÖ Ö´ÖŸÖÖ ¾Ö ˆ““ÖŸÖ´Ö ˆ¯Ö»Ö²¬ÖŸÖÖ ¯Ö¸ü ˆŸ¯ÖÖ¤ü­Ö | 2
Graph; Installed Capacity & Generation at Peak Availability
3 | ÖÏÖ±ú , VÉ±ÉÒªÉ +ÉÄEòcä÷ (¨ÉÊ½þxÉä EòÒ +ÉJÉ®úÒ iÉÉ®úÒJÉ EòÉä VÉ±É ºiÉ®ú) , ÖÏÖêÃÖ ˆŸ¯ÖÖ¤ü­Ö | 3
Graph,Hydraulic data (Levels on the last day of the month) & Gross Energy Generation
4 | ×¾Ö•Ö»Öß †Ö¯ÖæŸÖá úß ÛÃ£Ö×ŸÖ :>ðVÉÉÇ EòÒ +É´É¶ªÉEòiÉÉ, ={É±É¤vÉiÉÉ iÉlÉÉ Eò¨ÉÒ, =SSÉiÉ¨É ¨ÉÉÄMÉ, ={É±É¤vÉiÉÉ | 4
Power Supply Position: Energy reqt., availability and shortage & Peak availability & reqt.
5 | Ê{ÉUô±Éä ´É¹ÉÇ EòÒ iÉÖ±ÉxÉÉ ¨Éå =kÉ®úÒ IÉäjÉ ¨Éå SÉÉ±ÉÚ ´É¹ÉÇ EòÒ Ê´ÉtÖiÉ +É{ÉÚÌiÉ ÛÃ£Ö×ŸÖ | 5
Power Supply Position in Northern Region during the current year as compared to previous year
6 | ´ÖÖÆü êú ¤üÖî¸üÖ­Ö ¯ÖÖ¡ÖŸÖÖ/ ×¿Ö›ü¶æ»Ö / ×­ÖúÖÃÖß ¾Ö ãˆ•ÖÖÔ Ê´ÉÊxÉ¨ÉªÉ | 6
Entitlement/Schedule/ Drawal & Energy Exchanges for the month
7 | ˆ.Öê. ´Öë ÛÃ£ÖŸÖ ¸üÖ•µÖÖë/ÃÖÓ¬Ö ¿Ö×ÃÖŸÖ Öê¡ÖÖë ´Öë †Ö²ÖÓ×™üŸÖ ÃÖÓµÖãŒŸÖ ¾Ö êú­¦üßµÖ ÃÖêŒ™ü¸ü ˆ¯ÖµÖÖê•µÖÖë úÖê ÃÖ´ÖÖ×ÆüŸÖ ú¸üŸÖê Æãü‹ ×¾ÖªãŸÖ ˆ¯ÖµÖÖê•µÖÖë úß ÃÖÓÃ£ÖÖ×¯ÖŸÖ Ö´ÖŸÖÖ (´ÖêÖÖ¾ÖÖ™ü ´Öë) | 7
Installed capacity(in MW) of power utilities in the states/Uts located in NR including allocated
shares in joint &central sector utilities
8 | Ê´ÉvÉÖiÉ º]äõ¶ÉxÉÉä EòÉ =i{ÉÉnùxÉ | 8 to11
Generation of Power Stations
9 | iÉÉ{ÉÒªÉ/xÉÉÊ¦ÉEòÒªÉ/MÉèºÉÒªÉ Ê´ÉtÖiÉ º]äõ¶ÉxÉÖêÓ EòÉ {ÉÒ.B±É.B¡ò. | 12 to13
P.L.F. of Thermal/ Nuclear/ Gas Power Stations.
10 | IÉäjÉÒªÉ =SSÉiÉ¨É ¨ÉÉÄMÉ Eäò ºÉ¨ÉªÉ VÉ±ÉÒªÉ, iÉÉ{ÉÒªÉ iÉlÉÉ xÉÉÊ¦ÉEòÒªÉ EäòxpùÉå ºÉä +Æ¶ÉnùÉxÉ | 14
Contribution from Hydro, Thermal, Nuclear Stations at the time of Regional Peak Demand.
11 | IÉäjÉ Eäò =SSÉiÉ¨É ¨ÉÉÄMÉ êú ×¤ü­Ö ŸÖ£ÖÖ ­µÖæ­ÖŸÖ´Ö ´ÖÖòÖ êú ×¤ü­Ö úÖ PÉx]äõ´ÉÉ®ú ¦ÉÉ®ú/=i{ÉÉnùxÉ +ÉÄEòcä÷ | 15
Hourly Load / Generation Data of Region for Peak Day And Off Peak Day.
12 | +ÊvÉºÉÚÊSÉiÉ Ê´ÉtÖiÉ EòÒ Eò]õÉèÊiÉ B´ÉÆ ¦ÉÊiÉ¤ÉxvÉ | 16
Notified Power Cuts and Restrictions
13 | EäòxpùÒªÉ ºÉèC]õ®ú Eäò Ê´ÉtÖiÉ EäòxpùÉä ºÉä >ðVÉÉÇ EòÉ +É¤ÉÆ]õxÉ | 17
Allocation of Shares to Constituents in Central Sector
14 | +É´ÉÞÊkÉ Ê´É¶±Éä¹ÉhÉ | 18
Frequency Analysis
15 | ´ÉÉä±]äõWÉ Ê´É¶±Éä¹ÉhÉ | 19
Voltage Analysis
16 | Ê´ÉtÖiÉ Eò]õÉèÊiÉ Eäò Ê±ÉªÉä ÊxÉ¨xÉ++É´ÉÞÊiÉ Ê®ú±Éä EòÒ ÎºlÉÊiÉ | 20
Status of Under Frequency relays for load shedding
17 | Eèò{ÉäÊºÉ]õ®ú ºÉÆºlÉÉ{ÉxÉ EòÒ ¦ÉMÉÊiÉ | 21
Progress of installation of capacitor
18 | 400 Eäò.´ÉÉä. iÉlÉÉ 220 ÊEò.´ÉÉä. {ÉÉ®äú¹ÉhÉ ±ÉÉ<ÇxÉÉå {É®ú EòÉªÉÇ ¨Éå ¦ÉMÉÊiÉ | 22
Progress of works on 400 kV & 220 kV transmission lines
19 | xÉ<Ç =i{ÉnùÉxÉ ªÉÉäVÉxÉÉ+Éå Eäò ºÉÆºlÉÉ{ÉxÉÉ EòÒ +ÊvÉºÉÚSÉÒ / ªÉÚÊxÉ]åõ ´É SÉÉ±ÉÚ EòÒ MÉ<È {ÉÉ®äú¹ÉhÉ ±ÉÉ<ÇxÉå | 23
Commissioning schedule of new generation schemes/Units & Transmission lines commissioned
20 | VÉ±ÉÉ¶ÉªÉÉå Eäò VÉ±ÉÒªÉ +ÉÄEòcä÷ | 24
Hydraulic Data of Reservoirs
¦Énù¶ÉÇ EXHIBITS
¦Énù¶ÉÇ-1 | =SSÉiÉ¨É ÊnùxÉ EòÒ IÉäjÉÒªÉ IÉ¨ÉiÉÉ, ={É±É¤vÉÉiÉ iÉlÉÉ =i{ÉÉnùxÉ {Éè]õxÉÇ
Exbt.I | Regional capacity, availability and generation pattern of the Peak day
¦Énù¶ÉÇ-2 | ¤îüÊxÉEò üIÉäjÉÒªÉ ­Öî™ ˆ•ÖÖÔ ={É±É¤vÉiÉÉ/Eò¨ÉÒ ´ÉGò
Exbt.II | Daily regional availability/shortage curves
¦Énù¶ÉÇ-3 | ¤îüÊxÉEò IÉäjÉÒªÉ ¯Ößú ={É±É¤vÉiÉÉ/Eò¨ÉÒ ´ÉGò
Exbt.III | Daily regional peak availability/shortage curves
¦Énù¶ÉÇ-4 | =kÉ®úÒ IÉäjÉ ¨Éå =SSÉiÉ¨É ¨ÉÉÄMÉ Eàò ÊnùxÉ PÉx]äõ´ÉÉ®ú ¦ÉÉ®ú ´É =i{ÉÉnùxÉ Eäò ´ÉGò
Exbt.IV | Hourly load / generation curves of Peak day of NR.
¦Énù¶ÉÇ-5 | =kÉ®úÒ IÉäjÉ ¨Éå ­µÖæ­ÖŸÖ´Ö ´ÖÖòÖ ¾ÖÖ»Öê ×¤ü­Ö úÖ PÉx]äõ´ÉÉ®ú ¦ÉÉ®ú ´É =i{ÉÉnùxÉ Eäò ´ÉGò
Exbt.V | Hourly load/ generation curves of Off Peak day of NR.
¦Énù¶ÉÇ-6-10 | 2007-2008, 2008-2009 iÉlÉÉ 2009-2010 Eäò nùÉè®úÉxÉ nùVÉÇ ÊEòªÉä MÉªÉä Ê´ÉÊ¦ÉzÉ VÉ±ÉÉ¶ÉªÉÉå EòÉ ºiÉ®ú
Exbt.VI-X | Levels recorded/ generation during 2007-08, 2008-09 and 2009-10 of various reservoirs.
¦Énù¶ÉÇ-11 | ˆ¢Ö¸üß Öê¡Ö ´Öë ´ÖÖÆü êú ¤üÖî¸üÖ­Ö ³ÖÖ¸ü †¾Ö×¬Ö úÖ ¾ÖÎú
Exbt.XI | Load duration curve of Northern Region for the month
¦Énù¶ÉÇ-12 | ˆ¢Ö¸üß Öê¡Ö ´Öë ´ÖÖÆü êú ¤üÖî¸üÖ­Ö †Ö¾Öé×¢Ö †¾Ö×¬Ö úÖ ¾ÖÎú
Exbt.XII | Frequency duration curve of Northern Region for the month

## Page1
1.....=kÉ®ú IÉäjÉÒªÉ Ê´ÉtÖiÉ ¦ÉhÉÉ±ÉÒ Eäò ¨ÉÖJªÉ ±ÉIÉhÉ
SALIENT FEATURES OF NORTHERN REGIONAL POWER GRID
Gò.ºÉÆ. |  | ¨ÉÉSÉÇ 2010 | ¨ÉÉSÉÇ 2009 | {ÉÊ®ú´ÉiÉÇxÉ | FEATURES
Sl.No. |  | March, 10 | March,09 | CHANGE
1 | ºÉÆºlÉÉÊ{ÉiÉ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) | 42189.33 | 38723.2 | 3466.13 | Installed Capacity (MW)
2 | ¨ÉÉÄMÉ (¨ÉèMÉÉ´ÉÉ]õ) | 34164 | 32443 | 1721 | Requirement (MW)
3 | ={É±É¤vÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) | 30308 | 27678 | 2630 | Availability( MW)
4 | Eò¨ÉÒ (¨ÉèMÉÉ´ÉÉ]õ) | 3856 | 4765 | -909 | Shortage(MW)
5 | Eò¨ÉÒ (¦ÉÊiÉ¶ÉiÉ ¨Éå) | 11.2867 | 14.6873 | -3.4006 | % Shortage
6 | ¨ÉÉÄMÉ (Ê¨É.ªÉÚ / ÊnùxÉ) | 692.07 | 624.18 | 67.89 | Requirement (MU/day)
7 | ={É±É¤vÉiÉÉ (Ê¨É.ªÉÚ / ÊnùxÉ) | 613.48 | 550.64 | 62.84 | Availability (MU/day)
8 | Eò¨ÉÒ (Ê¨É.ªÉÚ / ÊnùxÉõ) | 78.59 | 73.54 | 5.05 | Shortage(MU/day)
9 | Eò¨ÉÒ (¦ÉÊiÉ¶ÉiÉ ¨Éå) | 11.3558 | 11.7819 | -0.42607 | % Shortage
10 | =i{ÉÉnùxÉ (Ê¨É.ªÉÚ / ÊnùxÉõ) |  |  |  | Generation (MU/day)
| VÉ±ÉÒªÉ | 100.7698 | 96.39 | 4.3798 | Hydro
| iÉÉ{ÉÒªÉ | 408.1153 | 402.56 | 5.5553 | Coal
| MÉèºÉ | 68.7249 | 61.32 | 7.4049 | Gas
| xÉÉÊ¦ÉEòÒªÉ | 20.0434 | 8.83 | 11.2134 | Nuclear
| EÖò±É (Ê¨É.ªÉÚ / ÊnùxÉ) | 615.7892 | 579.67 | 36.1192 | Total (MU/day)
| ÊxÉªÉÉÇiÉ (Ê¨É.ªÉÚ/ÊnùxÉõ) | 4.691 | 8.76 | -4.069 | Export(MU/day)
| +ÉªÉÉiÉ (Ê¨É.ªÉÚ/ÊnùxÉ) | 57.2374 | 33.78 | 23.4574 | Import(MU/day)
| ¶ÉÖvnù ÊxÉªÉÉÇiÉ / +ÉªÉÉiÉ(Ê¨É.ªÉÚ/ÊnùxÉ) | 52.5465 | 25.02 | 27.5265 | Net Exp. (-) / Net Imp. (+) (MU/day)
11 | =i{ÉÉnùxÉ (=SSÉiÉ¨É ¨ÉÉÄMÉ ÊnùxÉ ¨Éå) |  |  |  | Generation(on peak day at Peak Hr)
| VÉ±ÉÒªÉ | 7405 | 5543 | 1862 | Hydro
| iÉÉ{ÉÒªÉ | 16192 | 16238 | -46 | Coal
| MÉèºÉ | 2886 | 2625 | 261 | Gas
| xÉÉÊ¦ÉEòÒªÉ | 781 | 334 | 447 | Nuclear
| EÖò±É(¨ÉèMÉÉ´ÉÉ]õ) | 27643 | 24874 | 2769 | Total (MW)
| +ÆiÉ®ú IÉäjÉÒªÉ ºÉÆSÉ®úhÉ (=SSÉiÉ¨É ¨ÉÉÄMÉ) |  |  |  | Inter-regional transfer (At Peak Hr.)
| ÊxÉªÉÉÇiÉ (¨ÉèMÉÉ´ÉÉ]õ) | 139 | 27 | 112 | Export(MW)
| +ÉªÉÉiÉ (¨ÉèMÉÉ´ÉÉ]õ) | 2804 | 2831 | -27 | Import(MW)
| ¶Éövnù'ÊxÉªÉÉÇiÉ/+ÉªÉÉiÉ(-/+)(¨ÉèMÉÉ´ÉÉ]õ) | 2665 | 2804 | -139 | Net Export (-) / Import (+) (MW)
12 | ¨ÉÉ½þ Eäò +ÎxiÉ¨É ÊnùxÉ ¨Éå ¨ÉÖJªÉ VÉ±ÉÉ¶ÉªÉÉå |  |  |  | Levels of Major Reservoirs on the
| EòÉ VÉ±ÉÒªÉ ºiÉ®ú (¨ÉÒ]õ®ú) |  |  |  | last day of the month(Mtrs.)
I | ¦ÉÉJÉb÷É | 462.7169 | 476.38 | -13.6631 | Bhakra
ii | {ÉÉåMÉ | 395.4536 | 402.29 | -6.8364 | Pong
III | Ê®ú½þxnù | 255.6662 | 257.56 | -1.8938 | Rihand
iv | ®úÉhÉÉ¦ÉiÉÉ{É ºÉÉMÉ®ú | 345.9267 | 345.15 | 0.77666 | Rana Pratap Sagar
v | MÉÉÄvÉÒ ºÉÉMÉ®ú | 382.6154 | 383.35 | -0.73456 | Gandhi Sagar

## Page2
INSTALLED CAPACITY
Month | ¨ÉÉSÉÇ 2010 | ¨ÉÉSÉÇ 2009
VÉ±ÉÒªÉ | 13310.75 | 13425.15
iÉÉ{ÉÒªÉ | 24851.25 | 22351.68
xÉÉÊ¦ÉEòÒªÉ | 1620 | 1180
Total | 39782 | 36956.83
Gen. At PEAK AVAILABILITY
Month | ¨ÉÉSÉÇ 2010 | ¨ÉÉSÉÇ 2009
VÉ±ÉÒªÉ | 7405 | 5543
iÉÉ{ÉÒªÉ | 19078 | 18863
xÉÉÊ¦ÉEòÒªÉ | 781 | 334
Total | 27264 | 24740

## Page3
GROSS ENERGY GENERATION
Month | VÉ±ÉÒªÉ | iÉÉ{ÉÒªÉ | xÉÉÊ¦ÉEòÒªÉ | Total
¨ÉÉSÉÇ 2010 | 3123.8628 | 14782.046 | 621.3466 | 18527.2554
¨ÉÉSÉÇ 2009 | 2987.94 | 14380.07 | 273.82 | 17641.83
LEVELS
Reserviors | ¨ÉÉSÉÇ 2010 | ¨ÉÉSÉÇ 2009
¦ÉÉEòc÷É | 462.7169 | 476.38
{ÉÉéMÉ | 395.4536 | 402.29
Ê®ú½þxnù | 255.6662 | 257.56
®Éú.¦É.ºÉÉ. | 345.9267 | 345.15
MÉÉÄ.ºÉÉ. | 382.6154 | 383.35

## Page4
4...¨ÉÉ½ ¨ÉÉSÉÇ 2010 ¨Éå Ê´ÉtÖiÉ +É{ÉÚÌiÉ EòÒ ÎºlÉÊiÉ
POWER SUPPLY POSITION FOR THE MONTH OF MARCH 2010
|  |  |  | Average Energy /day (Net) | [5 empty] | 30092
| ®úÉVªÉ/Eäòxpù ¶ÉÉÊºÉiÉ | ={É±É¤vÉiÉÉ(Ê¨É.ªÉÚ./ÊnùxÉ) |  | ¨ÉÉÄMÉ(Ê¨É.ªÉÚ./ÊnùxÉ) |  | Eò¨ÉÒ | Eò¨ÉÒ(¦ÉÊiÉ¶ÉiÉ) | State/UT
|  | Availability (MU/day) |  | Requirement (MU/day) |  | Shortage | Shortage %
| SÉhb÷ÒMÉgø | 3.56 |  | 3.56 |  | 0 | 0 | Chandigarh | 11.8806
| Ênù±±ÉÒ | 57.43 |  | 57.64 |  | 0.21 | 0.36433 | Delhi | 33.63
| ½þÊ®úªÉÉhÉÉ | 79.45 |  | 88.05 |  | 8.6 | 9.7672 | Haryana
| Ê½þ¨ÉÉSÉ±É ¦Énäù¶É | 19.84 |  | 20.96 |  | 1.12 | 5.3435 | H.P.
| VÉ¨¨ÉÚ ´É Eò¶É¨ÉÒ®ú | 29.16 |  | 38.49 |  | 9.33 | 24.2401 | J & K
| {ÉÆVÉÉ¤É | 98.79 |  | 111.51 |  | 12.72 | 11.407 | Punjab
| ®úÉVÉºlÉÉxÉ | 129.24 |  | 129.81 |  | 0.57 | 0.4391 | Rajasthan
| =kÉ®ú ¦Énäù¶É | 171.82 |  | 215.07 |  | 43.25 | 20.1097 | U.P.
| ˆ¢Ö¸ÖÖ›üü | 21.93 |  | 24.72 |  | 2.79 | 11.2864 | Uttarakhand
| Æ ®äú±É | 2.26 |  | 2.26 |  | 0 | 0 | Railways
| IÉäjÉÒªÉ | 613.48 |  | 692.07 |  | 78.59 | 11.3558 | Region
Peak MW
| ®úÉVªÉ/Eäòxpù ¶ÉÉÊºÉiÉ | ={É±É¤vÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) |  | ¨ÉÉÄMÉ (¨ÉèMÉÉ´ÉÉ]õ) |  | Eò¨ÉÒ | Eò¨ÉÒ(¦ÉÊiÉ¶ÉiÉ) | State/UT
|  | Availability (MW) |  | Requirement (MW) |  | Shortage | Shortage %
| SÉhb÷ÒMÉgø | 195 |  | 195 |  | 0 | 0 | Chandigarh
| Ênù±±ÉÒ | 3411 |  | 3411 |  | 0 | 0 | Delhi
| ½þÊ®úªÉÉhÉÉ | 4618 |  | 5398 |  | 780 | 14.4498 | Haryana
* | Ê½þ¨ÉÉSÉ±É ¦Énäù¶É | 1095 |  | 1095 |  | 0 | 0 | H.P.
| VÉ¨¨ÉÚ ´É Eò¶É¨ÉÒ®ú | 1441 |  | 2247 |  | 806 | 35.87 | J & K
| {ÉÆVÉÉ¤É | 5497 |  | 6355 |  | 858 | 13.5012 | Punjab
| ®úÉVÉºlÉÉxÉ | 6567 |  | 6567 |  | 0 | 0 | Rajasthan
| =kÉ®ú ¦Énäù¶É | 8133 |  | 10332 |  | 2199 | 21.2834 | U.P.
| ˆ¢Ö¸ÖÖ›üü | 1207 |  | 1269 |  | 62 | 4.8857 | Uttarakhand
| Æ ®äú±É | 101 |  | 101 |  | 0 | 0 | Railways
| IÉäjÉÒªÉ | 30308 |  | 34164 |  | 3856 | 11.2867 | Region
|  | =SSÉiÉ¨É ={É±É¤vÉiÉÉ EòÉ ÊnùxÉ | Peak Availability on |  | 30.03.2010 | 2000 hrs at | 49.96 | Hz.
|  |  | Diversity Factor |  | 1.0646

## Page5
5...'=kÉ®úÒ IÉäjÉ ¨Éå ´ÉiÉÇ¨ÉÉxÉ ´É¹ÉÇ Eäò nèù®úÉxÉ Ê{ÉUô±Éä ´É¹ÉÇ EòÒ iÉÖ±ÉxÉÉ ¨Éå Ê´ÉtÖiÉ +É{ÉÚÌiÉ EòÒ ÎºlÉÊiÉ
POWER SUPPLY POSITION IN NORTHERN REGION DURING CURRENT YEAR AS COMPARED TO PREVIOUS YEAR
+. +ÉèºÉiÉ >ðVÉÉÇ (xÉä]õ)
A. AVERAGE ENERGY (NET)
¨ÉÉ½þ | 2 0 0 9 - 2 0 10 |  |  |  |  | 2 0 0 8 - 2 0 09 |  |  |  |  | MONTH
| ¨ÉÉÄMÉ (Ê¨É.ªÉÚ./ÊnùxÉ) REQUIREMENT (MU/DAY) | ={É±É¤vÉiÉÉ (Ê¨É.ªÉÚ./ÊnùxÉ) AVAILABILITY (MU/DAY) | Eò¨ÉÒ (Ê¨É.ªÉÚ./ÊnùxÉ) SHORTAGE (MU/DAY) | Eò¨ÉÒ ¦ÉÊiÉ¶ÉiÉ ¨Éå % SHORTAGE | +ÉèºÉiÉ +É´ÉÞÊkÉ (½þ]ÂõWÉÇ) AVERAGE FREQUENCY (Hz) | ¨ÉÉÄMÉ (Ê¨É.ªÉÚ./ÊnùxÉ) REQUIREMENT (MU/DAY) | ={É±É¤vÉiÉÉ (Ê¨É.ªÉÚ./ÊnùxÉ) AVAILABILITY (MU/DAY) | Eò¨ÉÒ (Ê¨É.ªÉÚ./ÊnùxÉ) SHORTAGE (MU/DAY) | Eò¨ÉÒ ¦ÉÊiÉ¶ÉiÉ ¨Éå % SHORTAGE | +ÉèºÉiÉ +É´ÉÞÊkÉ (½þ]ÂõWÉÇ) AVERAGE FREQUENCY (Hz)
+¦Éè±É | 622.91 | 553.81 | 69.1 | 11.09 | 49.46 | 557.68 | 480.29 | 77.39 | 13.88 | 49.22 | APRIL
¨É<Ç | 692.57 | 619.65 | 72.92 | 10.53 | 49.68 | 592.01 | 535.36 | 56.65 | 9.57 | 49.64 | MAY
VÉÚxÉ | 774.46 | 669.73 | 104.73 | 13.52 | 49.51 | 616.21 | 571.75 | 44.46 | 7.22 | 49.56 | JUNE
VÉÖ±ÉÉ<Ç | 782.51 | 696.97 | 85.55 | 10.93 | 49.67 | 700.25 | 624.7 | 75.55 | 10.79 | 49.31 | JULY
+MÉºiÉ | 801.24 | 684.07 | 117.18 | 14.62 | 49.41 | 657.89 | 610.58 | 47.31 | 7.19 | 49.55 | AUGUST
ÊºÉiÉ¨¤É®ú | 741.62 | 645.89 | 95.73 | 12.91 | 49.59 | 664.56 | 592.87 | 71.69 | 10.79 | 49.4 | SEPTEMBER
+C]Úõ¤É®ú | 678.03 | 598.84 | 79.19 | 11.68 | 49.66 | 637.1 | 568.86 | 68.24 | 10.71 | 49.41 | OCTOBER
xÉ´É¨¤É®ú | 620.28 | 558.11 | 62.17 | 10.02 | 49.88 | 594.34 | 522.7 | 71.64 | 12.05 | 49.53 | NOVEMBER
ÊnùºÉ¨¤É®ú | 657.89 | 589.37 | 68.52 | 10.42 | 49.81 | 600.73 | 532.04 | 68.69 | 11.43 | 49.6 | DECEMBER
VÉxÉ´É®úÒ | 663.28 | 589.26 | 74.02 | 11.16 | 49.71 | 626.83 | 546.17 | 79.66 | 12.73 | 49.58 | JANUARY
¡ò®ú´É®úÒ | 655.8 | 595.16 | 60.64 | 9.25 | 49.85 | 631.31 | 545.8 | 85.51 | 13.54 | 49.45 | FEBRUARY
¨ÉÉSÉÇ | 692.07 | 613.48 | 78.59 | 11.36 | 49.61 | 624.16 | 550.63 | 73.53 | 11.78 | 49.6 | MARCH
¤É. =SSÉiÉ¨É ¨ÉÉÄMÉ
B. PEAK DEMAND
¨ÉÉ½þ | 2 0 09 - 2 0 10 |  |  |  |  | 2 0 0 8 - 2 0 0 9 |  |  |  |  | MONTH
| ¨ÉÉÄMÉ (¨ÉèMÉÉ´ÉÉ]õ) REQUIREMENT(MW) | ={É±É¤vÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) AVAILABILITY(MW) | Eò¨ÉÒ (¨ÉèMÉÉ´ÉÉ]õ) SHORTAGE (MW) | Eò¨ÉÒ ¦ÉÊiÉ¶ÉiÉ ¨Éå % SHORTAGE | +ÉèºÉiÉ +É´ÉÞÊkÉ (½þ]ÂõWÉÇ) AVERAGE FREQUENCY (Hz) | ¨ÉÉÄMÉ (¨ÉèMÉÉ´ÉÉ]õ) REQUIREMENT(MW) | ={É±É¤vÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) AVAILABILITY(MW) | Eò¨ÉÒ (¨ÉèMÉÉ´ÉÉ]õ) SHORTAGE (MW) | Eò¨ÉÒ ¦ÉÊiÉ¶ÉiÉ ¨Éå % SHORTAGE | +ÉèºÉiÉ +É´ÉÞÊkÉ (½þ]ÂõWÉÇ) AVERAGE FREQUENCY (Hz)
+¦Éè±É | 33599 | 29348 | 4251 | 12.65 | 49.46 | 30863 | 25564 | 5299 | 17.17 | 49.22 | APRIL
¨É<Ç | 35156 | 29739 | 5417 | 15.41 | 49.68 | 31438 | 27264 | 4174 | 13.28 | 49.64 | MAY
VÉÚxÉ | 38047 | 31751 | 6296 | 16.55 | 49.51 | 32004 | 27826 | 4178 | 13.05 | 49.56 | JUNE
VÉÖ±ÉÉ<Ç | 38979 | 32039 | 6940 | 17.8 | 49.67 | 35393 | 30287 | 5106 | 14.43 | 49.31 | JULY
+MÉºiÉ | 38518 | 31931 | 6587 | 17.1 | 49.41 | 34530 | 29443 | 5087 | 14.73 | 49.55 | AUGUST
ÊºÉiÉ¨¤É®ú | 37178 | 31238 | 5940 | 15.98 | 49.59 | 34734 | 29136 | 5598 | 16.12 | 49.4 | SEPTEMBER
+C]Úõ¤É®ú | 35760 | 31016 | 4744 | 13.27 | 49.66 | 32565 | 28376 | 4189 | 12.86 | 49.41 | OCTOBER
xÉ´É¨¤É®ú | 32117 | 28180 | 3937 | 12.26 | 49.88 | 31072 | 26224 | 4848 | 15.6 | 49.53 | NOVEMBER
ÊnùºÉ¨¤É®ú | 34564 | 30117 | 4447 | 12.87 | 49.81 | 30484 | 27450 | 3034 | 9.95 | 49.6 | DECEMBER
VÉxÉ´É®úÒ | 34214 | 29776 | 4438 | 12.97 | 49.71 | 33169 | 28911 | 4258 | 12.84 | 49.58 | JANUARY
¡ò®ú´É®úÒ | 32597 | 29450 | 3147 | 9.65 | 49.85 | 31947 | 27670 | 4277 | 13.39 | 49.45 | FEBRUARY
¨ÉÉSÉÇ | 34164 | 30308 | 3856 | 11.29 | 49.61 | 32443 | 27678 | 4765 | 14.69 | 49.6 | MARCH

## Page6
6....¨ÉÉSÉÇ 2010 ¨ÉÉ½þ ¨Éå =i{ÉÉnùxÉ EòÉ Ê´ÉiÉ®úhÉ /Ê´ÉÊxÉ¨ÉªÉ
ENTITLEMENTS /SCHEDULE/DRAWAL FOR THE MONTH OF MARCH 2010
(All Figs. In M.Us.
| Gò¨É ºÉÆ. Sr. No. | ®úÉVªÉ/Eäò.¶ÉÉ.¦É./ ¦ÉhÉÉ±ÉÒ | '¶Éb÷¬Ú±Éò Schedule |  | ÊxÉEòÉºÉÒ Drawal | OD/UD +/- | State /UT/ System
| 1 | SÉhb÷ÒMÉgø | 94.06 |  | 110.28 | 16.22 | CHANDIGARH
| 2 | Ênù±±ÉÒ | 1235.63 |  | 1042.27 | -193.36 | DELHI
| 3 | Ê½þ.¦É. | 423.95 |  | 433.53 | 9.58 | H.P
| 4 | ½þÊ®úªÉÉhÉÉ | 681.77 |  | 1105.89 | 424.12 | HARYANA
| 5 | VÉ. ´É Eò. | 644.69 |  | 664.72 | 20.03 | J&K
| 6 | {ÉÆVÉÉ¤É | 960.97 | 752.473 | 1284.27 | 323.3 | PUNJAB
| 7 | ®äú±É | 67.7 |  | 70.01 | 2.31 | RAILWAYS
| 8 | ®úÉVÉºlÉÉxÉ | 1539.65 |  | 1557.35 | 17.7 | RAJASTHAN
| 9 | =kÉ® ¦Énäù¶É | 2434.92 |  | 2647.98 | 213.06 | UP
| 10 | ˆ¢Ö¸ÖÖ›üü | 393.36 |  | 423.64 | 30.28 | UTTARAKHAND
NOTE: The above figures are operational figures and should not be used for ABT based REA.
+xiÉ®ú+IÉäjÉÒªÉ Ê´ÉÊxÉ¨ÉªÉ
INTERREGIONAL EXCHANGES(MU)
+ÉªÉÉiÉ | [5 empty] | Import
1)ä BSÉ.´ÉÒ.b÷Ò.ºÉÒ ºÉ½þ: {ÉÞ¹`ö ¤Éxnù {É®ú |  |  |  |  | 123.98 | (i)From WR over HVDC Vindhyachal B/B .
2)220 EòÒ.´ÉÉä. EòÉä]õÉ-=VVÉèxÉ ºÉä ú |  |  |  |  | 36.19 | (ii) From WR over220 kv Kota/Morak-Badod
3)220 EòÒ.´ÉÉä. ¯ÖÃÖÖî»Öß-ºÉÉ½Öþ{ÉÖ®úÒ ºÉä ú |  |  |  |  | 51.46 | (iii) From E/R over 220 kV Pasauli-Sahupuri
4) BSÉ.´ÉÒ.b÷Ò.ºÉÒ.{É®ú ºÉ½þ: {ÉÞ¹`ö ¤Éxnù |  |  |  |  | 10.84 | (iv)From ER over 400 kv Sasaram Bypass
5)400 êú.¾Öß. ÖÖê¸üÖ¯Öã¸ü ´Öã•ÖÌ±ú¸ü¯Öã¸ü ¯Ö¸ü |  |  |  |  | 259.31 | (v) From ER Over 400 KV Gorakhpur-Muzaffarpur
6)400 êú.¾Öß. ¾ÖÖ×»ÖµÖ¸ü - †ÖÖ¸üÖ ¯Ö¸üü |  |  |  |  | 692.9 | (vi) From WR Over 400 KV Gwalior-Agra
7)400 êú.¾Öß. ¯Ö™ü­ÖÖ-²Ö»ÖßµÖÖ ¯Ö¸ü |  |  |  |  | 323.24 | (vii)From ER Over 400 KV Patna-Balia
8)220 EòÒ.´ÉÉä. †Öî¸îüµÖÖ ´Ö»Ö­Ö¯Öã¸ü ¯Ö¸ü ¨É.¦É.äºÉä |  |  |  |  | 0 | (viii)From WR Over 220 kV Auraiya-Malanpur.
9)400 êú ¾Öß ×²ÖÆüÖ¸ü ¿Ö¸üß±ú ²Ö×»ÖµÖÖ ¯Ö¸ü |  |  |  |  | 173.02 | (ix)From ER Over 400 KV Biharshariff-Balia
[5 empty] | 103.42 | (x) From WR Over 400 KV Kankroli-Zerda
EÖò±É +ÉªÉÉiÉ |  |  |  |  | 1774.36 | Total Import
äÊxÉªÉÉÇiÉ | [5 empty] | Export
1){ÉÎ¶SÉ¨ÉÒ ÊOÉb÷ EòÉä BSÉ.´ÉÒ.b÷Ò.ºÉÒ.{É®ú ºÉ½þ: {ÉÞ¹`ö ¤Éxnù ÊxÉªÉÉÇiÉ |  |  |  |  | 12.37 | (i)ToWR over HVDC Vindhyachal B/B
2)220 EòÒ.´ÉÉä. ºÉä ¨É.¦É. EòÉä |  |  |  |  | 52.92 | (ii)To WR over 220 kV Auraiya-Malanpur.
3)220 EòÒ.´ÉÉä.EòÉä]õÉ+=VVÉèxÉ ºÉä ¨É.¦É. EòÉä |  |  |  |  | 0.66 | (iii)To WR over 220 kv Kota/Morak-Badod
4)Ê¤É½þÉ®ú EòÉä 220/132 EòÒ.´ÉÉä ºÉä |  |  |  |  | 20.79 | (iv) To E/R over 220kV/132kV lines.
5)BSÉ.´ÉÒ.b÷Ò.ºÉÒ.{É®ú ºÉ½þ: {ÉÞ¹`ö ¤Éxnù ÊxÉªÉÉÇiÉ |  |  |  |  | 42.73 | (v) To ER over 400 kv Sasaram Bypass
6) ¯Öæ¾Öá ×ÖÏ›ü úÖê 400 êú¾Öß. ÖÖê¸üÖ¯Öã¸ü - ´Öã•ÖÌ±ú¸ü¯Öã¸ü úÖê |  |  |  |  | 0 | (vi)To ER over 400 KV Gorakhpur-Muzaffarpur
7)]õxÉEò{ÉÖ®ú ºÉä xÉè{ÉÉ±É |  |  |  |  | 15.95 | (vii)ToNepalover132kvTanakpur-Mahender Ngr.
8)400 êú.¾Öß. ¾ÖÖ×»ÖµÖ¸ü - †ÖÖ¸üÖ ¯Ö¸üü |  |  |  |  | 0 | (viii)To WR over 400 KV Gwalior-Agra
9)400 êú.¾Öß. ¯Ö™ü­ÖÖ-²Ö»ÖßµÖÖ ¯Ö¸üü |  |  |  |  | 0 | (ix)To ER over 400 KV Patna-Balia
10)400 êú ¾Öß ×²ÖÆüÖ¸ü ¿Ö¸üß±ú ²Ö×»ÖµÖÖ ¯Ö¸ü |  |  |  |  | 0 | (x)To ER over 400 KV Biharshariff-Balia
[5 empty] | 0 | (xi)To WR over 400 kv Kankroli-Zerda
[5 empty] | 0 | (xii) To ER over 220 kV -Sahupuri-Pasauli
EÖò±É ù ÊxÉªÉÉÇiÉ |  |  |  |  | 145.42 | Total Export

## Page7
7...ˆ.Öê. ´Öë ÛÃ£ÖŸÖ ¸üÖ•µÖÖë/ÃÖÓ¬Ö ¿Ö×ÃÖŸÖ Öê¡ÖÖë ´Öë †Ö²ÖÓ×™üŸÖ ÃÖÓµÖãŒŸÖ ¾Ö êú­¦üßµÖ ÃÖêŒ™ü¸ü ˆ¯ÖµÖÖê•µÖÖë úÖê ÃÖ´ÖÖ×ÆüŸÖ ú¸üŸÖê Æãü‹ ×¾ÖªãŸÖ ˆ¯ÖµÖÖê•µÖÖë úß ÃÖÓÃ£ÖÖ×¯ÖŸÖ Ö´ÖŸÖÖ (´ÖêÖÖ¾ÖÖ™ü ´Öë)
INSTALLED CAPACITY (IN MW) OF POWER UTILITIES IN THE STATES/UTS LOCATED IN NORTHERN REGION
INCLUDING ALLOCATED SHARES IN JOINT & CENTRAL SECTOR UTILITIES
(As on 31.03.2010,as per CEA )
State | Ownership Sector | Modewise breakup
|  | Thermal |  |  | TotalThermal | Nuclear | Hydro | RES | Grand Total
|  | Coal | Gas | Diesel |  |  | (Renewable) | ( MNRE)
Delhi ×¤ü»»Öß | State | 135 | 600.4 | 0 | 735.4 | 0 | 0 | 0 | 735.4
| Private | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Central | 2467.96 | 207.61 | 0 | 2675.57 | 122.08 | 581.62 | 0 | 3379.27
| Sub-Total | 2602.96 | 808.01 | 0 | 3410.97 | 122.08 | 581.62 | 0 | 4114.67
Haryana Æü×¸üµÖÖÖÖ | State | 2615 | 0 | 3.92 | 2618.92 | 0 | 884.51 | 68.7 | 3572.13
| Private | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 7.8
| Central | 402.99 | 535.29 | 0 | 938.28 | 109.16 | 443.17 | 0 | 1490.61
| Sub-Total | 3017.99 | 535.29 | 3.92 | 3557.2 | 109.16 | 1327.68 | 76.5 | 5070.54
Himachal Pradesh | State | 0 | 0 | 0.13 | 0.13 | 0 | 393.6 | 275.83 | 669.56
×Æü´ÖÖ“Ö»Ö | Private | 0 | 0 | 0 | 0 | 0 | 386 | 0 | 386
| Central | 118.3 | 61.88 | 0 | 180.18 | 34.08 | 760.34 | 0 | 974.6
| Sub-Total | 118.3 | 61.88 | 0.13 | 180.31 | 34.08 | 1539.94 | 275.83 | 2030.16
J&K •Ö´´Öæ ¾Ö ú¿´Öß¸üü | State | 0 | 175 | 8.94 | 183.94 | 0 | 780 | 129.33 | 1093.27
| Private | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Central | 263.7 | 129.14 | 0 | 392.84 | 77 | 700.53 | 0 | 1170.37
| Sub-Total | 263.7 | 304.14 | 8.94 | 576.78 | 77 | 1480.53 | 129.33 | 2263.64
Punjab ¯ÖÓ•ÖÖ²Ö | State | 2630 | 0 | 0 | 2630 | 0 | 2230.23 | 220.65 | 5080.88
| Private | 0 | 0 | 0 | 0 | 0 | 0 | 58.25 | 58.25
| Central | 578.19 | 263.92 | 0 | 842.11 | 208.04 | 732.66 | 0 | 1782.81
| Sub-Total | 3208.19 | 263.92 | 0 | 3472.11 | 208.04 | 2962.89 | 278.9 | 6921.94
Rajasthan ¸üÖ•ÖÃ£ÖÖ­Ö | State | 3365 | 443.8 | 0 | 3808.8 | 0 | 987.96 | 30.25 | 4827.01
| Private | 135 | 0 | 0 | 135 | 0 | 0 | 895.9 | 1030.9
| Central | 649.48 | 221.23 | 0 | 870.71 | 573 | 466.84 | 0 | 1910.55
| Sub-Total | 4149.48 | 665.03 | 0 | 4814.51 | 573 | 1454.8 | 926.15 | 7768.46
Uttar Pradesh ˆ.¯ÖÏ. | State | 4072 | 0 | 0 | 4072 | 0 | 524.1 | 25.1 | 4621.2
| Private | 300 | 0 | 0 | 300 | 0 | 0 | 562.6 | 862.6
| Central | 2540.84 | 549.97 | 0 | 3090.81 | 335.72 | 1073.32 | 0 | 4499.85
| Sub-Total | 6912.84 | 549.97 | 0 | 7462.81 | 335.72 | 1597.42 | 587.7 | 9983.65
Uttrakhand ˆ¢Ö¸üÖÖ›ü | State | 0 | 0 | 0 | 0 | 0 | 1252.15 | 132.92 | 1385.07
| Private | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 400
| Central | 261.26 | 69.35 | 0 | 330.61 | 22.28 | 267.03 | 0 | 619.92
| Sub-Total | 261.26 | 69.35 | 0 | 330.61 | 22.28 | 1919.18 | 132.92 | 2404.99
Chandigarh “Ö›üßÖœÍü | State | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Private | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Central | 27.09 | 15.32 | 0 | 42.41 | 8.84 | 46.74 | 0 | 97.99
| Sub-Total | 27.09 | 15.32 | 0 | 42.41 | 8.84 | 46.74 | 0 | 97.99
| Central - UA | 713.19 | 290.35 | 0 | 1003.54 | 129.8 | 399.95 | 0 | 1533.29
Total N.R ãú»Ö ˆ¢Ö¸üß Öê¡Ö | State | 12817 | 1219.2 | 12.99 | 14049.19 | 0 | 7052.55 | 882.78 | 21984.52
| Private | 435 | 0 | 0 | 435 | 0 | 786 | 1524.55 | 2745.55
| Central | 8023 | 2344.06 | 0 | 10367.06 | 1620 | 5472.2 | 0 | 17459.26
| Grand Total | 21275 | 3563.26 | 12.99 | 24851.25 | 1620 | 13310.75 | 2407.33 | 42189.33

## Page8
8...'=kÉ®úÒ IÉäjÉ ¨ÉåÇ ¨ÉÉSÉÇ 2010 ¨ÉÉ½þ Eäò nùÉè®úÉxÉ =i{ÉÉnùxÉ EäòxpùÉä EòÉ EòÉªÉÇ ÊxÉ¹{ÉÉnùxÉ
PERFORMANCE OF GENERATING STATIONS IN THE NORTHERN REGION DURING THE MONTH OF MARCH 2010
Ê´ÉtÖiÉ Eäòxpù |  | ºÉÆºlÉÉÊ{ÉiÉ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) |  | ¦É¦ÉÉ´ÉÒ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) | OÉÉäºÉ(Ê¨É.ªÉ.Ú) | xÉè]õ (Ê¨É.ªÉÚ.) | ÃÖ“ÖµÖß (1.4.09 ÃÖê) | ÃÖ“ÖµÖß (1.4.09 ÃÖê) | POWER STATION
|  | INSTALLED CAPACITY (MW) |  | EFFECTIVE CAPACITY (MW) | GROSS ( MU) | NET ( MU) | COMMULATIVE FROM 01.04.2009 (GROSS MU) | COMMULATIVE FROM 01.04.2009 (NET MU)
1.EäòxpùÒªÉ ºÉèC]õ®ú | [8 empty] | A.CENTRAL SECTOR
®úÉ.iÉÉ.Ê´É.ÊxÉ. | [8 empty] | NTPC
¤Énù®ú{ÉÖ®ú iÉÉ. Ê´É.Eäò. |  | 3x100 + 2x210 | 720 | 705 | 357.61 | 321.849 | 5107.94 | 4597.146 | Badarpur TPS | 412.91 | 371.619
ËºÉMÉ®úÉè±ÉÒ iÉÉ.Ê´É.Eäò. |  | 5x200 + 2x500 | 2000 | 2000 | 1551.64 | 1396.476 | 16264.43 | 14637.987 | Singrauli STPS | 1463.25 | 1316.925
Ê®ú½þxnù iÉÉ.Ê´É.Eäò. |  | 2x500+2x500 | 2000 | 2000 | 1486.72 | 1338.048 | 16743.4 | 15069.06 | Rihand STPS | 1444.77 | 1300.293
nùÉnù®úÒ iÉÉ.Ê´É.Eäò |  | 4x210+1x490 | 1330 | 1330 | 798.38 | 718.542 | 7833.5 | 7050.147 | Dadri NCTPS | 630.17 | 567.153
>ÄðSÉÉ½þÉ®ú iÉÉ.Ê´É.Eäò-1 |  | 2x210 | 420 | 420 | 323.3 | 290.97 | 3582.5 | 3224.25 | Unchahar TPS Stage-I | 315.75 | 284.175
>ÄðSÉÉ½þÉ®ú iÉÉ.Ê´É.Eäò-2 |  | 2x210 | 420 | 420 | 326.52 | 293.868 | 3478.96 | 3131.064 | Unchahar TPS Stage-2 | 300.06 | 270.054
>ÄðSÉÉ½þÉ®ú iÉÉ.Ê´É.Eäò-3 |  | 1X210 | 210 | 210 | 156.04 | 140.436 | 1890.78 | 1701.702 | Unchahar TPS Stage-3 | 157.82 | 142.038
]õÉÆb÷É iÉÉ.Ê´É.Eäò. |  | 4x110 | 440 | 440 | 250.88 | 225.792 | 3555.23 | 3199.707 | Tanda TPS | 311.74 | 280.566
EÖò±É 'EòÉäªÉ±ÉÉ |  |  | 7540 | 7525 | 5251.09 | 4725.981 | 58456.74 | 52611.068 | Total Coal | 5036.47 | 4532.823
+x]õÉ MÉè.Ê´É.Eäò. |  | 3x88 + 1x149 | 413 | 413 | 281.21 | 278.3979 | 3001.26 | 2971.2474 | Anta GPS | 252.38 | 249.8562
+Éè®èúªªÉÉ MÉè.Ê´É.Eäò. |  | 4x112 + 2x102 | 652 | 652 | 385.28 | 381.4272 | 4528.37 | 4483.0863 | Auraiya GPS | 402.92 | 398.8908
nùÉnù®úÒ MÉè.Ê´É.Eäò. |  | 4x131 +2x146.5 | 817 | 817 | 564.63 | 558.9837 | 5605.6 | 5549.544 | Dadri GPS | 527.4 | 522.126
¡ò®úÒnùÉ¤ÉÉnù MÉè.Ê´É.Eäò. |  | 2x143+1x144 | 430 | 430 | 291.09 | 288.1791 | 3211.95 | 3179.8305 | Faridabad GPS | 254.92 | 252.3708
EÖò±É MÉèºÉ |  |  | 2312 | 2312 | 1522.21 | 1506.9879 | 16347.18 | 16183.7082 | Total Gas | 1437.62 | 1423.2438
EÖò±É ®úÉ.iÉÉ.Ê´É.ÊxÉ. |  |  | 9852 | 9837 | 6773.3 | 6232.9689 | 74803.92 | 68794.7703 | Total NTPC | 6474.09 | 5956.0668
®úÉ.VÉ.Ê´É.ÊxÉ. | [8 empty] | NHPC
¤Éè®úÉºÉÚÚ±É VÉ.Ê´É.Eäò. |  | 3 x 66 | 198 | 180 | 77.22 | 76.45 | 622.87 | 616.3 | Baira Siul HPS | 87.23 | 86.36
ºÉ±ÉÉ±É VÉ.Ê´É.Eäò. |  | 3 x 115 + 3x115 | 690 | 690 | 177.95 | 176.17 | 3024.4 | 2997.08 | Salal HPS | 245.37 | 242.92
]õxÉEò{ÉÖ®ú VÉ.Ê´É.Eäò. |  | 3 x 40 | 120 | 94.2 | 20.14 | 19.94 | 471.1 | 466.48 | Tanakpur HPS | 17.02 | 16.85
SÉ¨Éä®úÉ VÉ.Ê´É.Eäò.+1 |  | 3 x 180 | 540 | 540 | 135.13 | 133.78 | 2065.79 | 2046.84 | Chamera HPS-Stg I | 190.02 | 188.12
SÉ¨Éä®úÉ VÉ.Ê´É.Eäò.+2 |  | 3x100 | 300 | 300 | 71.33 | 70.62 | 1368.85 | 1356.22 | Chamera HPS-Stg II | 106.21 | 105.15
=®úÒ VÉ.Ê´É.Eäò. |  | 4 x 120 | 480 | 480 | 338.14 | 334.76 | 2704.57 | 2677.46 | Uri HPS | 347.49 | 344.02
¬ÖîÖî»Öß ÖÓÖÖ, (ˆ¢Ö¸üÖÓ“Ö»Ö) | VÉ.Ê´É.Eäò. | 4x70 | 280 | 280 | 41.7 | 41.28 | 1133.22 | 1122.34 | Dhauliganga HPS | 40 | 39.6
¤ãü»ÖÆüÃŸÖß •Ö.×¾Ö.êú. |  | 3x130 | 390 | 390 | 123.56 | 122.32 | 2263.7 | 2241.16 | Dulhasti HPS | 151.6 | 150.08
EÖò±É ®úÉ.VÉ.Ê´É.ÊxÉ. |  |  | 2998 | 2954.2 | 985.17 | 975.32 | 13654.5 | 13523.88 | Total NHPC | 1184.94 | 1173.1
xÉÉ.Ê´É.ÊxÉ. | [8 empty] | NPC
®úÉ.+É.>ð.Eäò.-1 |  | 1x100 | 100 | 100 | 0 | 0 | 0 | 0 | RAPS-1 RAPS-A | 0 | 0
®úÉ.+É.>ð.Eäò.-2 |  | 1x200 | 200 | 200 | 144.968 | 125.46 | 937.238 | 820.44 | RAPS-2 | 0 | 0
®úÉ.+É.>ð.Eäò.-3 |  | 1x220 | 220 | 220 | 112.9263 | 96.56 | 1218.4703 | 1021.0235 | RAPS-3 RAPS-B | 112.478 | 96.422
®úÉ.+É.>ð.Eäò.-4 |  | 1x220 | 220 | 220 | 113.2023 | 98.669 | 1075.7011 | 923.8486 | RAPS-4 | 89.042 | 75.86
®úÉ.+É.>ð.Eäò.-5 |  | 1X220 | 220 | 220 | 150.77 | 137.82 | 271.39 | 248.8 | RAPS-5 RAPS-C
®úÉ.+É.>ð.Eäò.-6 |  | 1X220 | 220 | 220 |  |  |  |  | RAPS-6
EÖò±É'®úÉ.+É.>ð.Eäò. |  |  | 1180 | 1180 | 521.8666 | 458.509 | 3502.7994 | 3014.1121 | Total RAPS | 201.52 | 172.282
xÉ®úÉè®úÉ +É.>ð.Eäò.-1 |  | 1x220 | 220 | 220 | 99.48 | 82.838 | 817.55 | 664.6579 | NAPS-1 | 73.87 | 58.822
xÉ®úÉè®úÉ +É.>ð.Eäò.-2 |  | 1x220 | 220 | 220 | 0 | 0 | 0 | 0 | NAPS-2 | 0 | 0
EÖò±É xÉ®úÉè®úÉ +É.>ð.Eäò. |  |  | 440 | 440 | 99.48 | 82.838 | 817.55 | 664.6579 | Total NAPS | 73.87 | 58.822
EÖò±É xÉÉ.Ê´É.ÊxÉ. |  |  | 1620 | 1620 | 621.3466 | 541.347 | 4320.3494 | 3678.77 | Total NPC | 275.39 | 231.104
2.ºÉÆªÉÖHò ºÉèC]õ®ú | [8 empty] | B.JOINT SECTOR
¦ÉÉ.¤ªÉÉ.¦É.¤ÉÉä. | [8 empty] | BBMB
¦ÉÉJÉc÷É (¤ÉÉÆªÉÉ ) |  | 5x108 | 540 | 540 | 143.616 |  | 2115.942 |  | Bhakra (Left) | 132.58
¦ÉÉJÉc÷É ( nùÉÆªÉÉ) |  | 5x157 | 785 | 785 | 163.351 |  | 2381.516 |  | Bhakra (Right) | 103.49
MÉÆMÉÚ´ÉÉ±É |  | 1x29.25 +2x24.20 | 77.65 | 77.65 | 39.849 |  | 555.307 |  | Ganguwal | 39.87
EòÉä]õ±ÉÉ |  | 1x29.25 +2x24.20 | 77.65 | 77.65 | 38.02 |  | 440.148 |  | Kotla | 35.99
EòÖò±É ¦ÉÉJÉc÷É {ÉÊ®úºÉ®ú |  |  | 1480.3 | 1480.3 | 384.836 | 380.639 | 5492.913 | 5424.543 | Total Bhakra Complex | 311.93 | 307.16
näù½þ®ú VÉ.Ê´É.Eäò. |  | 6 x 165 | 990 | 990 | 157.599 | 156.153 | 2937.908 | 2921.828 | Dehar HPS | 161.15 | 158.88
{ÉÉåMÉ VÉ.Ê´É.Eäò. |  | 6x66 | 396 | 396 | 25.643 | 25.163 | 950.49 | 922.13 | Pong HPS | 25.83 | 25.2
EÖòò±É ¦ÉÉ.¤ªÉÉ.¦É.¤ÉÉä. |  |  | 2866.3 | 2866.3 | 568.078 | 561.955 | 9381.311 | 9268.501 | Total BBMB | 498.91 | 491.24
ÃÖŸÖ»Öã•Ö •Ö»Ö ×¾ÖªãŸÖ ×­ÖÖ´Ö, | [8 empty] | SJVNL
xÉÉ{ÉlÉÉ ZÉÉEòc÷Ò VÉ.Ê´É.Eäò |  | 6x250 | 1500 | 1500 | 295.922 | 293.278 | 7018.805 | 6956.849 | Nathpa Jhakri HPS | 294.832 | 292.336
Ê].VÉ.Ê´É.ÊxÉ. | [8 empty] | THDC Ltd.
™êüÆü¸üß •Ö.×¾Ö.êú. |  | 4x250 | 1000 | 1000 | 247.654 | 244.682 | 2116.7711 | 2091.364 | Tehri HPP | 197.04 | 194.676

## Page9
Ê´ÉtÖiÉ Eäòxpù |  | ºÉÆºlÉÉÊ{ÉiÉ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) |  | ¦É¦ÉÉ´ÉÒ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) | OÉÉäºÉ(Ê¨É.ªÉ.Ú) | xÉè]õ (Ê¨É.ªÉÚ.) | ÃÖ“ÖµÖß (1.4.09 ÃÖê) | ÃÖ“ÖµÖß (1.4.09 ÃÖê) | POWER STATION
|  | INSTALLED CAPACITY (MW) |  | EFFECTIVE CAPACITY (MW) | GROSS ( MU) | NET ( MU) | COMMULATIVE FROM 01.04.2009 (GROSS MU) | COMMULATIVE FROM 01.04.2009 (NET MU)
3.®úÉVªÉ ºÉèC]õ®ú | [8 empty] | C.STATE SECTOR
1. Ênù±±ÉÒ | [8 empty] | 1. DELHI
EòÉäªÉ±ÉÉ | [8 empty] | Coal
<xpù¦ÉºlÉ.iÉÉ.Ê´É.Eäò. |  |  | 0 | 0 | 0 | 0 | 448.613 | 386.087 | Indra Prastha TPS | 92.051 | 81.92
®úÉVÉPÉÉ]õ iÉÉ.Ê´É.Eäò. |  | 2 x 67.5 | 135 | 135 | 85.16 | 75.658 | 645.118 | 554.369 | Rajghat TPS | 73.601 | 63.889
EÖò±É 'EòÉäªÉ±ÉÉ |  |  | 135 | 135 | 85.16 | 75.658 | 1093.731 | 940.456 | TOTAL COAL | 165.652 | 145.809
MÉèºÉ ]õ®ú¤ÉÉ<ÇxÉ |  | 6x30 + 3x30 | 270 | 270 | 117.47 | 112.999 | 1498.897 | 1446.085 | Gas Turbines | 123.364 | 119.13
¦ÉMÉÊiÉ MÉèºÉ ]õ®ú¤ÉÉ<ÇxÉ |  | 2x104.6+1x121.2 | 330.4 | 330.4 | 230.136 | 224.314 | 2452.712 | 2385.684 | Pragati Gas Turbine | 212.67 | 206.805
EÖò±É MÉèºÉ |  |  | 600.4 | 600.4 | 347.606 | 337.313 | 3951.609 | 3831.769 | TOTAL GAS | 336.034 | 325.935
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | R.E.S | 0 | 0
EÖò±É Ênù±±ÉÒ |  |  | 735.4 | 735.4 | 432.766 | 412.971 | 5045.34 | 4772.225 | Total DELHI | 501.686 | 471.744
2. ½þÊ®úªÉÉhÉÉ | [8 empty] | 2. HARYANA
EòÉäªÉ±ÉÉ | [8 empty] | COAL
¡ò®úÒnùÉ¤ÉÉnù iÉÉ.Ê´É.Eäò. |  | 1x60 | 60 | 55 | 24.934 | 21.013 | 383.782 | 322.108 | Faridabad TPS | 46.51 | 39.58
{ÉÉxÉÒ{ÉiÉ iÉÉ.Ê´É.Eäò. |  | 4x110 + 2x210+2x250 | 1360 | 1360 | 803.468 | 725.206 | 10206.817 | 9241.027 | TDLTPS (Panipat) | 937.66 | 851.039
ªÉ¨ÉÖxÉÉ­ÖÖ¸ü | iÉÉ.Ê´É.Eäò. | 2x300 | 600 | 600 | 294.841 | 266.586 | 4275.91 | 3878.701 | DCRTPP(Yamunanagar) | 310.774 | 281.986
|  | 1X600 | 600 | 600 | 54.97 | 43.429 | 76.406 | 56.95 | RGTPP(Hissar)
EÖò±É iÉÉ{ÉÒªÉ |  |  | 2620 | 2615 | 1178.213 | 1056.234 | 14942.915 | 13498.786 | TOTAL THERMAL | 1294.944 | 1172.605
b÷Ò÷WÉ±É |  |  | 3.92 | 3.92 |  |  |  |  | Diesel
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ | [8 empty] | R.E.S
®úÉVªÉ-'{ÉÎ¶SÉ¨ÉÒ.ªÉ¨ÉÖxÉÉ.EäòxÉÉ±É |  | 6x8+2x7.2 | 62.4 | 62.4 | 13.247 | 13.09 | 231.416 | 229.531 | State-WYC Yamuna Ngr. (SHP) | 14.169 | 14.01
|  |  | 0.3 | 0.3 |  |  |  |  | Kakroi Micro Hydel Project
|  |  | 6 | 6
†Ö‡Ô ¯Öß ¯Öß |  |  | 7.8 | 7.8 |  |  |  |  | IPP
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ |  |  | 76.5 | 76.5 | 13.247 | 13.09 | 231.416 | 229.531 | Total RES | 14.169 | 14.01
EÖò±É ½þÊ®úªÉÉhÉÉ |  |  | 2700.42 | 2695.42 | 1191.46 | 1069.324 | 15174.331 | 13728.317 | Total HARYANA | 1309.113 | 1186.615
3. Ê½þþ¨ÉÉSÉ±É ¦Énäù¶É | [8 empty] | 3.HIMACHAL PRADESH
VÉ±ÉÒªÉ | [8 empty] | HYDRO
»ÖÖ•Öá |  | 3X42 | 126 | 126 | 32.446 |  | 601.734 |  | Larji | 32.185
ÊMÉÊ®ú |  | 2X30 | 60 | 60 | 4.492 |  | 110.148 |  | Giri | 5.234
¤ÉººÉÒ |  | 4x15 | 60 | 60 | 18.144 |  | 189.199 |  | Bassi | 18.533
¦ÉÉ¦ÉÉ |  | 3x40 | 120 | 120 | 24.68 |  | 625.131 |  | Bhabha | 32.825
+ÉxvÉÞÉ |  | 3x5.65 | 16.95 | 16.95 | 3.104 |  | 40.416 |  | Andhra | 2.59
¤ÉxÉä®ú |  | 3x4 | 12 | 12 | 2.975 |  | 32.042 |  | Baner | 3.633
Ê¤ÉxÉ´ÉÉ |  | 2x3 | 6 | 6 | 3.053 |  | 25.578 |  | Binwa | 3.171
MÉÉVÉ |  | 3x3.5 | 10.5 | 10.5 | 2.667 |  | 35.947 |  | Gaj | 4.014
×£Ö¸üÖê™ü |  | 3x1.5 | 4.5 | 4.5 | 0.446 |  | 8.033 |  | Thirot | 0.402
PÉÉxÉ´ÉÒ |  | 2x11.25 | 22.5 | 22.5 | 4.002 |  | 70.24 |  | Ghanvi | 3.16
ÖÖê»Öß |  | 12 | 12 | 12 | 3.214 |  | 33.355 |  | Khauli | 4.321
»Ö‘Öã •Ö»ÖßµÖ |  |  | 17.3 | 17.3 | 1.8 |  | 33.642 |  | Micros(State's) | 2.912
EÖò±É |  |  | 450.45 | 466.45 | 101.023 | 100.01 | 1805.465 | 1787.41 | Total | 112.98 | 111.85
¨É±ÉÉxÉÉ( +É<Ç.{ÉÒ. {ÉÒ.) |  | 2x43 | 86 | 86 | 11.799 | 11.68 | 301.77 | 298.73 | MALANA HEP (IPP) | 11.974 | 11.85
¤ÉÉºÉ{ÉÉ( +É<Ç.{ÉÒ. {ÉÒ.) |  | 3x100 | 300 | 300 | 36.674 | 36.31 | 1303.464 | 1290.42 | BASPA HEP(IPP) | 40.282 | 39.88
¯ÖÖŸÖßúÖ¸üß | ('+É<Ç.{ÉÒ. {ÉÒ.) | 2x8 | 16 | 16 | 2.605 | 2.58 | 36.092 | 35.73 | Patikari(IPP) | 2.283 | 2.26
|  | 2x5 | 10 | 10 | 3.499 | 3.46 | 8.744 | 8.65 | Toss(IPP)
»Ö‘Öã •Ö»ÖßµÖ(('+É<Ç.{ÉÒ. {ÉÒ. | ('+É<Ç.{ÉÒ. {ÉÒ.) |  | 90.35 | 90.35 | 27.68 | 27.4 | 301.266 | 298.24 | Micros (IPP's ) | 20.256 | 20.05
EÖò±É VÉ±ÉÒªÉ |  |  | 952.8 | 968.8 | 183.28 | 181.44 | 3756.801 | 3719.18 | Total Hydro | 187.775 | 185.89
b÷Ò÷WÉ±É ºÉè]õ |  |  | 0.13 | 0.13 |  |  |  |  | Diesel Gen. Sets
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ |  |  | 275.83 | 275.83 |  |  |  |  | R.E.S-State
EÖò±É Ê½þ¨ÉÉSÉ±É ¦Énäù¶É |  |  | 1228.76 | 1244.76 | 183.28 | 181.44 | 3756.801 | 3719.18 | TOTAL HP | 187.775 | 185.89
®úÉVªÉ-

## Page10
Ê´ÉtÖiÉ Eäòxpù |  | ºÉÆºlÉÉÊ{ÉiÉ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) |  | ¦É¦ÉÉ´ÉÒ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) | OÉÉäºÉ(Ê¨É.ªÉ.Ú) | xÉè]õ (Ê¨É.ªÉÚ.) | ÃÖ“ÖµÖß (1.4.09 ÃÖê) | ÃÖ“ÖµÖß (1.4.09 ÃÖê) | POWER STATION
|  | INSTALLED CAPACITY (MW) |  | EFFECTIVE CAPACITY (MW) | GROSS ( MU) | NET ( MU) | COMMULATIVE FROM 01.04.2009 (GROSS MU) | COMMULATIVE FROM 01.04.2009 (NET MU)
4 VÉ¨¨ÉÚ ´É Eò¶É¨ÉÒ®ú | [8 empty] | 4.JAMMU & KASHMIR
VÉ±ÉÒªÉ | [8 empty] | HYDRO
²ÖÖ»ÖßÆüÖ¸ü (•Ö.×¾Ö.êú.) |  | 2x150 | 300 | 300 | 184.645 | 183.955 | 2703.747 | 2699.278 | Baghlihar HPS | 255.575 | 255.374
—Öê»Ö´Ö ­Ö¤üß ‘ÖÖ™üß | [8 empty] | Jhelum River Basin
ÊxÉSÉ±ÉÒ ZÉä±É¨É |  | 3x35 | 105 | 105 | 36.586 | 36.559 | 391.16 | 390.937 | Lower Jhelum | 48.23 | 48.21
>ð{É®Òú ÊºÉxvÉ-1 |  | 2x11.3 | 22.6 | 22.6 | 5.7756 | 5.7681 | 90.5941 | 90.4893 | Upper Sindh-I | 6.799 | 6.793
>ð{É®Òú ÊºÉxvÉ-2 |  | 3x35 | 105 | 105 | 0 | 0 | 144.803 | 144.465 | Upper Sindh-II | 18.088 | 18.04
MÉxnù®ú´É±É |  | 2x3+2x4.5 | 15 | 15 | 1.6928 | 1.6838 | 18.1798 | 18.0793 | Ganderbal | 2.0924 | 2.084
ú¸ü­ÖÖ |  |  | 2 | 2 | 0 | 0 | 0 | 0 | Karna | 0 | 0
¯ÖÆü»ÖÖÖ¾Ö | 3x1.5(2m/cinstalled) |  | 3 | 3 | 0 | 0 | 0 | 0 | Pahalgam | 0 | 0
×“Ö­ÖÖ²Ö ‘ÖÖ™üß | [8 empty] | Chenab Basin
ÊSÉxÉÉxÉÒ 1,2,3 |  | 5x4.66+2x1+3x2.5 | 32.8 | 32.8 | 7.53 | 7.51 | 60.322 | 60.112 | Chenani - I,II,III | 8.647 | 8.643
³ÖÖ¤ü¸ü¾ÖÖÆü |  |  | 1 | 1 | 0 | 0 | 0 | 0 | Badarwah | 0 | 0
¸üÖ¾Öß ‘ÖÖ™üß | [8 empty] | Ravi Basin
ÃÖê¾ÖÖ-III |  | 3x3 | 9 | 9 | 0 | 0 | 4.392 | 4.266 | Sewa-III | 0.586 | 0.585
EÖò±É VÉ±ÉÒªÉ |  |  | 595.4 | 595.4 | 236.2294 | 235.4759 | 3413.1979 | 3407.6266 | Total Hydro | 340.0174 | 339.729
b÷Ò÷WÉ±É ºÉè]õ |  | 8.94 | 8.94 | 7.18 | 0 | 0 | 0 | 0 | Diesel Gen. Sets | 0 | 0
{É¨{ÉÉä®ú VÉÒ.]õÒ. |  | 7x25 | 175 | 175 | 0 | 0 | 12.536 | 12.536 | Pampoer GT | 0 | 0
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ |  |  | 129.33 | 129.33 | 0 | 0 | 0 | 0 | R.E.S-State | 0 | 0
EÖò±É VÉ¨¨ÉÚ ´É Eò¶É¨ÉÒ®ú |  |  | 908.67 | 906.91 | 236.2294 | 235.4759 | 3425.7339 | 3420.1626 | Total J&K | 340.0174 | 339.729
5 {ÉÆVÉÉ¤É | [8 empty] | 5. PUNJAB
VÉ±ÉÒªÉ | [8 empty] | HYDRO
ú ¶ÉÉxÉxÉ |  | 4x15 + 1x50 | 110 | 110 | 35.495 | 35.171 | 510.529 | 504.472 | Shanan(Jogindernagar) | 40.162 | 39.707
ªÉÚ.¤ÉÒ.b÷Ò.ºÉÒ. |  | 6x15 | 90 | 90 | 32.46 | 32.26 | 1089.098 | 334.43 | UBDC | 32.409 | 32.216
¨ÉÖEäòÊ®úªÉxÉ |  | 6x15 + 6x19.5 | 207 | 207 | 19.787 | 19.25 | 885.93 | 862.146 | Mukerian HP | 17.52 | 17.4
+ÉxÉÆnù{ÉÖ®ú ºÉÊ½þ¤É |  | 4x33.5 | 134 | 134 | 44.38 | 43.991 | 574.409 | 569.755 | Anandpur Sahib HPS | 21.1 | 20.828
®úhÉVÉÒiÉ ºÉÉMÉ®ú |  | 4x150 | 600 | 600 | 81.435 | 81.17 | 1068.765 | 1065.141 | Ranjit Sagar HPS | 100.342 | 100.017
EÖò±É VÉ±ÉÒªÉ |  |  | 1141 | 1141 | 213.557 | 211.842 | 4128.731 | 3335.944 | Total Hydro | 211.533 | 210.168
EòÉäªÉ±ÉÉ | [8 empty] | COAL
¦ÉÊ]õõxb÷É iÉÉ.Ê´É.Eäò. |  | 4x110 | 440 | 400 | 159.25 | 143.099 | 2723.351 | 2413.967 | GNDTPS (Bhatinda) | 195.506 | 172.321
®úÉä{Éc÷ Ê´É.,Eäò. |  | 6x210 | 1260 | 1260 | 810.705 | 745.66 | 10056.44 | 9238.095 | GGSTPS (Ropar) | 788.03 | 723.462
±Éè½þ®úÉ ¨ÉÉä½þ¤¤ÉiÉ iÉÉ.Ê´É.Eäò. |  | 2x210+2x250 | 920 | 920 | 706.469 | 652.435 | 7515.915 | 6923.652 | GHTPS(Lehra Mohabat) | 561.993 | 516.532
•Ö»ÖÖê›Íüß ŸÖÖ.×¾Ö.êú. |  | 1x10 | 10 | 10 | 0 | 0 | 0 | 0 | Jalkheri Rice Straw fired | 0 | 0
EÖò±É iÉÉ{ÉÒªÉ |  |  | 2630 | 2590 | 1676.424 | 1541.194 | 20295.706 | 18575.714 | Total Thermal | 1545.529 | 1412.315
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ | [8 empty] | R.E.S
®úÉVªÉ |  |  | 220.62 | 220.62 | 25.277 | 25.28 | 240.329 | 240.332 | State | 15.92 | 15.92
+É<Ç.{ÉÒ. {ÉÒ. |  |  | 58.25 | 58.25 |  |  |  |  | IPP
EÖò±É {ÉÆVÉÉ¤É |  |  | 4049.87 | 4009.87 | 1915.258 | 1778.316 | 24664.766 | 22151.99 | Total PUNJAB | 1772.982 | 1638.403
6 ®úÉVÉºlÉÉxÉ | [8 empty] | 6. RAJASTHAN
VÉ±ÉÒªÉ ú | [8 empty] | HYDRO
¨ÉÉ½þÒ VÉ±ÉÒªÉ ú-1 |  | 2x25 | 50 | 50 | 3.061 | 3.048 | 63.657 | 63.179 | Mahi H P S.-I | 0 | 0
¨ÉÉ½þÒ VÉ±ÉÒªÉ ú-2 |  | 2x45 | 90 | 90 | 1.627 | 1.605 | 21.526 | 21.318 | Mahi H P S.-II | 0 | 0
“Ö´²Ö»Ö •Ö.×¾Ö.êú. | [8 empty] | Chambal Project
¸üÖÖÖ ¯ÖÏŸÖÖ¸ü ÃÖÖÖ¸ü |  | 4x43 | 172 | 172 | 0 | 0 | 143.857 | 143.575 | Rana Partap Sagar | 0 | 0
ÖÖò¬Öß ÃÖÖÖ¸ü |  | 5x23 | 115 | 115 | 7.228 | 7.17 | 130.622 | 130.05 | Gandhi Sagar | 10.081 | 10.017
•Ö¾ÖÖÆü¸ü ÃÖÖÖ¸ü |  | 3x33 | 99 | 99 | 0.45 | 0.426 | 117.23 | 116.888 | Jawahar Sagar | 0.85 | 0.819
»Ö‘Öã •Ö»ÖßµÖ ¯Ö×¸üµÖÖê•Ö­ÖÖ |  |  |  |  | 0.093 | 0.088 | 5.792 | 5.65 | MMH | 0.036 | 0.024
EÖò±É VÉ±ÉÒªÉ |  |  | 526 | 526 | 12.459 | 12.337 | 482.684 | 480.66 | Total Hydro | 10.967 | 10.86
EòÉäªÉ±ÉÉ | [8 empty] | COAL |  |  | 281.82
EòÉä]õÉ iÉÉ.Ê´É.Eäò. |  | 2x110 + 3x210+2x195 | 1240 | 1240 | 913.123 | 826.18 | 9054.763 | 8133.27 | Kota TPS | 744.303 | 637.73 | 55.0429
ºÉÚ®úiÉMÉgø iÉÉ.Ê´É.Eäò. |  | 2x250+2x250+2x250 | 1500 | 1500 | 880.362 | 803.134 | 9582.761 | 8704.276 | Suratgarh TPS | 824.585 | 749.984
×‘Ö¸üÖ»Ö ŸÖÖ.×²Ö.êú.-I |  | 1x125 | 125 | 125 | 61.77 | 53.293 | 416.112 | 350.423 | Giral LTPS-I | 73.904 | 62.257
×‘Ö¸üÖ»Ö ŸÖÖ.×²Ö.êú._II |  | 1x125 | 125 | 125 | 60.386 | 52.353 | 248.911 | 213.341 | Giral LTPS-II
ÃÖŸÖ¯Öã¸üÖ ŸÖÖ.×¾Ö.êú. |  | 5x62.5 | 312.5 | 312.5 | 174.762 | 157.975 | 1800.1005 | 1614.67 | Satpura TPS | 161.1055 | 144.255
|  | 1x135 | 135 | 135 | 63.677 | 55.466 | 249.239 | 211.589 | Jalipa Kapurdi TPS IPP
|  | 1x250 | 250 | 250 | 88.956 | 77.283 | 246.197 | 214.513 | Chhabra TPS
|  | 1x125 | 125 | 125 | 0 | 0 | 1.762 | 1.227 | Barsingsar LTPS
EÖò±É 'EòÉäªÉ±ÉÉ |  |  | 3812.5 | 3812.5 | 2243.036 | 2025.684 | 21586.016 | 19432.264 | Total Coal | 1803.8975 | 1594.226
®úÉ¨ÉMÉgø VÉÒ.]õÒ. |  | 1x37.5+1x35.5+1x37.8+1x3 | 113.8 | 110.5 | 32.608 | 31.14 | 352.908 | 334.07 | Ramgarh Gas | 29.754 | 27.405
¬ÖÖî»Ö¯Öã¸ü •Öß.™üß. |  | 3x110 | 330 | 330 | 228.047 | 218.725 | 2425.642 | 2363.922 | Dholpur CCGT | 205.652 | 200.195
ãú»Ö ÖîÃÖ |  |  | 443.8 | 440.5 | 260.655 | 249.865 | 2778.554 | 2697.989 | Total Gas | 235.406 | 227.6
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ | [8 empty] | R.E.S
®úÉVªÉ |  |  | 30.25 | 30.25 |  |  |  |  | State
+É<Ç.{ÉÒ. {ÉÒ. |  |  | 895.9 | 895.9 |  |  |  |  | IPP
¯Ö¾Ö­Ö ‰ú•ÖÖÔ |  |  |  |  | 81.985 | 81.985 | 1069.296 | 1069.293 | Wind | 74.65 | 74.65
²ÖÖòµÖÖê ´ÖÖÃÖ ‰ú•ÖÖÔ |  |  | 30.5 | 30.5 | 14.979 | 14.979 | 175.291 | 175.279 | BP | 15.144 | 15.14
[5 empty] | 103.923 | 103.923 | 1144.043 | 1144.047 | CPP | 65.264 | 65.26
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ |  |  | 926.15 | 926.15 | 200.887 | 200.887 | 2388.644 | 2388.639 | Total RES | 155.058 | 155.05
EÖò±É ®úÉVÉºlÉÉxÉ |  |  | 5708.45 | 5705.15 | 2717.037 | 2488.773 | 27235.877 | 24999.533 | Total RAJASTHAN | 2205.3285 | 1987.736

## Page11
Ê´ÉtÖiÉ Eäòxpù |  | ºÉÆºlÉÉÊ{ÉiÉ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) |  | ¦É¦ÉÉ´ÉÒ IÉ¨ÉiÉÉ (¨ÉèMÉÉ´ÉÉ]õ) | OÉÉäºÉ(Ê¨É.ªÉ.Ú) | xÉè]õ (Ê¨É.ªÉÚ.) | ÃÖ“ÖµÖß (1.4.09 ÃÖê) | ÃÖ“ÖµÖß (1.4.09 ÃÖê) | POWER STATION
|  | INSTALLED CAPACITY (MW) |  | EFFECTIVE CAPACITY (MW) | GROSS ( MU) | NET ( MU) | COMMULATIVE FROM 01.04.2009 (GROSS MU) | COMMULATIVE FROM 01.04.2009 (NET MU)
7.ˆ¢Ö¸ÖÖ›üü | [8 empty] | 7.UTTARAKHAND
VÉ±ÉÒªÉ | [8 empty] | HYDRO
ÊUô¤É®úÉä |  | 4x60 | 240 | 240 | 29.626 | 29.575 | 587.9658 | 586.8619 | Chibro | 30.222 | 29.92
JÉÉänù®úÒ |  | 4x30 | 120 | 120 | 14.0469 | 13.99 | 275.866 | 274.9508 | Khodri | 14.63 | 14.48
¬Öú¸üÖ­Öß |  | 3x11.25 | 33.75 | 33.75 | 5.0805 | 5.05 | 105.0775 | 104.5587 | Dhakrani | 5.26 | 5.21
¬ÖÖ»Öß¯Öã¸ü |  | 3x17 | 51 | 51 | 7.408 | 7.383 | 160.149 | 159.7556 | Dhalipur | 7.62 | 7.54
ãúÆüÖ»Ö |  | 3x10 | 30 | 30 | 5.719 | 5.6936 | 112.553 | 112.1275 | Kulhal | 6.116 | 6.05
¨ÉxÉä®úÒ ¦ÉÉ±ÉÒ-1 |  | 3x30 | 90 | 90 | 30.18 | 30.107 | 449.07 | 447.927 | Maneri Bhalli Stg.-1 | 30.49 | 30.19
¨ÉxÉä®úÒ ¦ÉÉ±ÉÒ-2 |  | 4x76 | 304 | 304 | 57.99 | 57.775 | 1198.03 | 1193.3704 | Maneri Bhalli Stg.-2 | 55.67 | 55.11
×“Ö»ÖÖ |  | 4x36 | 144 | 144 | 61.198 | 61.115 | 739.496 | 737.698 | Chilla | 54.57 | 54.02
¯ÖÖ£Ö¸üß |  | 3x6.8 | 20.4 | 20.4 | 11.027 | 10.956 | 84.026 | 83.301 | Pathri | 6.609 | 6.54
´ÖÖêÆü´´Ö¤ü¯Öã¸ü |  | 3x3.1 | 9.3 | 9.3 | 4.663 | 4.629 | 42.832 | 42.472 | Mohamadpur | 4.206 | 4.16
®úÉ¨ÉMÉÆMÉÉ |  | 3x66 | 198 | 198 | 19.823 | 19.722 | 174.277 | 173.225 | Ramganga | 17.319 | 17.15
JÉ]õÒ¨ÉÉ |  | 3x13.8 | 41.4 | 41.4 | 10.104 | 10.053 | 151.004 | 150.246 | Khatima | 8.35 | 8.27
Ö»ÖÖêÖß |  | 2x1+2x0.5 | 3 | 3 | 0.126 | 0.12 | 2.0045 | 1.9571 | Galogi | 0.25 | 0.25
ãú»Ö µÖÖêÖ |  |  | 1284.85 | 1284.85 | 256.9914 | 256.1686 | 4082.3508 | 4068.451 | Total | 241.312 | 238.89
×¾ÖÂÖã ¯ÖÏµÖÖÖ •Ö.×¾Ö.êú. |  | 4x100 | 400 | 400 | 61.573 | 60.96 | 1951.946 | 1932.42 | Vishnu Prayag HEP(IPP) | 66.64 | 65.97
EÖò±É VÉ±ÉÒªÉ |  |  | 1684.85 | 1684.85 | 318.5644 | 317.1286 | 6034.2968 | 6000.871 | Total Hydro | 307.952 | 304.86
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ | [8 empty] | R.E.S
®úÉVªÉ |  |  | 132.92 | 132.92 |  |  |  |  | State
+É<Ç.{ÉÒ. {ÉÒ. |  |  | 0 | 0 |  |  |  |  | IPP
EÖò±É ˆ¢Ö¸ÖÖ›üü |  |  | 1817.77 | 1817.77 | 318.5644 | 317.1286 | 6034.2968 | 6000.871 | Total UTTARAKHAND | 307.952 | 304.86 |  | 16605.76
8 =kÉ®ú ¦Énäù¶É | [8 empty] | 8. UTTAR PRADESH
VÉ±ÉÒªÉ | [8 empty] | HYDRO
Ê®ú½þxnù |  | 6x50 | 300 | 300 | 30.88 |  | 400.899 |  | Rihand | 48.723
+Éä¤É®úÉ |  | 3x33 | 99 | 99 | 12.293 |  | 149.842 |  | Obra | 19.075
¨ÉÉiÉÉ]õÒ±ÉÉ |  | 3x10.2 | 30.6 | 30.6 | 7.836 |  | 112.063 |  | Matatila | 0
JÉÉ®úÉ |  | 3x24 | 72 | 72 | 11.94 |  | 249.419 |  | Khara | 12.707
EÖò±É VÉ±ÉÒªÉ |  |  | 501.6 | 501.6 | 62.949 | 62.32 | 912.223 | 903.12 | Total Hydro | 80.505 | 79.7
EòÉäªÉ±ÉÉ | [8 empty] | COAL
+Éä¤É®úÉ |  |  | 1400 | 1372 | 400.011 |  | 5151.046 |  | ObraTPS | 421.7 |  | +Éä¤É®úÉ -2 | 3x100 | 300 | 282 | 503.194
{ÉxÉEòÒ |  |  | 220 | 210 | 118.108 |  | 1228.78 |  | Panki TPS | 119.464 |  | {ÉxÉEòÒ-2 | 2x110 | 220 | 210 | 73.132
½þ®únÖù+ÉMÉÆVÉ |  |  | 230 | 220 | 75.112 |  | 803.746 |  | Harduaganj TPS | 86.22 |  | ½þ®únÖù+ÉMÉÆVÉ+¤ÉÒ | 1x60 | 60 | 55 | 51.736
{ÉÉ®úÒSUôÉ |  |  | 640 | 640 | 349.424 |  | 3728.023 |  | Parichha TPS | 368.635 |  | {ÉÉ®úÒSUôÉ | 2x110+2X210 | 640 | 640 | 302.462
+xÉ{ÉÉ®úÉ |  |  | 1630 | 1630 | 1181.199 |  | 11991.978 |  | Anpara TPS |  |  | +xÉ{ÉÉ®úÉ+-1 | 3x210 | 630 | 630
|  |  | 300 | 300 | 93.798 |  | 114.963 |  | Rosa TPP IPP
EÖò±É 'EòÉäªÉ±ÉÉ |  |  | 4420 | 4372 | 2217.652 | 1951.53 | 23018.534 | 20256.29 | Total Coal | 2051.657 | 1805.46 | EÖò±É 'EòÉäªÉ±ÉÉ |  | 1850 | 1817 | 930.524
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ | [8 empty] | R.E.S
®úÉVªÉ |  |  | 25.1 | 25.1 | 322.8 | 322.8 | 1532.56 | 1532.56 | State | 63.6 | 157
+É<Ç.{ÉÒ. {ÉÒ. |  |  | 562.6 | 562.6 |  |  |  |  | IPP
EÖò±É =kÉ®¦Énäù¶É |  |  | 5509.3 | 5461.3 | 2603.401 | 2336.65 | 25463.317 | 22691.99 | Total UP | 2195.762 | 2042.16
4.EÖò±É IÉäjÉÒªÉ | [8 empty] | D. TOTAL REGIONAL
EÖò±É IÉäjÉÒªÉ VÉ±ÉÒªÉ |  |  | 12975.15 |  | 3123.8628 | 3095.7785 | 50899.3185 | 49687.9923 | Total Regional Hydro | 3314.4714 | 3282.559
EÖò±É IÉäjÉÒªÉ'EòÉäªÉ±ÉÉ |  |  | 21157.5 |  | 12651.575 | 11376.281 | 139393.635 | 125314.581 | Total Regional Coal | 11898.1495 | 10663.238
EÖò±É IÉäjÉÒªÉ MÉèºÉ |  |  | 3531.2 |  | 2130.471 | 2094.1659 | 23089.875 | 22726.0053 | Total Regional Gas | 2009.06 | 1976.7788
EÖò±É IÉäjÉÒªÉ b÷Ò÷WÉ±É |  |  | 14.99 |  | 0 | 0 | 0 | 0 | Total Regional Diesel | 0 | 0
EÖò±É IÉäjÉÒªÉ iÉÉ{ÉÒªÉ |  |  | 24703.69 |  | 14782.046 | 13470.4469 | 162483.506 | 148040.5769 | Total Regional Thermal | 13907.2095 | 12640.0168
EÖò±É IÉäjÉÒªÉ xÉÉÊ¦ÉEòÒªÉ |  |  | 1620 |  | 621.3466 | 541.347 | 4320.3446 | 3678.771 | Total Regional Nuclear | 275.39 | 231.104
†¯Ö¸ü´¯Ö¸üÖÖŸÖ ‰ú•ÖÖÔ ÄÖÖêŸÖ |  |  | 1407.81 |  | 562.211 | 562.057 | 4392.946 | 4391.17 | Total Regional R.E.S | 248.747 | 341.98
EÖò±É IÉäjÉÒªÉ |  |  | 40706.65 |  | 19089.4664 | 17669.6294 | 256476.0564 | 236939.3294 | TOTAL REGIONAL | 17745.8179 | 16495.6598
NOTE : | Ê]õ{{ÉhÉÒ
( a ) | The auxiliary consumption for hydro and gas units of state sector has been taken as 1% and 3% respectively.
( b ) | The auxiliary consumption for coal fired units in the state sector has been assumed at 12% for UP | [6 empty] | and 10% for rest coal fired units.
[c] | RES=Renewable Energy Sources includes SHP (Small Hydro Project) , wind power, BG(Biomass Gasifier) BP(Biomass Power),U&I(Urban & Industrial Waste Power)

## Page12
9...¨ÉÉ½ ¨ÉÉSÉÇ 2010 Eäò =kÉ®úÒ IÉäjÉ Eäò iÉÉ{ÉÒªÉ/MÉèºÉÒªÉ/xÉÉÊ¦ÉEòÒªÉ Ê´ÉtÖiÉ Eäòxpù EòÉ {±Éx]õ ±ÉÉäb÷ ¡èòC]õ®ú ({ÉÒ.B±É.B¡ò.)
PLANT LOAD FACTOR (PLF) OF THERMAL/GAS/NUCLEARPOWER STATIONS
IN NORTHERN REGION DURING THE MONTH OF MARCH 2010
2004-01-01
| Gò¨É ºÉÆ. S.No. | Ê´ÉtÖiÉ Eäòxpù | ¦É¦ÉÉ´ÉÒ IÉ¨ÉiÉÉ Effective Capacity (MW) | ¨ÉÉ½þ ¨Éå =i{ÉÉnùxÉ Gen. Of the month (MU) | ¨ÉÉ½þ EòÉ {ÉÒ.B±É.B¡ò. PLF of the month ( %) | 01.04.2009 ºÉä =i{ÉÉnùxÉ (Ê¨É.ªÉÚ.) Gen.since 01.04.2009(MU) | 01.04.2009 ºÉä {ÉÒ.B±É.B¡ò. PLF since 01.04.2009 (%) | Power Station
[11 empty] | 463.4 | 1220.93
| +. | EäòxpùÒªÉ ºÉäC]õ®ú | [5 empty] | A.CENTRAL SECTOR
| 1 | ®úÉ.iÉÉ.Ê´É.ÊxÉ. | [5 empty] | 1.NTPC
|  | ¤Énù®ú{ÉÖ®ú iÉÉ. Ê´É.Eäò. | 705 | 357.61 | 68.18 | 5107.94 | 82.71 | Badarpur TPS |  |  | 463.4 | 1305.28
|  | ËºÉMÉ®úÉè±ÉÒ iÉÉ.Ê´É.Eäò. | 2000 | 1551.64 | 104.28 | 16264.43 | 92.83 | Singrauli STPS |  |  | 396.2 | 1220.93
|  | Ê®ú½þxnù iÉÉ.Ê´É.Eäò. | 2000 | 1486.72 | 99.91 | 16743.4 | 95.57 | Rihand STPS |  |  | 479.57 | 1140.99
|  | nùÉnù®úÒ iÉÉ.Ê´É.Eäò | 1330 | 798.38 | 80.68 | 7833.5 | 67.24 | Dadri NCTPS |  |  | 488.1 | 1116.6
|  | >ÄðSÉÉ½þÉ®ú iÉÉ.Ê´É.Eäò.+1 | 420 | 323.3 | 103.46 | 3582.5 | 97.37 | Unchahar TPS Stg.-I |  |  | 1827.27 | 4783.8
|  | >ÄðSÉÉ½þÉ®ú iÉÉ.Ê´É.Eäò.+2 | 420 | 326.52 | 104.49 | 3478.96 | 94.56 | Unchahar TPS Stg-II
|  | >ÄðSÉÉ½þÉ®ú iÉÉ.Ê´É.Eäò.+3 | 210 | 156.04 | 99.87 | 1890.78 | 102.78 | Unchahar TPS Stg-III
|  | ]õÉÄb÷É iÉÉ.Ê´É.Eäò. | 440 | 250.88 | 76.64 | 3555.23 | 92.24 | Tanda TPS
|  | EÖò±É iÉÉ{ÉÒªÉ | 7525 | 5251.09 | 93.79 | 58456.74 | 88.68 | Total Thermal
|  | +x]õÉ MÉè.Ê´É.Eäò. | 413 | 281.21 | 91.52 | 3001.26 | 82.96 | Anta GPS
|  | +Éè®èúªªÉÉ MÉè.Ê´É.Eäò. | 652 | 385.28 | 79.42 | 4528.37 | 79.28 | Auraiya GPS
|  | nùÉnù®úÒ MÉè.Ê´É.Eäò. | 817 | 564.63 | 92.89 | 5605.6 | 78.32 | Dadri GPS
|  | ¡ò®úÒnùÉ¤ÉÉnù MÉè.Ê´É.Eäò. | 430 | 291.09 | 90.99 | 3211.95 | 85.27 | Faridabad GPS
|  | EÖò±É MÉèºÉ | 2312 | 1522.21 | 88.49 | 16347.18 | 80.71 | Total Gas
|  | EÖò±É ®úÉ.iÉÉ.Ê´É.ÊxÉ. | 9837 | 6773.3 | 92.55 | 74803.92 | 86.81 | Total NTPC
| 2 | xÉÉ.Ê´É.ÊxÉ. | [5 empty] | 2.NPC
|  | ®úÉ.+É.>ð.Eäò. | 300 | 144.968 | 64.95 | 937.238 | 35.66 | RAPS-A
|  | ®úÉ.+É.>ð.Eäò.+¤É | 440 | 226.1286 | 69.08 | 2294.1714 | 59.52 | RAPS-B
|  | xÉ®úÉè®úÉ +É.>ð.Eäò. | 440 | 99.48 | 30.39 | 817.55 | 21.21 | NAPS
|  | EÖò±É xÉÉ.Ê´É.ÊxÉ. | 1180 | 500.7266 | 57.04 | 4199.7294 | 40.63 | Total NPC
|  | EÖò±É EäòxpùÒªÉ ºÉäC]õ®ú | 11017 | 7274.0266 | 88.74 | 79003.6494 | 81.86 | Total Central Sector
| ¤É. | ®úÉVªÉ ºÉèC]õ®ú | [5 empty] | B.STATE SECTOR
| 1 | Ênù±±ÉÒ | [5 empty] | 1.DELHI
|  | <xpù¦ÉºlÉ.iÉÉ.Ê´É.Eäò. | 0 | 0 | 0 | 448.613 | 24.46 | Inder Prastha TPS
|  | ®úÉVÉPÉÉ]õ iÉÉ.Ê´É.Eäò. | 135 | 85.16 | 84.79 | 645.118 | 54.55 | Rajghat TPS
|  | EÖò±É iÉÉ{ÉÒªÉ | 135 | 85.16 | 84.79 | 645.118 | 54.55 | Total Thermal
|  | MÉèºÉ ]õ®ú¤ÉÉ<ÇxÉ | 270 | 117.47 | 58.48 | 1498.897 | 63.37 | Gas Turbine
|  | ¦ÉMÉÊiÉ MÉèºÉ ]õ®ú¤ÉÉ<ÇxÉ | 330.4 | 230.136 | 93.62 | 2452.712 | 84.74 | Pragati Gas Turbine
|  | EÖò±É MÉèºÉ | 600.4 | 347.606 | 77.82 | 3951.609 | 75.13 | Total GAS
|  | EÖò±É Ênù±±ÉÒ | 735.4 | 432.766 | 79.1 | 4596.727 | 71.35 | Total Delhi
| 2 | ½þÊ®úªÉÉhÉÉ | [5 empty] | 2. HARYANA
|  | ¡ò®úÒnùÉ¤ÉÉnù iÉÉ.Ê´É.Eäò. | 55 | 24.934 | 60.93 | 383.782 | 79.66 | Faridabad TPS
|  | {ÉÉxÉÒ{ÉiÉ iÉÉ.Ê´É.Eäò. | 1360 | 803.468 | 79.41 | 10206.817 | 85.67 | Panipat TPS
|  | ªÉ¨ÉÖxÉÉ­ÖÖ¸ü | 600 | 294.841 | 66.05 | 4275.91 | 81.35 | DCRTPP(Yamunanagar)
|  | EÖò±É iÉÉ{ÉÒªÉ | 2015 | 1123.243 | 74.92 | 14866.509 | 84.22 | Total Thermal
|  | EÖò±É ½þÊ®úªÉÉhÉÉ | 2015 | 1123.243 | 74.92 | 14866.509 | 84.22 | Total Haryana
|  | APR | 4 | 30
|  | AUG | 8 | 31
|  | DEC | 12 | 31
|  | FEB | 2 | 28 |  |  | 30 | APR | 30
|  | JAN | 1 | 31 |  |  | 31 | MAY | 31
|  | JUL | 7 | 31 |  |  | 30 | JUN | 30
|  | JUN | 6 | 30 |  |  | 31 | JUL | 31
|  | MAR | 3 | 31 |  |  | 31 | AUG | 31
|  | MAY | 5 | 31 |  |  | 30 | SEP | 30
|  | NOV | 11 | 30 |  |  | 31 | OCT | 31
|  | OCT | 10 | 31 |  |  | 30 | NOV | 214
|  | SEP | 9 | 30 |  |  | 31 | DEC
|  |  |  | 365 |  |  | 31 | JAN
[7 empty] | 28 | FEB
|  |  | #N/A | 30 |  |  | 31 | MAR
31
9 |  |  |  | 365 |  | 214
31

## Page13
9...¨ÉÉ½ ¨ÉÉSÉÇ 2010 Eäò =kÉ®úÒ IÉäjÉ Eäò iÉÉ{ÉÒªÉ/MÉèºÉÒªÉ/xÉÉÊ¦ÉEòÒªÉ Ê´ÉtÖiÉ Eäòxpù EòÉ {±Éx]õ ±ÉÉäb÷ ¡èòC]õ®ú ({ÉÒ.B±É.B¡ò.)
PLANT LOAD FACTOR (PLF) OF THERMAL/GAS/NUCLEARPOWER STATIONS
IN NORTHERN REGION DURING THE MONTH OF MARCH 2010
Gò¨É ºÉÆ. S.No. | Ê´ÉtÖiÉ Eäòxpù | ¦É¦ÉÉ´ÉÒ IÉ¨ÉiÉÉ Effective Capacity (MW) | ¨ÉÉ½þ ¨Éå =i{ÉÉnùxÉ Gen. Of the month (MU) | ¨ÉÉ½þ EòÉ {ÉÒ.B±É.B¡ò. PLF of the month ( %) | 01.04.2009 ºÉä =i{ÉÉnùxÉ (Ê¨É.ªÉÚ.) Gen.since 01.04.2009(MU) | 01.04.2009 ºÉä {ÉÒ.B±É.B¡ò. PLF since 01.04.2009 (%) | Power Station
3 | VÉ¨¨ÉÚ ´É Eò¶É¨ÉÒ®ú | [5 empty] | 3.J&K
| {É¨{ÉÉä®ú VÉÒ.]õÒ. | 175 | 0 | 0 | 12.536 | 0.82 | Pampore Gas Turbine
| EÖò±É VÉ¨¨ÉÚ ´É Eò¶É¨ÉÒ®ú | 175 | 0 | 0 | 12.536 | 0.82 | Total J&K
4 | {ÉÆVÉÉ¤É | [5 empty] | 4.PUNJAB
| ¦É]õÒxb÷É iÉÉ.Ê´É.Eäò. | 400 | 159.25 | 53.51 | 2723.351 | 77.72 | GNDTPS (Bhatinda)
| ®úÉä{Éc÷ Ê´É.,Eäò. | 1260 | 810.705 | 86.48 | 10056.44 | 91.11 | GGSTPS (Ropar)
| ±Éè½þ®úÉ ¨ÉÉä½þ¤¤ÉiÉ iÉÉ.Ê´É.Eäò. | 920 | 706.469 | 103.21 | 7515.915 | 93.26 | Lehra Mohabat TPS
| EÖò±É {ÉÆVÉÉ¤É | 2580 | 1676.424 | 87.34 | 20295.706 | 89.8 | Total Punjab
5 | ®úÉVÉºlÉÉxÉ | [5 empty] | 5.RAJASTHAN
| EòÉä]õÉ iÉÉ.Ê´É.Eäò. | 1240 | 913.123 | 98.98 | 9054.763 | 83.36 | Kota TPS
| ºÉÚ®úiÉMÉgø iÉÉ.Ê´É.Eäò. | 1500 | 880.362 | 78.89 | 9582.761 | 72.93 | Suratgarh TPS
| ×Ö¸üÖ»Ö ŸÖÖ.×¾Ö.êú. | 125 | 61.77 | 66.42 | 416.112 | 38 | Giral LTPS-I
|  | 2865 | 1855.255 | 87.04 | 19053.636 | 75.92 | Total Thermal
| ®úÉ¨ÉMÉgø VÉÒ.]õÒ. | 110.5 | 32.608 | 39.66 | 352.908 | 36.46 | Ramgarh Gas Turbine
| ¬ÖÖî»Ö¯Öã¸ü •Öß.™üß. | 330 | 228.047 | 92.88 | 2425.642 | 83.91 | Dholpur CCGT
| ãú»Ö ÖîÃÖ | 440.5 | 260.655 | 79.53 | 2778.55 | 72.01 | Total GAS
| EÖòÖ±É ®úÉVÉºlÉÉxÉ | 3305.5 | 2115.91 | 86.04 | 21832.186 | 75.4 | Total Rajasthan
6 | =kÉ® ¦Énäù¶É | [5 empty] | 6.UTTAR PRADESH
| +Éä¤É®úÉ | 1372 | 400.011 | 39.19 | 5151.046 | 42.86 | Obra
| {ÉxÉEòÒ | 210 | 118.108 | 75.59 | 1228.78 | 66.8 | Panki
| ½þ®únÖù+ÉMÉÆVÉ | 220 | 75.112 | 45.89 | 803.746 | 41.71 | Harduaganj
| {ÉÉ®úÒSUôÉ | 640 | 349.424 | 73.38 | 3728.023 | 66.5 | Parichha
| +xÉ{ÉÉ®úÉ | 1630 | 1181.199 | 97.4 | 11991.978 | 83.98 | Anpara
| EÖò±É =kÉ® ¦Énäù¶É | 4072 | 2196.482 | 72.5 | 22903.573 | 64.21 | Total U.P. (Thermal)
| ®úÉVªÉ ºÉèC]õ®ú MÉèºÉÒªÉ | 1215.9 | 608.261 | 67.24 | 6742.695 | 63.3 | State Sector (Gas)
| ®úÉVªÉ ºÉèC]õ®ú iÉÉ{ÉÒªÉ | 11667 | 6936.564 | 79.91 | 77764.542 | 76.09 | State Sector (Thermal)*
| EÖò±É ®úÉVªÉ ºÉäC]õ®ú | 12882.9 | 7544.825 | 78.72 | 84507.237 | 74.88 | State Sector (Total)
| IÉäjÉ (iÉÉ{ÉÒªÉ) | 19192 | 12187.654 | 85.35 | 136221.282 | 81.03 | Region (Thermal)*
| IÉäjÉ (MÉèºÉÒªÉ) | 3527.9 | 2130.471 | 81.17 | 23089.875 | 74.71 | Region (Gas )
| IÉäjÉ (xÉÉÊ¦ÉEòÒªÉ | 1180 | 500.7266 | 57.04 | 4199.7294 | 40.63 | Region (Nuclear)
| EÖò±É IÉäjÉÒªÉ | 23899.9 | 14818.8516 | 83.34 | 163510.8864 | 78.1 | TOTAL REGIONAL

## Page14
10...¨ÉÉ½ ¨ÉÉSÉÇ 2010 Eäò IÉäjÉÒªÉ =SSÉiÉ¨É ¨ÉÉÄMÉ Eäò ºÉ¨ÉªÉ ¨Éå =kÉ®úÒ IÉäjÉ Eäò ºÉ¦ÉÒ ºÉÆPÉ]õEòÉå ºÉä +Æ¶ÉnùÉxÉ
CONTRIBUTIONS FROM THE CONSTITUENTS OF NORTHERN REGIONAT THE TIME OF
REGIONAL PEAK DEMAND DURING THE MONTH OF MARCH 2010
|  | iÉÉ®úÒJÉ | DATE | 30.03.2010
|  | ºÉ¨ÉªÉ | TIME | 2000 | Hrs.
|  | +É´ÉÞÊiÉú | FREQUENCY | 49.96 | Hz.
(ºÉ¦ÉÒ +ÉÄEòcä÷ ¨ÉèMÉÉ´ÉÉ]õ ¨Éå)
Gò¨É ºÉÆ. Sl.No. | ®úÉVªÉ/Eäò.¶ÉÉ./ ¦ÉhÉÉ±ÉÒ | =i{ÉÉnùxÉ Generation | [5 empty] | EÖò±É TOTAL
|  | VÉ±ÉÒªÉ Hydro | EòÉäªÉ±ÉÉ VÉÊ±ÉiÉ Coal fired | MÉèºÉ VÉÊ±ÉiÉ Gas fired | xÉÉÊ¦ÉEòÒªÉ Nuclear | ¯Ö¾Ö­Ö ‰ú•ÖÖÔ Wind | ²ÖÖòµÖÖê ´ÖÖÃÖ Bio mass
®úÉ.iÉÉ.Ê´É.ÊxÉ.
1 | ¤Énù®ú{ÉÖ®ú iÉÉ. Ê´É.Eäò. |  | 660 |  |  |  |  | 660
2 | ËºÉMÉ®úÉè±ÉÒ iÉÉ.Ê´É.Eäò. |  | 2099 |  |  |  |  | 2099
3 | Ê®ú½þxnù iÉÉ.Ê´É.Eäò. |  | 2073 |  |  |  |  | 2073
4 | >ÄðSÉÉ½þÉ®ú iÉÉ.Ê´É.Eäò. |  | 1093 |  |  |  |  | 1093
5 | nùÉnù®úÒ iÉÉ.Ê´É.Eäò. |  | 833 |  |  |  |  | 833 |  |  | 200
6 | nùÉnù®úÒ MÉè.Ê´É.Eäò. |  |  | 777 |  |  |  | 777
7 | +x]õÉ MÉè.Ê´É.Eäò. |  |  | 368 |  |  |  | 368
8 | +Éè®èúªªÉÉ MÉè.Ê´É.Eäò. |  |  | 597 |  |  |  | 597
9 | ¡ò®úÒnùÉ¤ÉÉnù MÉè.Ê´É.Eäò. |  |  | 375 |  |  |  | 375
10 | ']õÉÆb÷É iÉÉ.Ê´É.Eäò |  | 297 |  |  |  |  | 297
xÉÉ.Ê´É.ÊxÉ.
11 | ®úÉ.+É.>ð.Eäò. |  |  |  | 646 |  |  | 646
12 | xÉ®úÉè®úÉ +É.>ð.Eäò. |  |  |  | 135 |  |  | 135
¦ÉÉ.¤ªÉÉ.¦É.¤ÉÉä.
13 | ¦ÉÉJÉ®úÉ {ÉÊ®úºÉ®ú | 692 | [5 empty] | 692
14 | näù½þ®ú VÉ.Ê´É.Eäò. | 495 | [5 empty] | 495
15 | {ÉÉåMÉ VÉ.Ê´É.Eäò. | 56 | [5 empty] | 56
| ®úÉ.VÉ.Ê´É.ÊxÉ. | [6 empty] | 0
16 | ºÉ±ÉÉ±É VÉ.Ê´É.Eäò. | 291 | [5 empty] | 291
17 | ]õxÉEò{ÉÖ®ú VÉ.Ê´É.Eäò. | 31 | [5 empty] | 31 |  |  | 227
18 | SÉ¨Éä®úÉ VÉ.Ê´É.Eäò.1,2 | 740 | [5 empty] | 740
19 | ¤Éè®úÉºªÉÚ±É VÉ.Ê´É.Eäò. | 179 | [5 empty] | 179
20 | =®úÒ VÉ.Ê´É.Eäò. | 483 | [5 empty] | 483
21 | ¬ÖÖî»ÖßÖÓÖÖ •Ö.×¾Ö.êú. | 207 | [5 empty] | 207
22 | ¤ãü»ÖÆüÃŸÖß •Ö.×¾Ö.êú. | 392 | [5 empty] | 392
23 | xÉÉ{ÉlÉÉ ZÉÉEòc÷Ò | 1573 | [5 empty] | 1573 |  | xÉÉ{ÉlÉÉ ZÉÉEòc÷Ò | 1269 |  | 1269 | Naptha Jhakri HPS
24 | Ê].VÉ.Ê´É.ÊxÉ. | 702 | [5 empty] | 702
®úÉVªÉ
25 | ½þ®úªÉÉhÉÉ | 16 | 1615 | 0 |  |  |  | 1631
26 | Ê½þ.¦Énäù¶É | 227 | [5 empty] | 227
27 | VÉ ´É Eò | 87 |  | 0 |  |  |  | 87
28 | {ÉÆVÉÉ¤É | 298 | 2362 |  |  |  |  | 2660
29 | ®úÉVÉºlÉÉxÉ | 227 | 2567 | 302 |  | 56 | 23 | 3175 |  |  |  | 2895
30 | =.¦Énäù¶É | 16 | 2541 |  |  |  | 300 | 2857
31 | ˆ¢Ö¸ÖÖ›üü | 442 | [5 empty] | 442 | 25757
32 | Ênù±±ÉÒ | 0 | 52 | 467 |  |  |  | 519
33 | ¤ÉÉºÉ{ÉÉ | 36 | [5 empty] | 36 |  |  |  | 56
34 | ¨É±ÉÉxÉÉ | 38 | [5 empty] | 38
35 | ×¾ÖÂÖã ¯ÖÏµÖÖÖ | 104
36 | ²ÖÖ»ÖßÆüÖ¸ü | 300
| IÉäjÉ | 7405 | 16192 | 2886 | 781 | 56 | 323 | 27643 | 17319
| +xªÉ IÉäjÉÉå ºÉä +ÉªÉÉiÉ | [6 empty] | 2804
| +xªÉ IÉäjÉÉå EòÉä ÊxÉªÉÉÇiÉ | [6 empty] | 139
| ´ÉÉºiÉÊ´ÉEò +ÉªÉÉiÉ | [6 empty] | 2665
| EÖò±É ={É±É¤vÉiÉÉ | [6 empty] | 30308

## Page15
11...=SSÉiÉ¨É ¨ÉÉÄMÉ Eäò ÊnùxÉ IÉäjÉ ¨Éå PÉx]äõ´ÉÉ®ú ¦ÉÉ®ú ´É =i{ÉÉnùxÉ
HOURLY LOAD- GENERATION DATA OFTHE REGION FOR PEAK DAY
30.03.2010
PÉx]äõ HOURS | VÉ±ÉÒªÉ =i{ÉÉnùxÉ HYDRO GENERATION(MW) | xÉÉÊ¦ÉEòÒªÉ =i{ÉÉnùxÉ NUCLEAR GENERATION(MW) | 'MÉèºÉÒªÉ =i{ÉÉnùxÉ GAS FIRED GENERATION(MW) | iÉÉ{ÉÒªÉ =i{ÉÉnùxÉ COAL FIRED GENERATION(MW) | EÖò±É =iÉÂ{ÉÉnùxÉ TOTAL GENERATION(MW) | EÖò±É Ê´ÉÊxÉ¨ÉªÉ TOTAL EXCHANGE(MW) | ={É±É¤vÉiÉÉ AVAILABILITY(MW) | ÊxÉªÉÊ¨ÉiÉ ={É±É¤vÉiÉÉ REGULATED LOAD (MW)* | LOAD SHEDDING (MW) | ÊxÉªÉÊ¨ÉiÉ ¨ÉÉÄMÉ REGULATED DEMAND (MW) $ | ¦ÉÊiÉ PÉx]õÉ +É´ÉÞÊkÉ INSTANTANEOUS FREQUENCY(Hz) | RES.DEMAND (AVAIL.+L/S)(MW)#
01 | 4831 | 886 | 2172 | 17450 | 25339 | -1269 | 26608 | 26608 | 2190 | 28798 | 49.36 | 28798
02 | 4013 | 886 | 2645 | 17484 | 25028 | -1065 | 26093 | 26093 | 2185 | 28278 | 50.12 | 28278
03 | 3291 | 889 | 2656 | 17476 | 24312 | -1541 | 25853 | 25853 | 1912 | 27765 | 50.36 | 27765
04 | 3277 | 895 | 2649 | 17748 | 24569 | -1290 | 25859 | 25859 | 1844 | 27703 | 50.08 | 27703
05 | 3660 | 902 | 2648 | 17783 | 24993 | -1189 | 26182 | 26182 | 1659 | 27841 | 49.56 | 27841
06 | 4083 | 898 | 2675 | 17726 | 25382 | -2004 | 27386 | 27386 | 2618 | 30004 | 49.08 | 30004
07 | 3488 | 903 | 2685 | 17720 | 24796 | -2218 | 27014 | 27014 | 2872 | 29886 | 49.84 | 29886
08 | 3392 | 912 | 2654 | 17279 | 24237 | -2238 | 26475 | 26475 | 3257 | 29732 | 51 | 29732
09 | 3867 | 905 | 2633 | 17304 | 24709 | -2062 | 26771 | 26771 | 3741 | 30512 | 50.52 | 30512
10 | 4479 | 897 | 2536 | 17220 | 25132 | -1970 | 27102 | 27102 | 4158 | 31260 | 49.88 | 31260
11 | 4933 | 895 | 2556 | 17265 | 25649 | -2254 | 27903 | 27903 | 3768 | 31671 | 49.8 | 31671
12 | 4815 | 889 | 2554 | 17316 | 25574 | -2691 | 28265 | 28265 | 3370 | 31635 | 49.68 | 31635
13 | 3731 | 886 | 2532 | 17290 | 24439 | -2866 | 27305 | 27305 | 3388 | 30693 | 50.08 | 30693
14 | 4176 | 880 | 2530 | 16178 | 23764 | -3041 | 26805 | 26805 | 2313 | 29118 | 49.48 | 29118
15 | 4275 | 875 | 2556 | 17385 | 25091 | -2785 | 27876 | 27876 | 2819 | 30695 | 49.6 | 30695
16 | 3893 | 784 | 2495 | 17375 | 24547 | -2563 | 27110 | 27110 | 2626 | 29736 | 49.76 | 29736
17 | 3401 | 781 | 2541 | 17125 | 23848 | -2760 | 26608 | 26581 | 2698 | 29279 | 49.96 | 29306
18 | 3540 | 779 | 2482 | 16677 | 23478 | -2429 | 25907 | 25907 | 3740 | 29647 | 49.48 | 29647
19 | 6232 | 780 | 2508 | 16618 | 26138 | -569 | 26707 | 26707 | 3452 | 30159 | 48.88 | 30159
20 | 7405 | 781 | 2596 | 16861 | 27643 | -2665 | 30308 | 30308 | 3688 | 33996 | 49.4 | 33996
21 | 6298 | 775 | 2642 | 16977 | 26692 | -2803 | 29495 | 29495 | 3806 | 33301 | 49.52 | 33301
22 | 5600 | 783 | 2656 | 17035 | 26074 | -2262 | 28336 | 28336 | 3322 | 31658 | 50.24 | 31658
23 | 5646 | 780 | 2648 | 16912 | 25986 | -2299 | 28285 | 28285 | 3064 | 31349 | 49.68 | 31349
24 | 5402 | 778 | 2659 | 16973 | 25812 | -2247 | 28059 | 28059 | 3179 | 31238 | 49.56 | 31238
xªÉÚxÉkÉ¨Éú ¨ÉÉÄMÉ Eäò ÊnùxÉ IÉäjÉ ¨Éå PÉx]äõ´ÉÉ®ú ¦ÉÉ®ú ´É =i{ÉÉnùxÉ
HOURLY LOAD - GENERATION DATA OFTHE REGION FOR OFF PEAK DAY
02.03.2010
PÉx]äõ HOURS | VÉ±ÉÒªÉ =i{ÉÉnùxÉ HYDRO GENERATION(MW) | xÉÉÊ¦ÉEòÒªÉ =i{ÉÉnùxÉ NUCLEAR GENERATION (MW) | MÉèºÉÒªÉ =i{ÉÉnùxÉ GAS FIRED GENERATION (MW) | iÉÉ{ÉÒªÉ =i{ÉÉnùxÉ COAL FIRED GENERATION (MW) | EÖò±É =iÉÂ{ÉÉnùxÉ TOTAL GENERATION (MW) | EÖò±É Ê´ÉÊxÉ¨ÉªÉ TOTAL EXCHANGE (MW) | ={É±É¤vÉiÉÉ AVAILABILITY (MW) | ÊxÉªÉÊ¨ÉiÉ ={É±É¤vÉiÉÉ REGULATED LOAD * (MW) | LOAD SHEDDING (MW) | ÊxÉªÉÊ¨ÉiÉ ¨ÉÉÄMÉ REGULATED DEMAND (MW) $ | ¦ÉÊiÉ PÉx]õÉ +É´ÉÞÊkÉ INSTANTANEOUS FREQUENCY(Hz) | RES.DEMAND (AVAIL.+L/S)(MW) #
01 | 2359 | 833 | 1997 | 15856 | 21045 | -1770 | 22815 | 22376 | 935 | 23311 | 50.12 | 23750 | 22592.02
02 | 2303 | 840 | 1966 | 15936 | 21045 | -1675 | 22720 | 22257 | 765 | 23022 | 50.72 | 23485
03 | 2239 | 839 | 1900 | 15823 | 20801 | -1532 | 22333 | 22025 | 792 | 22817 | 50.8 | 23125
04 | 2228 | 836 | 1979 | 15670 | 20713 | -1713 | 22426 | 21909 | 799 | 22708 | 51 | 23225
05 | 2869 | 832 | 2112 | 15653 | 21466 | -888 | 22354 | 22141 | 1004 | 23145 | 50.52 | 23358
06 | 3823 | 800 | 2209 | 16810 | 23642 | -1922 | 25564 | 25201 | 1010 | 26211 | 50.04 | 26574
07 | 5194 | 828 | 2167 | 16725 | 24914 | -2110 | 27024 | 26788 | 1115 | 27903 | 50.52 | 28139
08 | 4783 | 681 | 2129 | 16425 | 24018 | -2199 | 26217 | 25916 | 1131 | 27047 | 50.68 | 27348
09 | 4427 | 794 | 2105 | 16425 | 23751 | -2314 | 26065 | 25982 | 1206 | 27188 | 50.56 | 27271
10 | 4573 | 819 | 2278 | 16958 | 24628 | -2728 | 27356 | 27085 | 1237 | 28322 | 50.24 | 28593
11 | 5084 | 823 | 2041 | 16961 | 24909 | -1900 | 26809 | 26788 | 3045 | 29833 | 50.48 | 29854
12 | 5353 | 815 | 2215 | 16784 | 25167 | -1875 | 27042 | 26945 | 2110 | 29055 | 50.48 | 29152
13 | 4664 | 813 | 2299 | 17011 | 24787 | -1764 | 26551 | 26267 | 1916 | 28183 | 49.88 | 28467
14 | 4150 | 816 | 2053 | 16884 | 23903 | -2190 | 26093 | 25814 | 1765 | 27579 | 50.4 | 27858
15 | 3589 | 815 | 2193 | 16898 | 23495 | -1945 | 25440 | 25188 | 1972 | 27160 | 50.04 | 27412
16 | 2645 | 819 | 2143 | 16830 | 22437 | -2058 | 24495 | 24534 | 1327 | 25861 | 49.84 | 25822
17 | 2779 | 819 | 2150 | 16823 | 22571 | -1811 | 24382 | 24179 | 1815 | 25994 | 50.16 | 26197
18 | 4239 | 827 | 2001 | 16798 | 23865 | -1057 | 24922 | 24559 | 2449 | 27008 | 50.36 | 27371
19 | 6895 | 824 | 2269 | 17011 | 26999 | -1055 | 28054 | 27798 | 2182 | 29980 | 50.68 | 30236
20 | 5746 | 823 | 2300 | 17118 | 25987 | -1183 | 27170 | 27062 | 3087 | 30149 | 50.8 | 30257
21 | 4477 | 827 | 2330 | 16932 | 24566 | -1347 | 25913 | 25748 | 2444 | 28192 | 50.32 | 28357
22 | 4117 | 831 | 2158 | 17096 | 24202 | -1035 | 25237 | 25277 | 1480 | 26757 | 50.72 | 26717
23 | 3669 | 824 | 2219 | 17099 | 23811 | -1462 | 25273 | 25172 | 1217 | 26389 | 50.24 | 26490
24 | 3112 | 823 | 2372 | 17158 | 23465 | -1542 | 25007 | 24858 | 1063 | 25921 | 50.12 | 26070
Note : | Import (-) / Export (+)
* : | Regulated Load is recorded load with frequency correction(3% per Hz for peak hrs.and 4% per Hz for other hrs.)
$ : | Regulated Demand is regulated load plus load shedding
# | Res. Demand is availability plus load shedding

## Page16
¨ÉÉSÉÇ 2010 ¨ÉÉ½þ Eäò nùÉè®úÉxÉ +ÊvÉºÉÚÊSÉiÉ Ê´ÉtÖiÉ Eò]õÉèÊiÉ +Éè®ú ¦ÉÊiÉ¤ÉxvÉ
NOTIFIED POWER CUTS AND RESTRICTIONS DURING THE MONTH OF MARCH 2010
1.Power Cut on Industries
Gò¨É ºÉÆ. | .®úÉVªÉ/Eäòxpù ¶ÉÉÊºÉiÉ | Industries | Energy Cut(MU/day) | Demand Cut(MW) | Restriction Timings | Remarks
Sr.No. | State/UT
1 | SÉhb÷ÒMÉgø | HT/LT | No Notified Power Cut
| CHANDIGARH | [7 empty] | 0.0036 |  | 0.0016667
2 | Ênù±±ÉÒ | HT/LT | No Notified Power Cut
DELHI
3 | ½þÊ®úªÉÉhÉ | HT/LT | 0-3.375 | 250 | Different durations for Different days for energy cuts
HARYANA
4 | Ê½þ¨ÉÉSÉ±É ¦Énäù¶É | HT/LT | 0 | 0 | 18.30 to21.30 (Peak Hrs.)
H.P
5 | PUNJAB {ÉÆVÉÉ¤É | HT/LT | 1.8 | 600 | 3 hrs(18.30 to 21.30 hrs.) of Peak Load Hour Restrictions.
|  |  | 3.55 |  | Extended PLR for 9 hrs.remained applicable on continous process industry from 19.3.10 to 29.3.10.One weekly off day/week on arc/induction furnaces and general industry fed from feeders having predominant industrial load(except 3 days off on rc/induction furnances and 58 hrs.off on general industry from 19.3.10 to 29.3.10)
PUNJAB
[8 empty] | 624 | 29 | 21.5172
6 | RAJASTHAN ®úÉVÉºlÉÉxÉ | HT | No Notified Power Cut
7 | ˆ¢Ö¸ÖÖ›üü | HT/LT-Furnances | 0.5187 | 80 | 1700 to 2400 hrs. |  |  |  | 0.51871
| UTTARAKHAND | HT/LT-Non-continous | 0.40355 | 90 | 1800 to 2300 hrs.
8 | .=kÉ®ú ¦Énäù¶É. | HT/LT | No Notified Power Cut
UTTAR PRADESH
2.Power Supply To Agriculture
2.Power Supply To Agriculture
Gò¨É ºÉÆ. | .®úÉVªÉ/Eäòxpù ¶ÉÉÊºÉiÉ |  | Three Phase | Supply Hrs. Per Day |  |  | Remarks
Sr.No. | State/UT |  |  | Maximum | Minimum | Average
1 | SÉhb÷ÒMÉgø |  | 24 hrs
CHANDIGARH
2 | Ênù±±ÉÒ |  | 24 Hrs
DELHI
3 | ½þÊ®úªÉÉhÉ |  | Three Phase | 6 | 5.3 | 6
HARYANA
4 | Ê½þ¨ÉÉSÉ±É ¦Énäù¶É |  | 24hrs
HIMACHAL PRADESH
5 | {ÉÆVÉÉ¤É |  | Three Phase | 12.41 | 2.13 | 4.54
PUNJAB
6 | ®úÉVÉºlÉÉxÉ |  | Three Phase | 20.5 | 14 | 17.25
| RAJASTHAN | [8 empty] | 11.5
7 | ˆ¢Ö¸ÖÖ›üü |  | Three Phase | 24 | 15.05 | 17.192 |  |  | 20.2
UTTARAKHAND
8 | .=kÉ®ú ¦Énäù¶É. |  |  | 14.26 | 8.5 | 10.11
UTTAR PRADESH
Commercial & Domestic Power Cuts:
1. Rajasthan- No Notified Power Cuts
2.Himachal Pradesh--No Notified Power Cuts
3.Punjab:(Avg supply):Rural Domestic supply=20.77 hrs,Distt.H/Q supply=21.20 hrs,,Main cities supply=21.39 hrs,Urban industrial{ mixed}=21.06 hrs)
4.U P:Avg.Supply hrs to :Tehsil Towns: 10.11,Distt.H/Q Towns:15.18, Commissionary H/Q towns:17.43,Bundelkhand Area:14.44
Corporation Towns:20.04,Industrial Feeders:24.00
5.Uttarakhand-15 to 100 MW demand cuts on commercial/towns with 2 to 4 hrs. Restrictions
6.Curtailment Schedule of Jammu & Kashmir-:
Sr.No. | Category of Consumers |  |  |  | Power Cuts per day
1 | Essentail loads like Hospitals,Defence,PHE(Water Supplies),Irrigation etc......................No Cuts
2 | Domestic,Commercial and mixed load feeders that have 100% consumer metering........No Cuts
3 | Domestic,Commercial and mixed load feeders with partial or no consumer metering....9 Hrs and 30 minutes
4 | Industrial Consumers in Organised Industra\ial Estates........................................................3 hours to 8 hours,depending on systempeak load
demands &system constraints

## Page17(1)
PERCENTAGE SHARES AND ENTITLEMENTS OF NORTHERN REGION UTILITIES
IN VARIOUS CENTRAL SECTOR GENERATING STATIONS
Summary
A. Allocations from N.R. |  |  | (All figures in %)
[10 empty] | % | [5 empty] | MWs
U.A.-Pooled 1339 MW excluding RAPP-B |  |  |  |  | U.A.(66 MW)- RAPS:B |  |  |  |  | U.A.(66 MW)- RAPS:B # 3 & 4 | [5 empty] | U.A.(66 MW)- RAPS:B # 3 & 4 | [6 empty] | SINGRAULI (2000 MW)
State/UT | 00-06 & 23-24 hrs | 06-10 hrs | 10-18 hrs | 18-23 hrs | State/UT | 00-06 & 23-24 hrs | 06-10 hrs | 10-18 hrs | 18-23 hrs | State/UT | 00-06 & 23-24 hrs | 06-12 hrs | 12-19 hrs | 19-23 hrs |  | State/UT | 00-06 & 23-24 hrs | 06-12 hrs | 12-19 hrs | 19-23 hrs |  |  |  | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23
[22 empty] | State/UT | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt
Chandigarh | 0 | 5 | 0 | 5 | Chandigarh | 0 | 0 | 0 | 0 | Chandigarh | 0 | 0 | 0 | 0 |  | Chandigarh | 0 | 0 | 0 | 0 |  | Chandigarh | 0 | 0 | 0 | 0.75 | 0.75 | 0 | 0 | 0.75 | 0.75
Delhi | 0 | 0 | 0 | 0 | Delhi | 0 | 0 | 0 | 3.1818 | Delhi | 0 | 0 | 0 | 3.1818 |  | Delhi | 0 | 0 | 0 | 14 |  | Delhi | 7.5 | 0 | 7.5 | 0.6 | 8.1 | 0 | 7.5 | 0.6 | 8.1
Haryana | 14 | 11 | 14 | 11 | Haryana | 2.5 | 0 | 3.75 | 0 | Haryana | 2.5 | 0 | 3.75 | 0 |  | Haryana | 11 | 0 | 16.5 | 0 |  | Haryana | 10 | 2.1 | 12.1 | 1.65 | 11.65 | 2.1 | 12.1 | 1.65 | 11.65
H.P. | 7 | 11 | 12 | 12 | H.P. | 0 | 0 | 0 | 0 | H.P. | 0 | 0 | 0 | 0 |  | H.P. | 0 | 0 | 0 | 0 |  | H.P. | 0 | 1.05 | 1.05 | 1.65 | 1.65 | 1.8 | 1.8 | 1.8 | 1.8
J & K | 18.15 | 28.03 | 18.15 | 32.15 | J & K | 0 | 0 | 0 | 0 | J & K | 0 | 0 | 0 | 0 |  | J & K | 0 | 0 | 0 | 0 |  | J & K | 0 | 3.9 | 3.9 | 4.95 | 4.95 | 3.9 | 3.9 | 4.95 | 4.95
Punjab | 7 | 2 | 7 | 3 | Punjab | 3.1818 | 3.1818 | 1.25 | 0 | Punjab | 3.1818 | 3.1818 | 1.25 | 0 |  | Punjab | 14 | 14 | 5.5 | 0 |  | Punjab | 10 | 1.05 | 11.05 | 0.3 | 10.3 | 1.05 | 11.05 | 0.45 | 10.45
Rajasthan | 10 | 7 | 7 | 7 | Rajasthan | 5.9091 | 8.4091 | 7.5 | 8.4091 | Rajasthan | 5.9091 | 8.4091 | 7.5 | 8.4091 |  | Rajasthan | 26 | 37 | 33 | 37 |  | Rajasthan | 15 | 1.5 | 16.5 | 1.05 | 16.05 | 1.05 | 16.05 | 1.05 | 16.05
U.P. | 37.85 | 30.85 | 35.85 | 25.73 | U.P. | 3.4091 | 3.4091 | 2.5 | 3.4091 | U.P. | 3.4091 | 3.4091 | 2.5 | 3.4091 |  | U.P. | 15 | 15 | 11 | 15 |  | U.P. | 37.68 | 4.5 | 42.18 | 3.45 | 41.13 | 4.2 | 41.88 | 3.3 | 40.98
Uttarakhand | 6 | 5.12 | 6 | 4.12 | Uttarakhand | 0 | 0 | 0 | 0 | Uttarakhand | 0 | 0 | 0 | 0 |  | Uttarakhand | 0 | 0 | 0 | 0 |  | Uttarakhand | 5.52 | 0.9 | 5.72 | 0.6 | 5.42 | 0.9 | 5.72 | 0.45 | 5.27
[22 empty] | HVDC_Rihand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 100 | 100 | 100 | 100 | Total | 15 | 15 | 15 | 15 | Total | 15 | 15 | 15 | 15 |  | Total | 66 | 66 | 66 | 66 |  | HVDC_Dadri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | Total | 85.7 | 15 | 100 | 15 | 100 | 15 | 100 | 15 | 100
Unallocated Pool |  |  |  |  | 1423.5 | MW
Additional specific allocation to Uttarakhand from UA Pool |  |  |  |  | 64 | MW | [5 empty] | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440 | 440
Specific Allocation to J&K from RAPS-C |  |  |  |  | 20.5 | MW
Balance Unallocated Pool for beneficiaries of the Region |  |  |  |  | 1339 | MW | [5 empty] | 66 | 11 | 14 | 15 | 22 | 26 | 37 | 33 | 5.5 | 16.5
[12 empty] | 15 | 2.5 | 3.1818 | 3.4091 | 5 | 5.9091 | 8.4091 | 7.5 | 1.25 | 3.75
[12 empty] | 440 | 440 | 440 | 440 | 440
[12 empty] | 26 | 37 | 33 | 5.5 | 16.5
[12 empty] | 5.9091 | 8.4091 | 7.5 | 1.25 | 3.75
Note on H24: Bhagwan: 107/2MW from RAPPC

## Page17(2)
PERCENTAGE SHARES AND ENTITLEMENTS OF NORTHERN REGION UTILITIES
IN E.R. AND BHUTAN CENTRAL SECTOR GENERATING STATIONS
B. Allocations from E.R. and Tala , HPS (Bhutan) | [9 empty] | (All figures in %)
Allocations from UA share of CGS of ER/DVC surrendered power
| 0000-0600 & 2300-2400 hrs |  |  | 0600-1200 hrs |  |  | 1200-1900 hrs |  |  | 1900-2300 hrs
State/UT | FARAKKA | K'GAON-I | TALCHER | FARAKKA | K'GAON-I | TALCHER | FARAKKA | K'GAON-I | TALCHER | FARAKKA | K'GAON-I | TALCHER | [5 empty] | MEJIA unit - 6
| 1600 MW | 840 MW | 1000 MW | 1600 MW | 840 MW | 1000 MW | 1600 MW | 840 MW | 1000 MW | 1600 MW | 840 MW | 1000 MW
Chandigarh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Delhi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 19.6 | 32.6667 | 11.76
Haryana | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9.8 | 16.3333 | 5.88
H.P. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
J & K | 1.89 | 1.88 | 1.9 | 1.46 | 1.44 | 1.46 | 1.17 | 1.15 | 1.16 | 1.17 | 1.15 | 1.16 | [5 empty] | 11.8 | 19.6667 | 7.08
Punjab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 19.6 | 32.6667 | 11.76
Rajasthan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9.8 | 16.3333 | 5.88
U.P. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 29.4 | 49 | 17.64
Uttarakhand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Total | 1.89 | 1.88 | 1.9 | 1.46 | 1.44 | 1.46 | 1.17 | 1.15 | 1.16 | 1.17 | 1.15 | 1.16 | [5 empty] | 100 | 166.6667 | 60
| Add.allocation from E.R. In lieu of Tala, HEP (170*6 = 1020 MW ) |  |  |  | Total Allocations from CGS of ER / DVC surrendered power from E.R.
| 0000 -- 2400 hrs |  |  |  | 0000-0600 & 2300-2400 hrs |  |  | 0600-1200 hrs |  |  | 1200-1900 hrs |  |  | 1900-2300 hrs
State/UT | FARAKKA | K'GAON-I | MEJIA # 6 | Tala, HEP | FARAKKA | K'GAON-I | TALCHER | FARAKKA | K'GAON-I | TALCHER | FARAKKA | K'GAON-I | TALCHER | FARAKKA | K'GAON-I | TALCHER
| 1600 MW | 840 MW | 250 M W | (15% UA Power) | 1600 MW | 840 MW | 1000 MW | 1600 MW | 840 MW | 1000 MW | 1600 MW | 840 MW | 1000 MW | 1600 MW | 840 MW | 1000 MW
Chandigarh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delhi | 1.85 | 7.54 | 11.76 | 2.94 | 1.85 | 7.54 | 0 | 1.85 | 7.54 | 0 | 1.85 | 7.54 | 0 | 1.85 | 7.54 | 0
Haryana | 0.91 | 3.78 | 5.88 | 1.47 | 0.91 | 3.78 | 0 | 0.91 | 3.78 | 0 | 0.91 | 3.78 | 0 | 0.91 | 3.78 | 0
H.P. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J & K | 1.12 | 4.56 | 7.08 | 1.77 | 3.01 | 6.44 | 1.9 | 2.58 | 6 | 1.46 | 2.29 | 5.71 | 1.16 | 2.29 | 5.71 | 1.16 | Please SEE
Punjab | 1.85 | 7.54 | 11.76 | 2.94 | 1.85 | 7.54 | 0 | 1.85 | 7.54 | 0 | 1.85 | 7.54 | 0 | 1.85 | 7.54 | 0
Rajasthan | 0.91 | 3.78 | 5.88 | 1.47 | 0.91 | 3.78 | 0 | 0.91 | 3.78 | 0 | 0.91 | 3.78 | 0 | 0.91 | 3.78 | 0
U.P. | 2.76 | 11.32 | 17.64 | 4.41 | 2.76 | 11.32 | 0 | 2.76 | 11.32 | 0 | 2.76 | 11.32 | 0 | 2.76 | 11.32 | 0
Uttarakhand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 9.4 | 38.52 | 60 | 15 | 11.29 | 40.4 | 1.9 | 10.86 | 39.96 | 1.46 | 10.57 | 39.67 | 1.16 | 10.57 | 39.67 | 1.16
C. Kahalgaon-II (3*500 MW = 1500 MW) Eastern Region: Revised allocation after COD of Kahalgaon STPP-II Two Unit (1000 MW)
(All figures in %)
State/UT |  | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23
| Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt
Chandigarh | 0.2 | 0 | 0.2 | 0.29 | 0.49 | 0 | 0.2 | 0.29 | 0.49
Delhi | 10.77 | 0 | 10.77 | 0 | 10.77 | 0 | 10.77 | 0 | 10.77
Haryana | 4.72 | 0.82 | 5.54 | 0.64 | 5.36 | 0.82 | 5.54 | 0.65 | 5.37
H.P. | 1.53 | 0.41 | 1.94 | 0.64 | 2.17 | 0.7 | 2.23 | 0.7 | 2.23
J & K | 5.73 | 1.06 | 6.79 | 1.65 | 7.38 | 1.07 | 6.8 | 1.88 | 7.61
Punjab | 8.31 | 0.41 | 8.72 | 0.12 | 8.43 | 0.41 | 8.72 | 0.18 | 8.49
Rajasthan | 7.25 | 0.59 | 7.84 | 0.41 | 7.66 | 0.41 | 7.66 | 0.41 | 7.66
U.P. | 17.16 | 2.22 | 19.38 | 1.81 | 18.97 | 2.1 | 19.26 | 1.51 | 18.67
Uttarakhand | 1.87 | 0.35 | 2.22 | 0.3 | 2.17 | 0.35 | 2.22 | 0.24 | 2.11
Total | 57.54 | 5.86 | 63.4 | 5.86 | 63.4 | 5.86 | 63.4 | 5.86 | 63.4
| Pre Tala allocations from Eastern Region |  |  | Allocations applicable after COD of 6 units of Tala
|  |  |  | Add.allocation from E.R.In lieu of Tala, HEP |  | Total allocations from E.R.
| 0000 - 2400 hrs |  |  | 0000 - 2400 hrs |  | 0000 - 2400 hrs |  |  |  | 0000-2400 hrs
| FARAKKA | K'GAON-I | TALCHER | FARAKKA | K'GAON-I | FARAKKA | K'GAON-I | TALCHER | MEJIA # 6 | Tala, HEP
| 1600 MW | 840 MW | 1000 MW | 1600 MW | 840 MW |  |  |  |  | (15% UA Power)
[6 empty] | 1600 MW | 840 MW | 1000 MW | 250 MW | 1020 MW (6 Units)
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.28 | 1.28 | 1.28 | 1.85 | 7.54 | 3.13 | 8.82 | 1.28 | 11.76 | 2.94
| 0 | 0 | 0 | 0.91 | 3.78 | 0.91 | 3.78 | 0 | 5.88 | 1.47
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 1.12 | 4.56 | 1.12 | 4.56 | 0 | 7.08 | 1.77
| 0 | 0 | 0 | 1.85 | 7.54 | 1.85 | 7.54 | 0 | 11.76 | 2.94
| 0 | 0 | 0 | 0.91 | 3.78 | 0.91 | 3.78 | 0 | 5.88 | 1.47
| 1.19 | 1.18 | 1.19 | 2.76 | 11.32 | 3.95 | 12.5 | 1.19 | 17.64 | 4.41
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.47 | 2.46 | 2.47 | 9.4 | 38.52 | 11.87 | 40.98 | 2.47 | 60 | 15
Note on F53: Bhagwan:
Note on H53: dell:
Note on J51: dell:

## Page17(3)
PERCENTAGE SHARES AND ENTITLEMENTS OF NORTHERN REGION UTILITIES IN VARIOUS CENTRAL SECTOR GENERATING STATIONS
NTPC stations
(All figures in %)
| SINGRAULI (2000 MW) | [8 empty] | RIHAND-I (1000 MW) | [8 empty] | RIHAND-II (1000 MW)
| 0.7 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.7 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.71 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23
State/UT | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt
Chandigarh | 0 | 0 | 0 | 0.72 | 0.72 | 0 | 0 | 0.71 | 0.71 | 1 | 0 | 1 | 0.71 | 1.71 | 0 | 1 | 0.71 | 1.71 | 0.8 | 0 | 0.8 | 0.71 | 1.51 | 0 | 0.8 | 0.72 | 1.52
Delhi | 7.5 | 0 | 7.5 | 0 | 7.5 | 0 | 7.5 | 0 | 7.5 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 12.6 | 0 | 12.6 | 0 | 12.6 | 0 | 12.6 | 0 | 12.6
Haryana | 10 | 2 | 12 | 1.57 | 11.57 | 2 | 12 | 1.57 | 11.57 | 6.5 | 1.99 | 8.49 | 1.56 | 8.06 | 1.99 | 8.49 | 1.56 | 8.06 | 5.7 | 2 | 7.7 | 1.57 | 7.27 | 2 | 7.7 | 1.57 | 7.27
H.P. | 0 | 1 | 1 | 1.57 | 1.57 | 1.72 | 1.72 | 1.72 | 1.72 | 3.5 | 1 | 4.5 | 1.56 | 5.06 | 1.71 | 5.21 | 1.71 | 5.21 | 3.3 | 1 | 4.3 | 1.57 | 4.87 | 1.71 | 5.01 | 1.71 | 5.01
J & K | 0 | 2.6 | 2.6 | 4.01 | 4.01 | 2.6 | 2.6 | 4.6 | 4.6 | 7 | 2.58 | 9.58 | 3.99 | 10.99 | 2.58 | 9.58 | 4.57 | 11.57 | 9.4 | 2.59 | 11.99 | 4.01 | 13.41 | 2.59 | 11.99 | 4.59 | 13.99
Punjab | 10 | 1 | 11 | 0.29 | 10.29 | 1 | 11 | 0.43 | 10.43 | 11 | 0.99 | 11.99 | 0.29 | 11.29 | 0.99 | 11.99 | 0.43 | 11.43 | 10.2 | 1 | 11.2 | 0.29 | 10.49 | 1 | 11.2 | 0.43 | 10.63
Rajasthan | 15 | 1.43 | 16.43 | 1 | 16 | 1 | 16 | 1 | 16 | 9.5 | 1.42 | 10.92 | 1 | 10.5 | 1 | 10.5 | 0.99 | 10.49 | 10 | 1.43 | 11.43 | 1 | 11 | 1 | 11 | 1 | 11
U.P. | 37.68 | 5.41 | 43.09 | 4.41 | 42.09 | 5.12 | 42.8 | 3.68 | 41.36 | 32.57 | 5.39 | 37.96 | 4.38 | 36.95 | 5.1 | 37.67 | 3.66 | 36.23 | 29.6 | 5.41 | 35.01 | 4.41 | 34.01 | 5.13 | 34.73 | 3.68 | 33.28
Uttarakhand | 4.82 | 1.56 | 6.38 | 1.43 | 6.25 | 1.56 | 6.38 | 1.29 | 6.11 | 3.93 | 1.55 | 5.48 | 1.43 | 5.36 | 1.55 | 5.48 | 1.29 | 5.22 | 3.4 | 1.57 | 4.97 | 1.44 | 4.84 | 1.57 | 4.97 | 1.3 | 4.7
HVDC_Rihand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HVDC_Dadri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 85 | 15 | 100 | 15 | 100 | 15 | 100 | 15 | 100 | 85 | 15 | 100 | 15 | 100 | 15 | 100 | 15 | 100 | 85 | 15 | 100 | 15 | 100 | 15 | 100 | 15 | 100
| UNCHAHAR-I (420 MW) | [8 empty] | UNCHAHAR-II (420 MW) | [8 empty] | UNCHAHAR-III (210 MW)
| 0.21 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.69 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.71 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23
State/UT | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt
Chandigarh | 0.48 | 0 | 0.48 | 0.23 | 0.71 | 0 | 0.48 | 0.23 | 0.71 | 0.71 | 0 | 0.71 | 0.72 | 1.43 | 0 | 0.71 | 0.72 | 1.43 | 0.48 | 0 | 0.48 | 0.7 | 1.18 | 0 | 0.48 | 0.7 | 1.18
Delhi | 5.71 | 0 | 5.71 | 0 | 5.71 | 0 | 5.71 | 0 | 5.71 | 11.19 | 0 | 11.19 | 0 | 11.19 | 0 | 11.19 | 0 | 11.19 | 13.81 | 0 | 13.81 | 0 | 13.81 | 0 | 13.81 | 0 | 13.81
Haryana | 2.62 | 0.64 | 3.26 | 0.5 | 3.12 | 0.64 | 3.26 | 0.5 | 3.12 | 5.48 | 2.01 | 7.49 | 1.57 | 7.05 | 2 | 7.48 | 1.57 | 7.05 | 5.71 | 1.97 | 7.68 | 1.55 | 7.26 | 1.97 | 7.68 | 1.55 | 7.26
H.P. | 1.67 | 0.32 | 1.99 | 0.5 | 2.17 | 0.55 | 2.22 | 0.55 | 2.22 | 2.86 | 1 | 3.86 | 1.58 | 4.44 | 1.72 | 4.58 | 1.72 | 4.58 | 3.81 | 0.98 | 4.79 | 1.55 | 5.36 | 1.69 | 5.5 | 1.69 | 5.5
J & K | 3.33 | 0.82 | 4.15 | 1.28 | 4.61 | 0.83 | 4.16 | 1.46 | 4.79 | 7.14 | 2.6 | 9.74 | 4.01 | 11.15 | 2.6 | 9.74 | 4.6 | 11.74 | 6.19 | 2.55 | 8.74 | 3.94 | 10.13 | 2.55 | 8.74 | 4.52 | 10.71
Punjab | 8.57 | 0.32 | 8.89 | 0.09 | 8.66 | 0.32 | 8.89 | 0.14 | 8.71 | 14.28 | 1 | 15.28 | 0.29 | 14.57 | 1 | 15.28 | 0.43 | 14.71 | 8.1 | 0.98 | 9.08 | 0.28 | 8.38 | 0.98 | 9.08 | 0.42 | 8.52
Rajasthan | 4.76 | 0.46 | 5.22 | 0.32 | 5.08 | 0.32 | 5.08 | 0.32 | 5.08 | 9.05 | 1.43 | 10.48 | 1 | 10.05 | 1 | 10.05 | 1 | 10.05 | 10.95 | 1.41 | 12.36 | 0.98 | 11.93 | 0.98 | 11.93 | 0.98 | 11.93
U.P. | 59.52 | 1.73 | 61.25 | 1.41 | 60.93 | 1.63 | 61.15 | 1.17 | 60.69 | 30.69 | 5.41 | 36.1 | 4.41 | 35.1 | 5.13 | 35.82 | 3.68 | 34.37 | 30 | 5.32 | 35.32 | 4.33 | 34.33 | 5.04 | 35.04 | 3.61 | 33.61
Uttarakhand | 8.57 | 0.48 | 9.05 | 0.44 | 9.01 | 0.48 | 9.05 | 0.4 | 8.97 | 3.6 | 1.55 | 5.15 | 1.42 | 5.02 | 1.55 | 5.15 | 1.28 | 4.88 | 6.19 | 1.55 | 7.74 | 1.43 | 7.62 | 1.55 | 7.74 | 1.29 | 7.48
Total | 95.23 | 4.77 | 100 | 4.77 | 100 | 4.77 | 100 | 4.77 | 100 | 85 | 15 | 100 | 15 | 100 | 15 | 100 | 15 | 100 | 85.24 | 14.76 | 100 | 14.76 | 100 | 14.76 | 100 | 14.76 | 100
| ANTA (G) ( 419 MW) | [8 empty] | AURAIYA (G) (663 MW) | [8 empty] | DADRI(G) (830 MW) | [8 empty] | DADRI(T) (840 MW) |  | DADRI-II(T) (490 MW)
| 0.69 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.48 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.33 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 00 - 24 |  | 00 - 24
State/UT | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt |  | Share |  | Share
Chandigarh | 1.19 | 0 | 1.19 | 0.72 | 1.91 | 0 | 1.19 | 0.72 | 1.91 | 0.75 | 0 | 0.75 | 0.5 | 1.25 | 0 | 0.75 | 0.5 | 1.25 | 0.61 | 0 | 0.61 | 0.33 | 0.94 | 0 | 0.61 | 0.33 | 0.94 |  | 0 |  | 0
Delhi | 10.5 | 0 | 10.5 | 0 | 10.5 | 0 | 10.5 | 0 | 10.5 | 10.86 | 0 | 10.86 | 0 | 10.86 | 0 | 10.86 | 0 | 10.86 | 10.96 | 0 | 10.96 | 0 | 10.96 | 0 | 10.96 | 0 | 10.96 |  | 90 |  | 90
Haryana | 5.73 | 2.01 | 7.74 | 1.58 | 7.31 | 2.01 | 7.74 | 1.58 | 7.31 | 5.88 | 1.39 | 7.27 | 1.09 | 6.97 | 1.39 | 7.27 | 1.09 | 6.97 | 4.94 | 0.93 | 5.87 | 0.74 | 5.68 | 0.93 | 5.87 | 0.73 | 5.67 |  | 0 |  | 0
H.P. | 3.58 | 1 | 4.58 | 1.58 | 5.16 | 1.72 | 5.3 | 1.72 | 5.3 | 3.32 | 0.69 | 4.01 | 1.09 | 4.41 | 1.19 | 4.51 | 1.19 | 4.51 | 3.01 | 0.47 | 3.48 | 0.73 | 3.74 | 0.8 | 3.81 | 0.8 | 3.81 |  | 0 |  | 0
J & K | 6.92 | 2.6 | 9.52 | 4.02 | 10.94 | 2.61 | 9.53 | 4.61 | 11.53 | 6.64 | 1.8 | 8.44 | 2.78 | 9.42 | 1.8 | 8.44 | 3.19 | 9.83 | 6.75 | 1.21 | 7.96 | 1.87 | 8.62 | 1.21 | 7.96 | 2.15 | 8.9 |  | 0 |  | 0
Punjab | 11.69 | 1 | 12.69 | 0.29 | 11.98 | 1.01 | 12.7 | 0.43 | 12.12 | 12.52 | 0.69 | 13.21 | 0.2 | 12.72 | 0.69 | 13.21 | 0.3 | 12.82 | 15.9 | 0.47 | 16.37 | 0.13 | 16.03 | 0.47 | 16.37 | 0.2 | 16.1 |  | 0 |  | 0
Rajasthan | 19.81 | 1.44 | 21.25 | 1 | 20.81 | 1 | 20.81 | 1 | 20.81 | 9.2 | 0.99 | 10.19 | 0.69 | 9.89 | 0.69 | 9.89 | 0.69 | 9.89 | 9.28 | 0.67 | 9.95 | 0.47 | 9.75 | 0.47 | 9.75 | 0.47 | 9.75 |  | 0 |  | 0
U.P. | 21.75 | 5.44 | 27.19 | 4.43 | 26.18 | 5.14 | 26.89 | 3.7 | 25.45 | 32.06 | 3.76 | 35.82 | 3.06 | 35.12 | 3.56 | 35.62 | 2.55 | 34.61 | 29.6 | 2.53 | 32.13 | 2.07 | 31.67 | 2.4 | 32 | 1.72 | 31.32 |  | 10 |  | 10
Uttarakhand | 3.79 | 1.55 | 5.34 | 1.42 | 5.21 | 1.55 | 5.34 | 1.28 | 5.07 | 3.84 | 1.08 | 4.92 | 0.99 | 4.83 | 1.08 | 4.92 | 0.89 | 4.73 | 3.41 | 0.73 | 4.14 | 0.67 | 4.08 | 0.73 | 4.14 | 0.61 | 4.02 |  | 0 |  | 0
Railways | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.53 | 4.53 | 4.53 | 4.53 | 4.53 | 4.53 | 4.53 | 4.53 | 0 | 8.43 | 8.43 | 8.43 | 8.43 | 8.43 | 8.43 | 8.43 | 8.43 |  | 0 |  | 0
HVDC_Rihand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
HVDC_Dadri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  | 0 |  | 0
Total | 84.96 | 15.04 | 100 | 15.04 | 100 | 15.04 | 100 | 15.04 | 100 | 85.07 | 14.93 | 100 | 14.93 | 100 | 14.93 | 100 | 14.93 | 100 | 84.46 | 15.54 | 100 | 15.54 | 100 | 15.54 | 100 | 15.54 | 100 |  | 100 |  | 100
Note on D29: dell:
Note on D46: Bhagwan:
Note on H16: Bhagwan:
Note on H43: Bhagwan:
Note on H44: dell:
Note on J9: dell:
Note on J29: Bhagwan:
Note on J46: Bhagwan:
Note on M14: dell:
Note on M16: Bhagwan:
Note on M27: dell:
Note on M32: Bhagwan:
Note on M46: Bhagwan:
Note on O14: dell:
Note on O16: Bhagwan:
Note on O28: dell:
Note on Q14: dell:
Note on S15: dell:
Note on V41: dell:
Note on X42: dell:
Note on Z16: Bhagwan:
Note on Z41: dell:
Note on AB9: dell:
Note on AB32: Bhagwan:
Note on AB41: dell:

## Page17(4)
PERCENTAGE SHARES AND ENTITLEMENTS OF NORTHERN REGION UTILITIES IN VARIOUS CENTRAL SECTOR GENERATING STATIONS
NPC, NJ- HEP, Tehri and NHPC stations
and Unchahar-III NTPC station
(All figures in %)
| State/UT | NAPS (440 MW) | [8 empty] | RAPS-B (440 MW) | [8 empty] | RAPS-C # 5(220 MW)
|  | 0.68 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  |  | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  |  | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23
|  | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt
| Chandigarh | 1.14 | 0 | 1.14 | 0.69 | 1.83 | 0 | 1.14 | 0.69 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68 | 0 | 0.68 | 0.75 | 1.43 | 0 | 0.68 | 0.75 | 1.43
| Delhi | 10.68 | 0 | 10.68 | 0 | 10.68 | 0 | 10.68 | 0 | 10.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1818 | 3.1818 | 12.69 | 0 | 12.69 | 0 | 12.69 | 0 | 12.69 | 0 | 12.69
| Haryana | 6.36 | 1.94 | 8.3 | 1.53 | 7.89 | 1.94 | 8.3 | 1.53 | 7.89 | 10.91 | 2.5 | 13.41 | 0 | 10.91 | 3.75 | 14.66 | 0 | 10.91 | 5.67 | 2.1 | 7.77 | 1.65 | 7.32 | 2.1 | 7.77 | 1.65 | 7.32
| H.P. | 3.18 | 0.97 | 4.15 | 1.53 | 4.71 | 1.67 | 4.85 | 1.66 | 4.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4 | 1.05 | 4.45 | 1.65 | 5.05 | 1.8 | 5.2 | 1.8 | 5.2
| J & K | 7.5 | 2.52 | 10.02 | 3.88 | 11.38 | 2.52 | 10.02 | 4.46 | 11.96 | 7.95 | 0 | 7.95 | 0 | 7.95 | 0 | 7.95 | 0 | 7.95 | 0 | 12.04 | 12.04 | 13.52 | 13.52 | 12.04 | 12.04 | 14.14 | 14.14
| Punjab | 11.59 | 0.97 | 12.56 | 0.28 | 11.87 | 0.97 | 12.56 | 0.42 | 12.01 | 22.73 | 3.1818 | 25.9118 | 3.1818 | 25.9118 | 1.25 | 23.98 | 0 | 22.73 | 10.41 | 1.05 | 11.46 | 0.3 | 10.71 | 1.05 | 11.46 | 0.45 | 10.86
| Rajasthan | 10 | 1.39 | 11.39 | 0.97 | 10.97 | 0.97 | 10.97 | 0.97 | 10.97 | 28.41 | 5.9091 | 34.3191 | 8.4091 | 36.8191 | 7.5 | 35.91 | 8.4091 | 36.8191 | 19.94 | 1.5 | 21.44 | 1.05 | 20.99 | 1.05 | 20.99 | 1.05 | 20.99
| U.P. | 31.3 | 5.25 | 36.55 | 4.28 | 35.58 | 4.97 | 36.27 | 3.57 | 34.87 | 15 | 3.4091 | 18.4091 | 3.4091 | 18.4091 | 2.5 | 17.5 | 3.4091 | 18.4091 | 19.49 | 5.68 | 25.17 | 4.63 | 24.12 | 5.38 | 24.87 | 3.86 | 23.35
| Uttarakhand | 3.7 | 1.51 | 5.21 | 1.39 | 5.09 | 1.51 | 5.21 | 1.25 | 4.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4 | 0.9 | 4.3 | 0.77 | 4.17 | 0.9 | 4.3 | 0.62 | 4.02
| Total | 85.45 | 14.55 | 100 | 14.55 | 100 | 14.55 | 100 | 14.55 | 100 | 85 | 15 | 100 | 15 | 100 | 15 | 100 | 15 | 100 | 75.68 | 24.32 | 100 | 24.32 | 100 | 24.32 | 100 | 24.32 | 100
|  | Nathpa-Jhakri (1500 MW) | [8 empty] | Tehri-I (1000 MW) | [8 empty] | DULHASTI (390 MW)
|  | 0.47 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.46 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.69 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23
| State/UT | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt
| Chandigarh | 0.53 | 0 | 0.53 | 0.47 | 1 | 0 | 0.53 | 0.47 | 1 | 0.6 | 0 | 0.6 | 0.47 | 1.07 | 0 | 0.6 | 0.47 | 1.07 | 0.47 | 0 | 0.47 | 0.72 | 1.19 | 0 | 0.47 | 0.72 | 1.19
| Delhi | 9.47 | 0 | 9.47 | 0 | 9.47 | 0 | 9.47 | 0 | 9.47 | 10.3 | 0 | 10.3 | 0 | 10.3 | 0 | 10.3 | 0 | 10.3 | 12.83 | 0 | 12.83 | 0 | 12.83 | 0 | 12.83 | 0 | 12.83
| Haryana | 4.27 | 1.32 | 5.59 | 1.04 | 5.31 | 1.32 | 5.59 | 1.04 | 5.31 | 4.3 | 1.32 | 5.62 | 1.04 | 5.34 | 1.32 | 5.62 | 1.04 | 5.34 | 5.47 | 2.01 | 7.48 | 1.57 | 7.04 | 2 | 7.47 | 1.57 | 7.04
| H.P. | 36.47 | 0.66 | 37.13 | 1.04 | 37.51 | 1.14 | 37.61 | 1.14 | 37.61 | 2.8 | 0.66 | 3.46 | 1.04 | 3.84 | 1.13 | 3.93 | 1.13 | 3.93 | 0 | 1 | 1 | 1.58 | 1.58 | 1.72 | 1.72 | 1.72 | 1.72
| J & K | 7 | 1.72 | 8.72 | 2.65 | 9.65 | 1.72 | 8.72 | 3.04 | 10.04 | 4.8 | 1.72 | 6.52 | 2.65 | 7.45 | 1.72 | 6.52 | 3.03 | 7.83 | 21.15 | 2.6 | 23.75 | 4.01 | 25.16 | 2.6 | 23.75 | 4.6 | 25.75
| Punjab | 10.13 | 0.66 | 10.79 | 0.19 | 10.32 | 0.66 | 10.79 | 0.29 | 10.42 | 7.7 | 0.66 | 8.36 | 0.19 | 7.89 | 0.66 | 8.36 | 0.28 | 7.98 | 8.28 | 1 | 9.28 | 0.29 | 8.57 | 1 | 9.28 | 0.43 | 8.71
| Rajasthan | 7.47 | 0.95 | 8.42 | 0.67 | 8.14 | 0.66 | 8.13 | 0.66 | 8.13 | 7.5 | 0.94 | 8.44 | 0.66 | 8.16 | 0.66 | 8.16 | 0.66 | 8.16 | 10.88 | 1.43 | 12.31 | 1 | 11.88 | 1 | 11.88 | 1 | 11.88
| U.P. | 14.73 | 3.58 | 18.31 | 2.92 | 17.65 | 3.39 | 18.12 | 2.43 | 17.16 | 37.4 | 3.57 | 40.97 | 2.91 | 40.31 | 3.38 | 40.78 | 2.44 | 39.84 | 21.81 | 5.41 | 27.22 | 4.41 | 26.22 | 5.13 | 26.94 | 3.68 | 25.49
| Uttarakhand | 0 | 1.04 | 1.04 | 0.95 | 0.95 | 1.04 | 1.04 | 0.86 | 0.86 | 14.7 | 1.03 | 15.73 | 0.94 | 15.64 | 1.03 | 15.73 | 0.85 | 15.55 | 4.11 | 1.55 | 5.66 | 1.42 | 5.53 | 1.55 | 5.66 | 1.28 | 5.39
| Total | 90.07 | 9.93 | 100 | 9.93 | 100 | 9.93 | 100 | 9.93 | 100 | 90.1 | 9.9 | 100 | 9.9 | 100 | 9.9 | 100 | 9.9 | 100 | 85 | 15 | 100 | 15 | 100 | 15 | 100 | 15 | 100
|  | Dhauliganga(280 MW) | [8 empty] | CHAMERA-II (300 MW) | [8 empty] | B. SIUL | SALAL | T.PUR | CHAM-I | URI
|  | 0.71 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 0.83 | 00-06 & 23-24 |  | 06-10 |  | 10-18 |  | 18-23 |  | 180 MW | 690 MW | 94 MW | 540 MW | 480 MW
| State/UT | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Share | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | U.A. | Entlmnt | Entlmnt '00-24
| Chandigarh | 0.72 | 0 | 0.72 | 0.71 | 1.43 | 0 | 0.72 | 0.71 | 1.43 | 0.67 | 0 | 0.67 | 0.86 | 1.53 | 0 | 0.67 | 0.86 | 1.53 | 0 | 0.27 | 1.28 | 3.9 | 0.62
82 | Delhi | 13.21 | 0 | 13.21 | 0 | 13.21 | 0 | 13.21 | 0 | 13.21 | 13.33 | 0 | 13.33 | 0 | 13.33 | 0 | 13.33 | 0 | 13.33 | 11 | 11.62 | 12.81 | 7.9 | 11.04
0.83 | Haryana | 5.71 | 2 | 7.71 | 1.57 | 7.28 | 2 | 7.71 | 1.57 | 7.28 | 5.67 | 2.4 | 8.07 | 1.89 | 7.56 | 2.4 | 8.07 | 1.89 | 7.56 | 30.5 | 15.02 | 6.4 | 15.8 | 5.42
82.83 | H.P. | 3.57 | 1 | 4.57 | 1.57 | 5.14 | 1.71 | 5.28 | 1.72 | 5.29 | 15.67 | 1.2 | 16.87 | 1.89 | 17.56 | 2.06 | 17.73 | 2.06 | 17.73 | 12 | 0.99 | 3.84 | 14.9 | 2.71
17.17 | J & K | 6.07 | 2.59 | 8.66 | 4.01 | 10.08 | 2.6 | 8.67 | 4.59 | 10.66 | 6.33 | 3.12 | 9.45 | 4.81 | 11.14 | 3.12 | 9.45 | 5.52 | 11.85 | 0 | 34.39 | 7.68 | 3.9 | 33.96
| Punjab | 10 | 1 | 11 | 0.29 | 10.29 | 1 | 11 | 0.43 | 10.43 | 10 | 1.2 | 11.2 | 0.34 | 10.34 | 1.2 | 11.2 | 0.52 | 10.52 | 46.5 | 26.6 | 17.93 | 10.2 | 13.75
| Rajasthan | 9.65 | 1.43 | 11.08 | 1 | 10.65 | 1 | 10.65 | 1 | 10.65 | 9.67 | 1.72 | 11.39 | 1.2 | 10.87 | 1.2 | 10.87 | 1.2 | 10.87 | 0 | 2.95 | 11.53 | 19.6 | 8.96
| U.P. | 20 | 5.41 | 25.41 | 4.41 | 24.41 | 5.12 | 25.12 | 3.68 | 23.68 | 20.66 | 6.5 | 27.16 | 5.3 | 25.96 | 6.16 | 26.82 | 4.42 | 25.08 | 0 | 6.95 | 22.64 | 20.27 | 20.06
| Uttarakhand | 16.07 | 1.57 | 17.64 | 1.44 | 17.51 | 1.57 | 17.64 | 1.3 | 17.37 | 0 | 1.86 | 1.86 | 1.71 | 1.71 | 1.86 | 1.86 | 1.53 | 1.53 | 0 | 1.21 | 15.89 | 3.53 | 3.48
| Total | 85 | 15 | 100 | 15 | 100 | 15 | 100 | 15 | 100 | 82 | 18 | 100 | 18 | 100 | 18 | 100 | 18 | 100 | 100 | 100 | 100 | 100 | 100
| Note: | Baira suil, Salal, Tanakpur, Chamera-I and Uri NHPC stations does not have Unallocated quota of power
Note on D29: dell:
Note on H13: dell:
Note on J29: dell:
Note on J41: dell:
Note on M28: dell:
Note on O28: dell:
Note on Q28: dell:
Note on S46: dell:
Note on V26: dell:
Note on X27: dell:

## Page18
14...माह ¨ÉÉSÉÇ 2010 का आवृत्ति विश्लेषण
FREQUENCY ANALYSIS FOR THE MONTH OF MARCH 2010
| Frequency(Hz.) |  |  | %age TimeSystem Frequency in frequency bands
Date | Max | Min | Avg. | <48.5 | 48.5- 48.8 | 48.8- 49 | 49-49.2 | 49.2- 49.5 | 49.5- 50 | 50-50.3 | 50.3-51 | >51.00
1 | 50.677 | 49.455 | 50.097 | 0 | 0 | 0 | 0 | 0.35 | 28.92 | 57.35 | 13.38 | 0
2 | 50.686 | 49.338 | 50.057 | 0 | 0 | 0 | 0 | 1.25 | 43.41 | 38.35 | 16.99 | 0
3 | 50.398 | 49.174 | 49.814 | 0 | 0 | 0 | 0.07 | 7.42 | 73.51 | 18.1 | 0.9 | 0
4 | 50.12 | 48.959 | 49.521 | 0 | 0 | 0.35 | 2.91 | 43.41 | 52.98 | 0.35 | 0 | 0
5 | 50.18 | 48.93 | 49.56 | 0 | 0 | 0.38 | 4.34 | 36.11 | 56.46 | 2.71 | 0 | 0
6 | 50.22 | 48.91 | 49.55 | 0 | 0 | 0.35 | 4.73 | 34.03 | 59.46 | 1.43 | 0 | 0
7 | 50.47 | 49.25 | 49.82 | 0 | 0 | 0 | 0 | 7.44 | 74.96 | 16.03 | 1.57 | 0
8 | 50.37 | 48.88 | 49.71 | 0 | 0 | 0.47 | 0.93 | 16.42 | 72.1 | 9.81 | 0.27 | 0
9 | 50.03 | 48.91 | 49.51 | 0 | 0 | 0.58 | 5.93 | 42.96 | 49.89 | 0.64 | 0 | 0
10 | 50.297 | 48.812 | 49.457 | 0 | 0 | 0.37 | 5.56 | 34.19 | 59.57 | 0.31 | 0 | 0
11 | 50.267 | 48.803 | 49.457 | 0 | 0 | 1.09 | 5.51 | 48.01 | 45.2 | 0.19 | 0 | 0
12 | 50.28 | 48.97 | 49.6 | 0 | 0 | 0.31 | 4.06 | 30.52 | 61.39 | 3.72 | 0 | 0
13 | 50.391 | 48.802 | 49.447 | 0 | 0 | 2.18 | 7.36 | 30.6 | 58.55 | 1.12 | 0.19 | 0
14 | 50.51 | 49.049 | 49.71 | 0 | 0 | 0 | 1.18 | 14.13 | 69.48 | 13.72 | 1.49 | 0
15 | 50.12 | 48.87 | 49.45 | 0 | 0 | 1.11 | 8.51 | 51.39 | 38.06 | 0.93 | 0 | 0
16 | 50.26 | 48.87 | 49.41 | 0 | 0 | 4.21 | 16.68 | 43.08 | 35.22 | 0.81 | 0 | 0
17 | 50.1 | 48.87 | 49.35 | 0 | 0 | 6.68 | 13.87 | 57.86 | 21.18 | 0.41 | 0 | 0
18 | 50.04 | 48.8 | 49.29 | 0 | 0 | 10.52 | 24.94 | 46.27 | 18.1 | 0.17 | 0 | 0
19 | 50.25 | 48.87 | 49.39 | 0 | 0 | 5.21 | 16.34 | 46.54 | 31.32 | 0.59 | 0 | 0
20 | 50.18 | 48.9 | 49.58 | 0 | 0 | 0.35 | 1.39 | 37.12 | 57.88 | 3.26 | 0 | 0
21 | 50.42 | 49.11 | 49.74 | 0 | 0 | 0 | 0.31 | 12.52 | 77.79 | 9.07 | 0.31 | 0
22 | 50.38 | 48.87 | 49.74 | 0 | 0 | 2.08 | 4.89 | 31.52 | 58.38 | 2.92 | 0.21 | 0
23 | 50.35 | 48.87 | 49.52 | 0 | 0 | 1.74 | 6.6 | 43.11 | 45.47 | 2.92 | 0.16 | 0
24 | 50.33 | 48.93 | 49.53 | 0 | 0 | 0.52 | 4.66 | 44.73 | 47.23 | 2.72 | 0.14 | 0
25 | 50.64 | 49.05 | 49.69 | 0 | 0 | 0 | 0.79 | 19.04 | 70.73 | 8.08 | 1.36 | 0
26 | 50.555 | 48.964 | 49.599 | 0 | 0 | 0.56 | 4.17 | 42.62 | 49.63 | 2.85 | 0.17 | 0
27 | 50.55 | 49.09 | 49.71 | 0 | 0 | 0 | 0.8 | 14.83 | 74.49 | 8.14 | 1.74 | 0
28 | 50.53 | 49.23 | 49.85 | 0 | 0 | 0 | 0 | 4.34 | 67.94 | 25.39 | 2.33 | 0
29 | 50.49 | 49.88 | 49.447 | 0 | 0 | 0 | 0 | 3.89 | 68.38 | 26.2 | 1.53 | 0
30 | 50.61 | 49.24 | 49.98 | 0 | 0 | 0 | 0 | 2.71 | 55.25 | 35.28 | 6.76 | 0
31 | 50.66 | 49.22 | 49.447 | 0 | 0 | 0 | 0 | 4.06 | 55.66 | 36.63 | 3.65 | 0
Avg. | 50.37 | 49.03 | 49.61 | 0 | 0 | 1.26 | 4.7268 | 27.499 | 54.1481 | 10.6516 | 1.7145 | 0

## Page19
15…. VOLTAGE ANALYSIS
¨ÉÉ½þþ ¨ÉÉSÉÇ 2010 Eäò nùÉè®úÉxÉ 400 ÊEò.´ÉÉä. ¤ÉºÉÉå ¨Éå +ÊvÉEòiÉ¨É +Éè®ú xªÉÚxÉiÉ¨É nùVÉÇ ÊEòªÉÉ MÉªÉÉ ´ÉÉä±]äõVÉ
MAXIMUM AND MINIMUM VOLTAGES RECORDED AT 400KV BUSES DURING THE MONTH OF MARCH 2010
[5 empty] | (All figures in KV) |  | (ºÉ¦ÉÒ +ÉÄEòcä÷ ÊEò.´ÉÉä. ¨Éå)
ÊnùxÉ DATE | 400 ÊEò.´ÉÉä. nùÉnù®úÒ {É®ú AT 400KV DADRI |  | 400 ÊEò.´ÉÉä. úÖ­Ö¯Öã¸ü {É®ú AT 400KV KANPUR |  | 400 ÊEò.´ÉÉä. ´ÖÖêÖÖ {É®ú AT 400KV MOGA |  | 400 Êeò.´ÉÉä. AT 400KV Bassi
| +ÊvÉEòiÉ¨É | xªÉÚxÉiÉ¨É | +ÊvÉEòiÉ¨É | xªÉÚxÉiÉ¨É | +ÊvÉEòiÉ¨É | xªÉÚxÉiÉ¨É | +ÊvÉEòiÉ¨É | xªÉÚxÉiÉ¨É
| MAXIMUM | MINIMUM | MAXIMUM | MINIMUM | MAXIMUM | MINIMUM | MAXIMUM | MINIMUM
1 | 418 | 397 | 417 | 397 | 414 | 386 | 426 | 397
2 | 415 | 392 | 414 | 395 | 416 | 385 | 425 | 387
3 | 411 | 385 | 413 | 390 | 412 | 387 | 422 | 389
4 | 412 | 389 | 410 | 391 | 413 | 392 | 421 | 389
5 | 413 | 391 | 413 | 394 | 413 | 393 | 420 | 390
6 | 412 | 395 | 411 | 394 | 414 | 395 | 421 | 392
7 | 417 | 398 | 415 | 398 | 420 | 391 | 425 | 395
8 | 414 | 393 | 415 | 390 | 412 | 393 | 424 | 390
9 | 408 | 387 | 408 | 392 | 411 | 391 | 411 | 385
10 | 406 | 388 | 412 | 395 | 405 | 390 | 416 | 382
11 | 409 | 387 | 413 | 390 | 410 | 388 | 416 | 382
12 | 409 | 379 | 416 | 390 | 413 | 392 | 418 | 379
13 | 412 | 396 | 417 | 394 | 411 | 391 | 420 | 386
14 | 415 | 386 | 416 | 391 | 413 | 384 | 425 | 387
15 | 409 | 389 | 412 | 393 | 413 | 392 | 421 | 388
16 | 409 | 387 | 411 | 392 | 414 | 391 | 416 | 383
17 | 410 | 382 | 413 | 391 | 412 | 390 | 418 | 385
18 | 412 | 389 | 414 | 394 | 415 | 391 | 420 | 387
19 | 412 | 381 | 416 | 392 | 412 | 388 | 420 | 387
20 | 413 | 389 | 413 | 396 | 410 | 388 | 422 | 394 | 201
21 | 414 | 391 | 416 | 394 | 414 | 391 | 423 | 392
22 | 414 | 383 | 416 | 392 | 418 | 385 | 427 | 385
23 | 412 | 390 | 418 | 400 | 412 | 389 | 425 | 396
24 | 412 | 388 | 415 | 395 | 408 | 387 | 420 | 394
25 | 409 | 385 | 412 | 394 | 411 | 387 | 419 | 395
26 | 410 | 382 | 412 | 388 | 413 | 385 | 418 | 385
27 | 410 | 389 | 413 | 394 | 414 | 387 | 423 | 394
28 | 411 | 392 | 413 | 395 | 411 | 387 | 425 | 401
29 | 410 | 387 | 414 | 396 | 414 | 391 | 421 | 399
30 | 412 | 387 | 415 | 392 | 420 | 387 | 424 | 398
31 | 409 | 385 | 411 | 396 | 414 | 389 | 425 | 398
Max | 418 | 398 | 418 | 400 | 420 | 395 | 427 | 401
Min | 406 | 379 | 408 | 388 | 405 | 384 | 411 | 379

## Page20
16…..'=kÉ®úÒ IÉäjÉ ¨Éå 31.03.10 EòÉä Ê´ÉtÖiÉ Eò]õÉèÊiÉ Eò®úxÉä ´ÉÉ±ÉÒ Eò¨É +É´ÉÞÊkÉ Ê®ú±ÉäWÉ EòÒ ÎºlÉÊiÉ
DETAILS OF UFRs FOR LOAD SHEDDING IN THE NORTHERN REGION AS ON 31.03.10
A. df/dt RELAYING SCHEME (As recommeded by NREB)
(All figures in MW)
®úÉVªÉ/Eäòxpù ¶ÉÉÊºÉiÉ/¦ÉhÉÉ±ÉÒ | Setting(Hz/s) and load relief (MW) through df/dt relays to be initiated at | [7 empty] | STATE / UT / SYSTEM
| 49.9 Hz./0.1 Hz/sec.(1st.Stg.) |  | 49.9Hz/0.2 Hz/sec.(2nd.Stg.) |  | 49.9Hz/0.3 Hz/sec.(3rd. Stg.)
| Load Relief |  | Load Relief |  | Load Relief
SÉhb÷ÒMÉgø | 0 |  | 50 |  | 50 |  |  |  | Chandigarh
Ênù±±ÉÒ | 250 |  | 280 |  | 280 |  |  |  | Delhi
½þÊ®úªÉÉhÉÉ | 280 |  | 310 |  | 310 |  |  |  | Haryana
Ê½þ¨ÉÉSÉ±É ¦Énäù¶É | 50 |  | 70 |  | 70 |  |  |  | HP
VÉ¨¨ÉÚ ´É Eò¶É¨ÉÒ®ú | 90 |  | 90 |  | 90 |  |  |  | J&K
{ÉÆVÉÉ¤É | 430 |  | 490 |  | 490 |  |  |  | Punjab
®úÉVÉºlÉÉxÉ | 330 |  | 370 |  | 370 |  |  |  | Rajasthan
=kÉ®ú ¦Énäù¶É | 500 |  | 280 |  | 280 |  |  |  | UP
ˆ¢Ö¸ÖÖ›üü | 70 |  | 70 |  | 70 |  |  |  | Uttarakhand
EÖò±É ªÉÉäMÉ | 2000 |  | 2010 |  | 2010 |  |  |  | Total
df/dt: Total in western UP=810
df/dt: Total in Punjab,Haryana,HP ,J&K,Chandigarh=2870
B. FLAT UFRs SCHEME
|  | STATE | Flat UFRs |  |  |  |  | TOTAL
|  |  | 48.8 Hz | 48.6 Hz | 48.2 Hz
|  | Chandigarh | 0 | 10 | 0 | 10 |  | 10
|  | Delhi | 110 | 140 | 150 | 400 |  | 400
|  | Haryana | 110 | 140 | 150 |  |  | 400
|  | HP | 20 | 20 | 75 |  |  | 115
|  | J&K | 40 | 50 | 75 |  |  | 165
|  | Punjab | 180 | 220 | 250 |  |  | 650
|  | Rajasthan | 120 | 150 | 225 |  |  | 495
|  | UP | 190 | 240 | 275 |  |  | 705
|  | Uttarakhand | 30 | 30 | 50 |  |  | 110
|  | Total | 800 | 1000 | 1250 |  |  | 3050

## Page21
17....31.03.2010 EòÉä =kÉ®úÒ IÉäjÉ ¨Éå Eèò{ÉäºÉÒ]õºÉÇú EòÒ ÎºlÉÊiÉ
PROGRESS OF INSTALLATION OF SHUNT CAPACITORS(11 KV AND ABOVE) IN THE NORTHERN REGION AS ON 31.03.2010
®úÉúVªÉ/Eäò.¶ÉÉ.¦É./ | Requirement as per NRPC Studied | Installed as on 31.03.09 | New Capacitors to be added during 2009-10 | Capacitors installed during 2009-10 upto 31.03.2010 | Balance to be istalled during 2009-10 | Defective Capacitors need revival | Defective Capacitors revived till 31.03.2010 | STATE / UT / SYSTEM
¦ÉhÉÉ±ÉÒ
SÉhb÷ÒMÉgø | 157 | 127 | 30 | 0 | 30 | 5 | 8 | Chandigarh
Ênù±±ÉÒ | 2097 | 3476 | 0 | 0 | 0 | 10 | 0 | Delhi
½þÊ®úªÉÉhÉÉ | 4175 | 3359 | 816 | 0 | 816 | 322 | 0 | Haryana
BSÉ.{ÉÒ. | 551 | 514 | 37 | 0 | 37 | 124 | 19 | H.P.
VÉ ´É Eò | 1271 | 147 | 1124 | 0 | 1124 | 170 | 0 | J & K
{ÉÆVÉÉ¤É | 6479 | 5736 | 743 | 551 | 192 | 203 | 162 | Punjab
®úÉVÉºlÉÉxÉ | 4269 | 3785 | 484 | 43 | 441 | 363 | 1169 | Rajasthan
=kÉ®ú ¦Énäù¶É | 7261 | 5812 | 1449 | 0 | 1449 | 1910 | 105 | U.P.
ˆ¢Ö¸ÖÖ›üü | 586 | 353 | 233 | 0 | 233 | 35 | 0 | Uttaranchal
EÖò±É | 26846 | 23309 | 4916 | 594 | 4322 | 3142 | 1463 | TOTAL

## Page22(i)
18...ÊxÉ¨ÉÉÇhÉÉvÉÒxÉ ¦É¨ÉÖJÉ {ÉÉ®äú¹ÉhÉ ±ÉÉ<ÇxÉÉå EòÒ ÎºlÉÊiÉ 31.03.10 iÉEò
STATUS OF IMPORTANT TRANSMISSION LINES UNDER CONSTRUCTION AS ON 31.03.10
Sl. | Generating Plant /Associated | No. of | Total | String.Compl. | Programme | Slipped Prog. | Stringing April | TL | Stubs | TE | Stringing | Target |  | Remarks
No. | Transmission Scheme | Circuits | Length | upto March 09 | for 2009-10 | from2008-09 | 2009 onwards | (Nos.) | (Nos.) | (Nos.) | Completed | Original | Revised
|  |  | CKM | CKM | CKM |  | CKM |  |  |  | CKM
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 765 kV Transmission Lines
Central Sector
i | LILO of Tehri_Meerut at Tehri Pooling Point. | 2xD/C | 25 | 3 | 4 | 18 | 16 | 59 | 57 | 46 | 19 | June'08 | June..10
( to be charged at 400KV)
2 | 500 kV HVDCTransmission Lines
Central Sector
i | 500KV Balia-Bhiwadi(2500MW) | Bipole | 1580 | 1300 | 280 |  | 280 | 2159 | 2159 | 2159 | 1580 | Sept.'09 | April..10 | Line test charged,
3 | 400 kV Transmission Lines
Central Sector
i | Barh-Balia(Quad) | D/C | 488 | 474 | 16 |  | 11 | 645 | 645 | 645 | 485 | Sept.'09 | July..10
ii | LILO of one ckt. Of Dhauliganga-Bareilly | D/C | 2 | 0 | 6 |  | 2 | 5 | 5 | 5 | 2 | March.07 | June..10 | Completion matching with
| at Pithoragarh(to be operated at220 kV) | [5 empty] | CKM 14: Pithoragarh S/S.
iii | Koteshwar-Tehri Pooling Point. | D/C | 5 | 0 | 6 |  | 0 | 11 | 4 | 0 | 0 | June'08 | June..10
iv | Koldam-Nalagarh(Quad) | D/C | 93 | 87 | 3 |  | 6 | 127 | 127 | 127 | 93 | Sept'.08 | June..10
v | Bhiwadi-Agra | D/C | 418 | 405 | 12 |  | 13 | 582 | 582 | 582 | 418 | June'09 | Aug..09 | Commissioned 8/09
vi | Bhiwadi-Moga | D/C | 702 | 695 | 7 |  | 7 | 932 | 932 | 932 | 702 | June'09 | March'10 | Commissioned 3/2010
vii | LILO of Parbati-II-Koldam/Nalagarh at Parbati | D/C | 20 | 0 | 0 |  | 0 | 20 | 0 | 0 | 0 | Jan.'10 | Nov..10
viii | LILO of Parbati-II-Parbati Pooling Pt. at Parbati-III | D/C | 7 | 0 | 0 |  | CKM 7: 0; CKM 12: Jan.'10; CKM 13: Nov.,10
ix | Parbati Pooling Point.-Amritsar | D/C | 516 | 0 | 285 | 75 | 182 | 639 | 562 | 473 | 182 | Jan.'10 | June..11 | WIP
x | Kankroli-Jodhpur | D/C | 193 | 185 | 8 |  | 8 | 517 | 517 | 517 | 193 | Oct.'09 | April.10 | Completed
xi | LILO of Ist ckt.of Kankroli-Zerda at Bhinmal | D/C | 55 | 52 | 3 |  | 3 | 152 | 152 | 152 | 55 | Dec.'09 |  | Commissioned 8/09
xii | LILO of Ballabhgarh-Bhiwadi at Gurgaon | D/C | 68 | 0 | 58 | 10 | 68 | 109 | 109 | 109 | 68 | July'09 | April.10 | Completed
State Sector
Rajasthan (RVPNL)
i | Dahra(Kota)-Bhilwara | S/C +D/C | 186 | 65 | 118 |  | 100 | 461 | 458 | 441 | 165 | Sept.08 | April.10
ii | LILO Dholpur-Heerapura at Hindaun | D/C | 8 | 0 | 13 |  | 8 | 14 | 14 | 14 | 8 | Sept.08 | Dec..09 | Commissioned12/09
iii | Chhabra-Hindaun | S/C +D/C | 342 | 224 | 37 | 81 | 117 | 803 | 803 | 803 | 341 | .March09 | April.10
iv | Suratgarh STPS -Bikaner | S/C | 162 | 133 | 0 | 29 | 29 | 403 | 403 | 403 | 162 | Oct.08 | Sept..09 | Commissioned 9/09
v | Jaisalmer-Barmer | S/C | 143 | 0 | 100 |  | 69 | 327 | 327 | 306 | 69 | April'09 | April.10
vi | Jaisalmer-Jodhpur | S/C | 250 | 75 | 150 |  | 51 | 601 | 596 | 536 | 126 | April'09 | April.10
vii | Raj West-Jodhpur | D/C | 417 | 0 | 391 |  | 417 | 560 | 560 | 560 | 417 | April'09 | April.10
viii | KTPS-Kota(PG)(to be charged at 220 KV) | D/C | 13 | 0 | 3 | 10 | 0 | 28 | 22 | 6 | 0 | March'08 | April.10
ix | Jodhpur-Merta(2nd ckt.) | S/C | 110 | 0 | 60 |  | 69 | 262 | 262 | 248 | 69 | March'08 | April.10

## Page22(ii)
Sl. | Generating Plant /Associated | No. of | Total | String.Compl. | Programme | Slipped Prog. | Stringing April | TL | Stubs | TE | Stringing | Target |  | Remarks
No. | Transmission Scheme | Circuits | Length | upto March 09 | for 2009-10 | from2008-09 | 2009 onwards | (Nos.) | (Nos.) | (Nos.) | Completed | Original | Revised
|  |  | CKM | CKM | CKM |  | CKM |  |  |  | CKM
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
HARYANA (HVPNL) :
i | Jhajjar-Daultabad | D/C | 136 | 0 | 60 |  | 0 | 175 | 147 | 20 | 0 | March'10 | June.10 | Tender awarded
ii | Jhajjar-Mundka | D/C | 132 | 0 | 0 |  | 0 | 187 | 91 | 18 | 0 | March'10 | June..10 | LOI placed
iii | Hissar-Kirori | D/C | 13 | 0 | 13 |  | 12 | 22 | 22 | 22 | 12 | Oct..09 | April.10
iv | Hissar-Fatehabad | D/C | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | March..11 |  | One ckt. Commissioned in 01/2010
4 | 220 kV Transmission Lines
Central Sector
State Sector
CHANDIGARH :
i | Ganguwal-Mohali (2nd Ckt. Stringing) | S/C | 72.4 | 72 | 0 |  | 0 | Existing |  |  | 72 | Jun'06 | April.10 | Deposit work of PSEB. Re-alingment
| (Incl of re-alignment) | [5 empty] | CKM 14: of Bays in progress
DELHI (DTL) :
i | Gajipur-Noida | D/C | 16 | 0 | 0 | 16 | 0 | 48 | 38 | 28 | 0 | March'04 |  | Work deffered
ii | LILO of Bawana-Narela at Khanjawala | 2xD/C | 12 | 12 | 0 | 0 | 0 | 33 | 33 | 31 | 12 | June'03 | April..10 | Ckt1of loop in charged,work awarded
iii | Papankalan-I-Papankalan-II | D/C | 11 | 0 | 0 | 11 | 0 | 32 | 32 | 32 | 0 | March'06 |  | Scheme under revision,deferred
iv | LILO of Bawana-Narela at Bawana DSIDC | 2xD/C | 14 | 13 | 1 | 0 | 1 | 52 | 52 | 52 | 14 | Dec.'05 | Nov..09 | Loop in portion charged WIP for Loop out
v | U/G of Maharani Bagh(PG)-Masjid Moth | D/C | 19 | 0 | 0 | 19 | 0 | Cable |  |  |  | Mar.'08 | July..10 | Bid opened 12.5.08Techno comm.evaluation in progress
vi | U/G of Maharani Bagh-Electric lane | D/C | 19 | 0 | 0 | 19 | 0 | Cable |  |  |  | March'08 | Aug..10 | Work awarded
vii | U/G of Maharani Bagh-Trauma Center/AIIMS | D/C | 22 | 0 | 0 | 22 | 0 | Cable |  |  |  | March'08 | Aug..10 | Work awarded
Himachal Pardesh(HPSEB)
i | Kashang-Bhaba | D/C | 76 | 58 | 18 | 0 | 17 | 100 | 100 | 100 | 75 | Mar'07 | April.10
ii | LILO of Kasang-Bhaba at Bhoktoo | D/C | 63 | 0 | 0 | 6 | CKM 7: 0; CKM 12: Jan.'08; CKM 13: April.10
iii | Allain Duhangan-Panarsa-Nalagarh D/C | D/C | 349 | 68 | 281 |  | 10 | 580 | 432 | 408 | 78 | June'09 | Sept.'09 | Forest clearance obtained and WIP
iv | LILO of Allain Duhangan-Nalagarh at Chhaur | D/C | 1 | 0 | 1 |  | CKM 7: 0; CKM 8: 0; CKM 11: 0; CKM 12: Sept.'09
v | Khodri-Majri (2ndckt) | S/C on D/C | 35 | 34 | 1 |  | 0 | Tower Existing |  |  | 34 | Mar'08 | April.10 | WIP
vi | Kangoo-Rauri | S/C | 24 | 0 | 0 |  | 4 | 62 | 57 | 47 | 4 | June'09 | April.10 | Forest clearance awaited
HARYANA (HVPNL) :
i | YTPP-Nilokheri | D/C | 104 | 0 | 0 | 104 | 97 | 173 | 168 | 166 | 97 | Mar'08 | April.10 | WIP
ii | LILO of Jind Hissar at Kirori | D/C | 26 | 0 | 25 | 0 | 26 | 92 | 92 | 92 | 26 | March'08 | April.10 | Line test charged on 1.4.09
iii | Kirori-Masudpur | D/C | 24 | 0 | 24 | 0 | 24 | 105 | 105 | 105 | 24 | March'08 | Oct..09 | Commissioned 10/2009
iv | Badshahpur–Rewari (2nd Ckt) Strg. | S/C | 51 | 50 | 1 |  | 1 | Tower Existing |  |  | 51 | Jun'06 | April.10 | Stringing completed

## Page22(iii)
Sl. | Generating Plant /Associated | No. of | Total | String.Compl. | Programme | Slipped Prog. | Stringing April | TL | Stubs | TE | Stringing | Target |  | Remarks
No. | Transmission Scheme | Circuits | Length | upto March 09 | for 2009-10 | from2008-09 | 2009 onwards | (Nos.) | (Nos.) | (Nos.) | Completed | Original | Revised
|  |  | CKM | CKM | CKM |  | CKM |  |  |  | CKM
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
v | Badshahpur-IMT Manesar 2ndCkt Strg. | S/C | 12 | 0 | 12 |  | 0 | Tower Existing |  |  | 0 | Mar'07 | April.10
vi | Cheeka-Durala | D/C | 106 | 98 | 0 | 8 | 2 | 168 | 168 | 168 | 100 | Dec.'08 | April.10 | WIP
vii | LILO of Palli-Gurgaon Sec 52A at GurgaonSec 56 | D/C | 2 | 0 | 2 | 0 | 2 | 4 | 4 | 4 | 2 | Dec.'08 | Aug..09 | Commissioned 8/09
viii | LILO of Jind- Hissar at Masudpur | D/C | 4 | 0 | 4 | 0 | 4 | 12 | 12 | 12 | 4 | Dec.'08 | April.10 | Line work completed
PUNJAB (PSEB) :
i | GHTP-Himatpura D/C | D/C | 80 | 0 | 0 | 80 | 53 | 126 | 126 | 124 | 53 | Dec.'07 | April.10 | WIP
ii | LILO one ckt. Of Lalton Kalan-Dhandarikalan | D/C | 5 | 0 | 5 |  | 0 | 12 | 4 | 2 | 0 | Aug.,09 | Dec..10 | WIP
at Ludhiana
iii | LILO one ckt. Of Lalton Kalan-Sahnewal | D/C | 3 | 0 | 3 |  | 0 | 12 | 0 | 0 | 0 | Aug.,09 | June..10 | Revised Route Plan approved
at Ludhiana(PG)
iv | Ludhiana(400 kv)-Doraha(220kv) | S/C on D/C | 18 | 0 | 18 |  | 0 |  |  |  |  | Aug.,09 | Dec..10 | Dropped
v | Ranjit Sagar Dam – Sarna (ckt.4 ) | D/C | 30 | 30 | 0 |  | 0 |  | Existing |  | 30 | Jun'05 | April.10 | Strg. Comp.forest clearance awaited
vi | LILO of Malerkotla – Lalton Kalan | D/C | 2 | 0 | 0 | 2 | 2 | 5 | 5 | 5 | 2 | ﻿Mar-06 | April.10 | Strg.Completed
S/C at Pakhowal
vii | Phagan Majra (400 kV) -F.P.Nabha | D/C | 66 | 13 | 52 |  | 16 | 108 | 108 | 106 | 29 | ﻿Mar-08 | Dec..10 | WIP
viii | LILO of one ckt.of GGSSTP- Mohali-I at Kharar | D/C | 6 | 0 | 0 | 10 | 0 | 12 | 11 | 0 | 0 | ﻿Dec-07 | June..10
ix | Nalagarh-Mohali -I | D/C | 107 | 79 | 28 | 7 | 24 | 198 | 198 | 193 | 103 | ﻿Jul-07 | June..10
x | LILO of one ckt. of Moga-Mukatsar DC at Sadiq | D/C | 38 | 0 | 1 | 49 | 0 | 62 | 20 | 11 | 0 | March'09 | June.10 | WIP
xi | LILO of one ckt. Of Fatehgarh Churian-Civil Line | D/C | 10 | 0 | 5 |  | 10 | 18 | 18 | 18 | 10 | June'09 | Dec.0.9 | Loop in portion Commissioned
| Amritsar at Majitha | [12 empty] | in 07/09,Loop out comm. In12/09
Rajasthan( RVPNL)
i | Giral TPS-Barmer 2nd ckt. | S/C | 35 | 9 | 0 | 31 | 26 | 109 | 109 | 109 | 35 | ﻿Mar-07 | Nov..-09 | Commissioned 11/09
ii | GiralTPS-Baitoo | S/C | 55 | 0 | 0 | 55 | 55 | 178 | 178 | 178 | 55 | March'09 | Dec.'09 | Commissioned 12/09
iii | Baitoo-Balotra | S/C | 48 | 0 | 0 | 48 | 48 | 146 | 146 | 146 | 48 | March'09 | Nov..-09 | Commissioned 11/09
iv | BarsinghsarTPS-Phalodi | S/C | 140 | 0 | 40 | 100 | 0 | 446 | 280 | 153 | 0 | March'09 | June.10
v | Ext. of Bikaner-Barsinghsar at BarsinghsarTPS | S/C | 3 | 3 | 0 |  | 0 | 10 | 10 | 10 | 3 | April'09 | April.10 | Strg. Completed
vi | LILO Kota-Bhilwara at Kota (PG) | D/C | 4 | 0 | 0 | 4 | 0 | 8 | 8 | 5 | 0 | ﻿Mar-08 | April.10 | Work awarded
vii | Kankroli(PG)-Kankroli | S/C | 8 | 0 | 0 | 22 | 8 | 28 | 28 | 28 | 8 | April'08 | March'10 | Commissioned in 3/10
viii | Chhabra TPS-Jhalawar S/C | S/C | 100 | 1 | 0 | 124 | 60 | 329 | 268 | 252 | 61 | ﻿Sept-08 | June.10
ix | Chhabra -Baran-Dahra | S/C | 138 | 19 | 0 | 111 | 119 | 355 | 355 | 353 | 138 | ﻿Sept-08 | June.09 | Commissioned 6/09
x | LILO Bhilwara-Pali at Bhilwara (400kv) | D/C | 10 | 0 | 0 | 10 | 10 | 17 | 17 | 17 | 10 | ﻿Sept-08 | Sept.09 | Commissioned 9/09
xi | LILO Bhilwara-Bali at Bhilwara (400kv) | D/C | 6 | 0 | 0 | 10 | 6 | 11 | 11 | 11 | 6 | ﻿Sept-08 | Sept.09 | commissioned9/09
xii | Hindaun(400kv)-Hidaun(220kv) | D/C | 16 | 15 | 0 | 1 | 1 | 28 | 28 | 28 | 16 | ﻿Sept-08 | Sept.09 | Commissioned 9/09
xiii | Hindaun(400kv)-Mandawar | S/C | 47 | 0 | 1 | 45 | 47 | 150 | 150 | 150 | 47 | ﻿Sept-08 | April.10 | Strg.completed

## Page22( iv)
Sl. | Generating Plant /Associated | No. of | Total | String.Compl. | Programme | Slipped Prog. | Stringing April | TL | Stubs | TE | Stringing | Target |  | Remarks
No. | Transmission Scheme | Circuits | Length | upto March 09 | for 2009-10 | from2008-09 | 2009 onwards | (Nos.) | (Nos.) | (Nos.) | Completed | Original | Revised
|  |  | CKM | CKM | CKM |  | CKM |  |  |  | CKM
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
xiv | LILO Bikaner-Sridungargarh atBikaner (400 kV) | D/C | 2 | 0 | 0 | 2 | 0 |  | 0 | 0 | 0 | Oct.'08 | April,10
xv | LILO Bikaner-Nagaur at Bikaner(400kv) | D/C | 37 | 0 | 2 | 38 | 37 | 64 | 64 | 64 | 37 | Oct.'08 | March..10 | Commissioned 3/10
xvi | Raj West-Barmer | D/C | 27 | 20 | 7 |  | 7 | 51 | 51 | 51 | 27 | April'09 |  | Commissioned 4/2009
xvii | Raj West-Dhorimanna | D/C | 90 | 0 | 90 |  | 0 | 274 | 87 | 62 | 0 | March'10 | December.10
xviii | Kankroli (PG)-Debari | S/C | 63 | 35 | 0 | 28 | 28 | 200 | 200 | 200 | 63 | ﻿Mar-08 | Aug..09 | Commissioned 8/2009
xix | LILO one ckt Bassi-Heerapura at Jagatpura | D/C | 19 | 0 | 0 | 22 | 0 | 42 | 39 | 31 | 0 | ﻿Mar-09 | June.10
xx | Dhorimana-Sanchore(Jalor) | D/C | 64 | 0 | 64 | 0 | 0 | 199 | 128 | 97 | 0 | ﻿Mar-09 | June.10
xxi | LILO Heerapura-Kukas at Renwal | D/C | 49 | 0 | 49 |  | 49 | 82 | 82 | 82 | 49 | July'08 | May'09 | Commissioned 5/2009
xxii | LILO Heerapura-Bassi at MahindraSEZ(Jaipur) | D/C | 16 | 0 | 24 |  | 2 | 30 | 30 | 18 | 2 | July'08 | June..10
UTTAR PRADESH (UPPCL) :
i | Matore(PG)-Nehtaur | S/C | 75 | 57 | 15 | 16 | 3 | 216 | 215 | 214 | 60 | June'09 | June.10 | Forest clearnce awaited
ii | Nanauta-Muzaffarnagar | S/C | 55 | 0 | 0 | 55 | 47 | 174 | 174 | 173 | 47 | June'09 | June..10
iii | Muzaffarnagar-Shamli | S/C | 56 | 0 | 0 | 56 | 22 | 178 | 171 | 170 | 22 | ﻿Mar-08 | June..10
iv | LILO of Saharanpur-Shamli at Nanouta | D/C | 6 | 0 | 0 | 6 | 2 | 12 | 8 | 8 | 2 | ﻿Apr-08 | June.10 | WIP
v | Metore(Meerut) (PG)-Gajraula | S/C | 87 | 58 | 0 | 29 | 28 | 255 | 255 | 255 | 86 | ﻿Apr-08 | June.10 | WIP
vi | LILO of Moradabad-NAPP at Sambhal | D/C | 3 | 0 | 0 | 3 | 0 | 9 | 7 | 5 | 0 | March'08 | June.10
vii | LILO of Khurja-Muradnagar at Dadri | D/C | 24 | 7 | 0 | 16 | 17 | 50 | 50 | 50 | 24 | ﻿Mar-08 | Feb..10 | Commissioned in 2/2010
viii | Basti-Gonda | S/C | 113 | 0 | 0 | 25 | 0 | 300 | 245 | 211 | 0 | April'08 | June..10 | WIP
ix | LILO of Sultanpur-Gonda atSohawal Gomtinagar | D/C | 26 | 0 | 26 |  | 26 | 88 | 88 | 88 | 26 | Dec.'08 | Jan..10 | Commissioned 01/2010
x | Bhauti(PG)-Orai | S/C | 90 | 90 | 0 |  | 0 | 263 | 263 | 263 | 90 | July'08 |  | Commissioned 04/2009
UTTARAKHAND (PTCUL)
i | Rishikesh-Maneribali Stage-II (3rd ckt.) | S/C | 79 | 78 | 1 |  | 1 | 230 | 230 | 230 | 79 | Dec.'05 | May'09 | Commissioned 5/2009
ii | Ghansali-Chamba | S/C | 35 | 10 | 25 |  | 25 | 94 | 94 | 94 | 35 | Dec.'05 | Oct.'09 | Commissioned 10/2009
iii | Bhilanganga-Ghansali | S/C | 38 | 0 | 0 |  | 0 |  |  |  |  | Dec.'05 | May..10 | WIP
iv | Kashipur - Barheni | D/C | 52 | 0 | 54 |  | 1 | 84 | 84 | 79 | 1 | Dec.'06 | May.10 | WIP
v | Barheni - Pantnagar | S/C | 35 | 35 | 0 |  | 0 | 115 | 115 | 115 | 35 | ﻿Dec-06 | April.10 | Stinging completed
JAMMU & KASHMIR (J&K) :
i | Zainkote-Alusteng-Mirbazar | D/C | 254 | 0 | 0 |  | 0 | 443 | 384 | 0 | 0 | March'10 | March..11
ii | Wagoora-Mirbazar | D/C | 104 | 0 | 0 |  | 0 | 178 | 172 | 20 | 0 | March'09 | Sept.10 | WIP
iii | Wagoora-Budgam-Zainkot | D/C | 60 | 0 | 0 |  | 0 | 114 | 96 | 11 | 0 | March'09 | March..11
iv | Zainkot-Amargarh | D/C | 85 | 0 | 0 |  | 0 | 140 | 130 | 27 | 0 | March'10 | March..11
v | Udampur-Gladni | S/C | 48 | 39 | 0 | 9 | 0 | 165 | 165 | 163 | 39 | April'08 | Dec.'10 | WIP
vi | Thein(RSD)-Hiranagar(2nd ckt.) | S/C | 40 | 37 | 3 | 0 | 2 | 117 | 117 | 117 | 39 | March'08 | April.10 | WIP
vii | LILO Kishanpur-Pampore at Ramban | D/C | 4 | 0 | 0 |  | 0 | 6 | 2 | 0 | 0 | March'09 | June..10 | Linked with Ramban S/S
viii | Barn-Bishnah-Hira nagar | D/C | 165 | 0 | 0 |  | 0 | 250 | 130 | 66 | 0 | March'09 | Dec.'10 | Contract agrement executed with KEC

## Page23
19...xÉ<Ç ºÉÆºlÉÉÊ{ÉiÉ EòÒ VÉÉxÉä ´ÉÉ±ÉÒ =i{ÉÉnùxÉ ªÉÉäVÉxÉÉ+Éå EòÒ +xÉÖºÉÚÊSÉ
COMMISSIONING SCHEDULE OF NEW GENERATION SCHEMES
Gò¨É ºÉÆ. | BVÉäxºÉÒ | Ê´ÉtÖiÉ Eäòxpù EòÉ xÉÉ¨É | <ÇEòÉ<Ç ºÉÆ. | IÉ¨ÉiÉÉ(¨ÉèMÉÉ´ÉÉ]õ) | ºÉÆºlÉÉ{ÉxÉÉ EòÒ +xÉÖºÉÚÊSÉ
Sl. No. | Agency | Name of Power Station | Unit No. | Capacity(MW) | Schedule forCommissioning.
1 | Æü×¸üµÖÖÖÖ | µÖ´Öã­ÖÖ ­ÖÖ¸ü ™üß ¯Öß ‹ÃÖ | 1to2 | 300x2 | Unit# 1,COD 14.04.08
| Haryana | Yamuna Nagar TPS |  |  | Unit #2 Synchronised on 29.03.08,
2 | Æü×¸üµÖÖÖÖ | Rajeev Gandhi TPS(Khedar) | 1 to 2 | 600x2 | Unit#1- Synchronized on 28.12.2009.
| Haryana |  |  |  | COD on 31.03.2010
Unit#2-April2010
3 |  |  | 3 | 500 | Synchronised on 28.06.2009
| NTPC | Kahalgaon Stg.II |  |  | COD March,2010
4 | {É.®úÉ.Ê´É.¤ÉÉä. | VÉÒ.BSÉ.iÉÉ.Ê´É.Eäò.(º]äõVÉ-**) | 4 | 250 | Commissioned on 31.07.08
| PSEB | GHTPP Stage-2
5 | ®úÉVÉºlÉÉxÉ | ×Ö¸Ö»Ö -×»ÖÖ­ÖÖ‡™ü-II (µÖæ×­Ö™ü-II) | 2 | 125 | Synchronised on 26.12.08
| Rajasthan | Giral Lignite-II (Unit-2)
6 | ®úÉVÉºlÉÉxÉ | ”ûÖ²Ö›ÍüÖ- ŸÖÖ.×¾Ö.êú. | 1 to 2 | 2x250 | U#1-Synchronised on16.04.09,COD-30.10.09
| Rajasthan | Chhabra TPS |  |  | U# 2-April 2010
7 | ®úÉVÉºlÉÉxÉ | úÖê™üÖ- ŸÖÖ.×¾Ö.êú. | 7 | 195 | Synchronised on 30.05.09
| Rajasthan | Kota- TPS |  |  | Commissioned on 31.08.09
8 | ®úÉVÉºlÉÉxÉ | ÃÖæ¸üŸÖÖœÍü- ŸÖÖ.×¾Ö.êú. | 6 | 250 | Synchronised on 31.03.09
| Rajasthan | Suratgarh TPS |  |  | Commissioned on 29.08.09
9 | ®úÉVÉºlÉÉxÉ | ²ÖÖ¸üÖüØÃÖÖÃÖ¸ü ×»ÖÖ­ÖÖ‡™üü | 1to 2 | 2x125 | U#1-Synchronised on 27.10.09
| Rajasthan | Barsingsar Lignite |  |  | U# 2-March,2010
10 | ‹­Ö.¯Öß.ÃÖß.†Ö‡Ô.‹»Ö. | †Ö¸ü ‹ ¯Öß ‹ÃÖ | 5to6 | 2x220 | Unit#5-Test Synchronized on 22.12.2009
| NPCIL | RAPS |  |  | Commissioned on 04.02.2010
Unit#6-Synchronized on 28.03.2010
COD-31.03.2010
11 | NTPC | NCP Project Stg.-II(Dadri) | 5 to 6 | 2x490 | Unit#5-Test Synchronized on 25.12.2009
Commissioned on 31.01.2010
Unit#6-June,2010
12 | NDPL,Delhi | Rithala CCPP | 1 | 108 | June, 2010
13 | Raj.West power Ltd. | Jallipa Kapurdi TPP | 1 to 8 | 8x135 | U#1-Commissioned on 16.10.09
Rest May.2010 to March 2011
14 | Rosa Power Supply Co. | Rosa TPP Ph.-I | 1 | 300 | Unit#1-Test Synchronized on 28.12.2009
Commissioned on 10.02.2010
¨ÉÉ½þ Eäò nùÉè®úÉxÉ xÉªÉä ±ÉMÉÉ<Ç MÉ<È =i{ÉÉnùEò <ÇEòÉ<ÇªÉÉÄ/{ÉÉ®äú¹ÉhÉ ±ÉÉ<ÇxÉ iÉlÉÉ ºÉ¤É º]äõ¶ÉxÉ
NEW GENERATING UNITS / TRANS. LINES / SUB-STATIONS,COMMISSIONED DURING THE MONTH.
A) Generating Units:
1.135 MW Unit of V.S.Lignite thermal project(Bikaner, Rajasthan) of VS Lignite Power Pvt.Ltd.started commercial operation on 24.03.2010
2. Unit #6 of RAPS synchronised on 28.03.2010 and commisioned on 31.03.2010
3.Unit#1 of Rajiv Gandhi TPP,Hissar(600MW) of HPGCL commissioned on 31.03.2010
B) Transmission Lines:
1.400 kv Bhiwadi-Moga,D/C,702 ckm,Powergrid
2.220 kv Rosa-Shahjahanpur-II,S/C,22ckm,UP
3.220 kv Kankroli(PG)-Kankroli,S?C,8ckm,Rajasthan
4.220 kvLILO of Bikaner-Nagaur at Bikaner(400kv),D/C,37ckm,Rajasthan
5.220kv Marta-Makrana-Kuchaman,S/C,108ckm,Rajasthan
6.220kv LILO of one ckt.of Banaswara-Debari at 132kv GSS Salumber,D/C,16ckm,Rajasthan
7.220kv LILO of Sikar-Kuchman at GSS Dhod,D/C,6ckm,Rajasthan
8.220 kvLILO of one ckt.of KTPS-Bewar at Gulabpur,D/C,13ckm,Rajasthan
9.220kvD/C line at approach section of 400kvGSS Akai and 220kv bays at 400 kv Akai(Jaisalmer),D/C,12ckm,Rajasthan
C) Sub-Stations:
1.400/220kv,315 MVA,RoorkeeS/S(2nd ICT),Powergrid
2.400/220kv,315 MVA,Ludhiana(3rd ICT),Powergrid
3.400/220kv,315 MVA,Bikaner S/S(1x315),Rajasthan
4.220/132 kv,100MVA Mahindra SEZ(1X100),Rajasthan
5.220/132 kv,100MVAGulabpura,Rajasthan
6.220/132 kv,100MVADhod,Rajasthan

## Page24
20....¨ÉÉSÉÇú 2010 ¨ÉÉ½þ Eäò +ÎxiÉ¨É ÊnùxÉ =kÉ®úÒ IÉäjÉ Eäò VÉ±ÉÉ¶ÉªÉÉå Eäò VÉ±ÉÒªÉ +ÉÄEòcä÷
HYDRAULIC DATA OF RESERVOIRS IN THE NORTHERN REGION AS ON THE LAST DAY OF THE MONTH OF MARCH 2010
¨Énù | ¦ÉÉJÉc÷É | {ÉÉåMÉ | Ê®ú½þxnù | ®Éú.¦É.ºÉÉ. | MÉÉÄ.ºÉÉMÉ®ú | ITEM
| BHAKRA | PONG | RIHAND | R.P.Sagar | GANDHI SAGAR
VÉ±ÉÉ¶ÉªÉ EòÉ {ÉÚhÉÇ VÉ±É ºiÉ®ú | [5 empty] | Full Reservoir Level (FRL)
¨ÉÒ]õ®ú | 514.5024 | 433.1208 | 268.224 | 352.6536 | 402.6408 | (m)
¡òÒ]õ | 1688 | 1421 | 880 | 1157 | 1321 | (ft)
xªÉÚxÉkÉ¨É b÷Ò.b÷Ò. ºiÉ®ú | [5 empty] | Min. Draw Down Level (MDDL)
¨ÉÒ]õ®ú | 445.6176 | 384.048 | 252.984 | 342.9 | 381 | (m)
¡òÒ]õ | 1462 | 1260 | 830 | 1125 | 1250 | (ft)
¨ÉÉSÉÇú 2010 ¨ÉÉ½þ Eäò +ÎxiÉ¨É ÊnùxÉ VÉ±ÉÒªÉ ºiÉ®ú | [5 empty] | Level as on last day of March 2010
¨ÉÒ]õ®ú | 462.7169 | 395.4536 | 255.6662 | 345.9267 | 382.6154 | (m) |  |  |  |  | 0.625 |  | 258.47
¡òÒ]õ | 1518.1 | 1297.42 | 838.8 | 1134.93 | 1255.3 | Ft. |  |  |  |  | 0.68 |  | 847.9987
0.11522
¨ÉÉSÉÇú 2009 ¨ÉÉ½þ Eäò +ÎxiÉ¨É ÊnùxÉ VÉ±ÉÒªÉ ºiÉ® | [5 empty] | Level as on last day of March 2009
¨ÉÒ]õ®ú | 476.38 | 402.29 | 257.56 | 345.15 | 383.35 | (m)
¡òÒ]õ | [5 empty] | (ft)
¨ÉÉSÉÇ 2010 Eäò +ÎxiÉ¨É ÊnùxÉ ±ÉÉ<Ç´É IÉ¨ÉiÉÉ | [5 empty] | Live capacity on last day of March 2010 | 0.3 |  | 0.02 | 0.75 | 0.35 | 1
| 0.10771 | 0.12132 | 0.071804 | 0.040854 | 0.025998 | (mhmt) | 1.62 |  | 0.98 | 0.8 | 0.27 | 0.38
B¨É.B.¡òÒ]õ | 0.87 | 0.98 | 0.58 | 0.33 | 0.21 | (maft)
¨ÉÉSÉÇ 2009 Eäò +ÎxiÉ¨É ÊnùxÉ ±ÉÉ<Ç´É IÉ¨ÉiÉÉ | [5 empty] | Live capacity on last day of March 2009
B¨É.BSÉ.¨ÉÒ]õ®ú | 0.23 | 0.21 | 0.14 | 0.03 | 0.04 | (mhmt)
B¨É.B.¡òÒ]õ | [5 empty] | (maft)
¨ÉÉSÉÇ 2010 ¨ÉÉ½þ Eäò +ÎxiÉ¨É ÊnxÉù Ê´ÉtÖiÉ ¨ÉÉjÉÉ | [5 empty] | Energy content on last day of March 2010
B¨É.ªÉÚ. | 370 | 150 | 115 | 72 | 70 | (MU)
¨ÉÉSÉÇ 2009 ¨ÉÉ½þ Eäò +ÎxiÉ¨É ÊnxÉù Ê´ÉtÖiÉ ¨ÉÉjÉÉ | [5 empty] | Energy content on last day ofMarch 2009
B¨É.ªÉÚ. | 800 | 290 | 215 | 53 | 100 | (MU)
¨ÉÉSÉÇ 2010 ¨ÉÉ½ þEäò nùÉè®úÉxÉ +ÊvÉEòiÉ¨É VÉ±ÉÒªÉ ºiÉ®ú | [5 empty] | Maximum level during March 2010
¨ÉÒ]õ®ú | 472.8667 | 395.9261 | 256.5806 | 345.9267 | 383.2494 | (m)
¡òÒ]õ | 1551.4 | 1298.97 | 841.8 | 1134.93 | 1257.38
ÊiÉÊlÉ | 2010-03-01 | 01.03.10 | 2010-03-01 | 31.03.10 | 2010-03-01 | (Date)
¨ÉÉSÉÇ 2010 ¨ÉÉ½ þEäò nùÉè®úÉxÉ xªÉÚxÉkÉ¨É VÉ±ÉÒªÉ ºiÉ®ú | [5 empty] | Minimum level during March 2010
¨ÉÒ]õ®ú | 462.7169 | 395.4475 | 255.6662 | 345.4512 | 382.6154 | (m)
¡òÒ]õ | 1518.1 | 1297.4 | 838.8 | 1133.37 | 1255.3 | (ft)
ÊiÉÊlÉ | 31.03.10 | 30.03.10 | 31.03.10 | 2010-03-01 | 31.03.10 | (Date)
Ê]õ{{ÉhÉÒ Notes :
¦ÉÉEòc÷É EòÒ Ê´ÉtÖiÉ ¨ÉÉjÉÉ | ¦ÉÉJÉc÷É, MÉÆMÉÖ´ÉÉ±É iÉlÉÉ EòÉä]õ±ÉÉ Ê´ÉtÖiÉ EäòxpùÉä EòÒ EÖò±É Ê´ÉtÖiÉ ¨ÉÉjÉÉ *
Energy content of Bhakra : | Total energy content at Bhakra, Ganguwal and Kotla Power Stations.
Ê®ú½þxnù EòÒ Ê´ÉtÖiÉ ¨ÉÉjÉÉ | Ê®ú½þxnù iÉlÉÉ +Éää¤É®úÉ Ê´ÉtÖiÉ EäòxpùÉä EòÒ EÖò±É Ê´ÉtÖiÉ ¨ÉÉjÉÉ
Energy content of Rihand : | Total energy content at Rihand and Obra Power Stations.
+É®ú.{ÉÒ.BºÉ.ù EòÒ Ê´ÉtÖiÉ ¨ÉÉjÉÉ | ®úÉhÉÉ¦ÉiÉÉ{É ºÉÉMÉ®ú iÉlÉÉ VÉ´ÉÉ½þ®ú ºÉÉMÉ®ú Ê´ÉtÖiÉ EäòxpùÉä EòÒ EÖò±É Ê´ÉtÖiÉ ¨ÉÉjÉÉ
Energy content of RPS : | Total energy content at Rana Pratap Sagar and Jawahar Sagar Power Stations.
MÉÉÄvÉÒ ºÉÉMÉ®ú EòÒ Ê´ÉtÖiÉ ¨ÉÉjÉÉ | MÉÉÄvÉÒ ºÉÉMÉ®ú, ®úÉhÉÉ¦ÉiÉÉ{É ºÉÉMÉ®ú iÉlÉÉ VÉ´ÉÉ½þ®ú ºÉÉMÉ®ú Ê´ÉtÖiÉ EäòxpùÉä EòÒ EÖò±É Ê´ÉtÖiÉ ¨ÉÉjÉÉ
Energy content of G.Sagar : | Total energy content at Gandhi Sagar, R. P. Sagar and Jawahar Sagar Power Stations

## Exbt1
| ºÉÆºlÉÉÊ{ÉiÉ | =i{ÉÉnùxÉ
VÉ±ÉÒªÉ | 13310.75 | 7405
iÉÉ{ÉÒªÉ | 24851.25 | 19078
xÉÉÊ¦ÉEòÒªÉ | 1620 | 781
| 39782 | 27264

## Exbt2
ÊiÉÊlÉ | ={É±É¤vÉiÉÉ | Eò¨ÉÒ
DATE | AVAILABILITY | SHORTAGE
1 | 572.8353 | 74.269
2 | 588.1896 | 87.532
3 | 611.7011 | 87.444
4 | 600.0554 | 88.138
5 | 604.2982 | 85.538
6 | 604.8535 | 89.717
7 | 600.4042 | 78.907
8 | 606.83 | 62.808
9 | 612.5972 | 31.101
10 | 622.6765 | 59.45
11 | 621.1703 | 48.174
12 | 620.9128 | 35.157
13 | 619.3383 | 36.934
14 | 621.8758 | 36.594
15 | 618.6189 | 39.012
16 | 630.6805 | 41.61
17 | 623.0168 | 44.212
18 | 604.9582 | 63.375
19 | 621.096 | 67.293
20 | 634.8754 | 76.047
21 | 622.6999 | 77.679
22 | 624.5739 | 79.967
23 | 632.8697 | 63.351
24 | 637.6893 | 80.185
25 | 635.6341 | 75.932
26 | 632.5243 | 68.791
27 | 631.7997 | 72.173
28 | 618.4481 | 53.18
29 | 626.3737 | 49.1037
30 | 633.2451 | 41.2982
31 | 637.3616 | 33.4927

## Exbt3
ÊiÉÊlÉ | ={É±É¤vÉiÉÉ | Eò¨ÉÒ
DATE | AVAILABILITY | SHORTAGE
1 | 23511 | 913
2 | 26423 | 1430
3 | 25703 | 1746
4 | 25593 | 2380
5 | 26375 | 2288
6 | 25652 | 2453
7 | 24947 | 1547
8 | 26175 | 1784
9 | 25557 | 3112
10 | 25772 | 2949
11 | 25909 | 3009
12 | 26156 | 2781
13 | 25749 | 3084
14 | 24727 | 2620
15 | 25757 | 2936
16 | 26427 | 3309
17 | 25889 | 3647
18 | 25013 | 4410
19 | 25707 | 3614
20 | 26285 | 3092
21 | 25299 | 3326
22 | 26116 | 3178
23 | 26179 | 2841
24 | 26473 | 2926
25 | 26843 | 2903
26 | 25882 | 3304
27 | 26347 | 3066
28 | 24676 | 1711
29 | 25869 | 2912
30 | 25415 | 2453
31 | 25740 | 2550

## Exbt4
Northern Region
PÉx]äõ | EòÉäªÉ±ÉÉ VÉÊ±ÉiÉ=i{ÉÉnùxÉ | xÉÉÊ¦ÉEòÒªÉ =i{ÉÉnùxÉ | 'MÉèºÉÒªÉ =i{ÉÉnùxÉ | VÉ±ÉÒªÉ =i{ÉÉnùxÉ | EÖò±É =i{ÉÉnùxÉ | +ÉªÉÉiÉ/ÊxÉªÉÉÇiÉ | ¦ÉÉ®ú | Eò]õÉèÊiÉ
Hrs | Coal Fired Gen | Nuclear Gen. | Gas Fired Gen | Hydro Gen | Total Gen. | Imp(+)/Exp(-) | Demand Met | Load Shedding
1 | 17450 | 886 | 2172 | 4831 | 25339 | 1269 | 26608 | 2190
2 | 17484 | 886 | 2645 | 4013 | 25028 | 1065 | 26093 | 2185
3 | 17476 | 889 | 2656 | 3291 | 24312 | 1541 | 25853 | 1912
4 | 17748 | 895 | 2649 | 3277 | 24569 | 1290 | 25859 | 1844
5 | 17783 | 902 | 2648 | 3660 | 24993 | 1189 | 26182 | 1659
6 | 17726 | 898 | 2675 | 4083 | 25382 | 2004 | 27386 | 2618
7 | 17720 | 903 | 2685 | 3488 | 24796 | 2218 | 27014 | 2872
8 | 17279 | 912 | 2654 | 3392 | 24237 | 2238 | 26475 | 3257
9 | 17304 | 905 | 2633 | 3867 | 24709 | 2062 | 26771 | 3741
10 | 17220 | 897 | 2536 | 4479 | 25132 | 1970 | 27102 | 4158
11 | 17265 | 895 | 2556 | 4933 | 25649 | 2254 | 27903 | 3768
12 | 17316 | 889 | 2554 | 4815 | 25574 | 2691 | 28265 | 3370
13 | 17290 | 886 | 2532 | 3731 | 24439 | 2866 | 27305 | 3388
14 | 16178 | 880 | 2530 | 4176 | 23764 | 3041 | 26805 | 2313
15 | 17385 | 875 | 2556 | 4275 | 25091 | 2785 | 27876 | 2819
16 | 17375 | 784 | 2495 | 3893 | 24547 | 2563 | 27110 | 2626
17 | 17125 | 781 | 2541 | 3401 | 23848 | 2760 | 26608 | 2698
18 | 16677 | 779 | 2482 | 3540 | 23478 | 2429 | 25907 | 3740
19 | 16618 | 780 | 2508 | 6232 | 26138 | 569 | 26707 | 3452
20 | 16861 | 781 | 2596 | 7405 | 27643 | 2665 | 30308 | 3688
21 | 16977 | 775 | 2642 | 6298 | 26692 | 2803 | 29495 | 3806
22 | 17035 | 783 | 2656 | 5600 | 26074 | 2262 | 28336 | 3322
23 | 16912 | 780 | 2648 | 5646 | 25986 | 2299 | 28285 | 3064
24 | 16973 | 778 | 2659 | 5402 | 25812 | 2247 | 28059 | 3179

## Exbt5
Northern Region
PÉx]äõ | EòÉäªÉ±ÉÉ VÉÊ±ÉiÉ=i{ÉÉnùxÉ | xÉÉÊ¦ÉEòÒªÉ =i{ÉÉnùxÉ | 'MÉèºÉÒªÉ =i{ÉÉnùxÉ | VÉ±ÉÒªÉ =i{ÉÉnùxÉ | EÖò±É =i{ÉÉnùxÉ | +ÉªÉÉiÉ/ÊxÉªÉÉÇiÉ | ¦ÉÉ®ú | Eò]õÉèÊiÉ
Hrs | Coal Fired Gen | Nuclear Gen. | Gas Fired Gen | Hydro Gen | Total Gen. | Imp(+)/Exp(-) | Demand Met | Load Shedding
1 | 15856 | 833 | 1997 | 2359 | 21045 | 1770 | 22815 | 935
2 | 15936 | 840 | 1966 | 2303 | 21045 | 1675 | 22720 | 765
3 | 15823 | 839 | 1900 | 2239 | 20801 | 1532 | 22333 | 792
4 | 15670 | 836 | 1979 | 2228 | 20713 | 1713 | 22426 | 799
5 | 15653 | 832 | 2112 | 2869 | 21466 | 888 | 22354 | 1004
6 | 16810 | 800 | 2209 | 3823 | 23642 | 1922 | 25564 | 1010
7 | 16725 | 828 | 2167 | 5194 | 24914 | 2110 | 27024 | 1115
8 | 16425 | 681 | 2129 | 4783 | 24018 | 2199 | 26217 | 1131
9 | 16425 | 794 | 2105 | 4427 | 23751 | 2314 | 26065 | 1206
10 | 16958 | 819 | 2278 | 4573 | 24628 | 2728 | 27356 | 1237
11 | 16961 | 823 | 2041 | 5084 | 24909 | 1900 | 26809 | 3045
12 | 16784 | 815 | 2215 | 5353 | 25167 | 1875 | 27042 | 2110
13 | 17011 | 813 | 2299 | 4664 | 24787 | 1764 | 26551 | 1916
14 | 16884 | 816 | 2053 | 4150 | 23903 | 2190 | 26093 | 1765 | 58355
15 | 16898 | 815 | 2193 | 3589 | 23495 | 1945 | 25440 | 1972
16 | 16830 | 819 | 2143 | 2645 | 22437 | 2058 | 24495 | 1327
17 | 16823 | 819 | 2150 | 2779 | 22571 | 1811 | 24382 | 1815
18 | 16798 | 827 | 2001 | 4239 | 23865 | 1057 | 24922 | 2449
19 | 17011 | 824 | 2269 | 6895 | 26999 | 1055 | 28054 | 2182
20 | 17118 | 823 | 2300 | 5746 | 25987 | 1183 | 27170 | 3087
21 | 16932 | 827 | 2330 | 4477 | 24566 | 1347 | 25913 | 2444
22 | 17096 | 831 | 2158 | 4117 | 24202 | 1035 | 25237 | 1480
23 | 17099 | 824 | 2219 | 3669 | 23811 | 1462 | 25273 | 1217
24 | 17158 | 823 | 2372 | 3112 | 23465 | 1542 | 25007 | 1063

## Exbt6
BHAKRA
RESERVOIR LEVEL(on last day of the month in Mtrs.)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 471.88 | 462.52 | 477.8
MAY | 465.81 | 466.25 | 474.19
JUNE | 463.71 | 489.65 | 479.83
JULY | 478.49 | 500.68 | 490.06
AUGUST | 491.84 | 510.21 | 504.47
SEPTEMBER | 499.56 | 512 | 505.46
OCTOBER | 499.42 | 508.69 | 502.08
NOVEMBER | 495.76 | 505.66 | 497.92
DECEMBER | 490.19 | 500.54 | 491.51
JANUARY | 482.52 | 493.39 | 484.82
FEBRUARY | 473.31 | 486.27 | 476.09
MARCH | 462.72 | 476.38 | 463.59
GENERATION (MU)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 311.93 | 258.77 | 529.48
MAY | 512.41 | 370.76 | 540.33
JUNE | 593.54 | 460.42 | 536.1
JULY | 612.56 | 742.41 | 647.57
AUGUST | 515.958 | 890.49 | 659.58
SEPTEMBER | 477.37 | 711.28 | 643.31
OCTOBER | 377.85 | 660.63 | 495.26
NOVEMBER | 433.93 | 456.29 | 458.91
DECEMBER | 437.97 | 522.45 | 501.57
JANUARY | 434.09 | 544.22 | 454.37
FEBRUARY | 395.7 | 441.71 | 410.06
MARCH | 384.84 | 467.76 | 447.55

## Exbt7
PONG
RESERVOIR LEVEL(on last day of the month in Mtrs.)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 402.45 | 393.4 | 411.21
MAY | 393.84 | 391.34 | 406.53
JUNE | 388.64 | 402.03 | 403.14
JULY | 394.88 | 412.66 | 407.65
AUGUST | 402.03 | 422.3 | 415.9
SEPTEMBER | 407.99 | 423.48 | 414.08
OCTOBER | 405.08 | 422.01 | 409.11
NOVEMBER | 402.6 | 418.13 | 404.67
DECEMBER | 398.25 | 414.26 | 399.97
JANUARY | 395.53 | 411.64 | 397.95
FEBRUARY | 395.91 | 408.22 | 396.02
MARCH | 395.45 | 402.29 | 393.64
GENERATION (MU)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 25.83 | 25.39 | 77.19
MAY | 192.53 | 53.92 | 215.81
JUNE | 81.13 | 33.2 | 188.5
JULY | 59.01 | 51.26 | 176.52
AUGUST | 68.458 | 214.74 | 178.61
SEPTEMBER | 81.44 | 125.91 | 220.41
OCTOBER | 124.49 | 134.2 | 227.57
NOVEMBER | 100 | 201.25 | 157.37
DECEMBER | 117.73 | 196.77 | 139.99
JANUARY | 62.6 | 125.49 | 65.01
FEBRUARY | 10.78 | 140.64 | 59.28
MARCH | 25.64 | 186.48 | 58.83

## Exbt8
RIHAND
RESERVOIR LEVEL(on last day of the month in Mtrs.)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 256.28 | 255.33 | 255.3
MAY | 254.97 | 254.75 | 254.29
JUNE | 254.08 | 255.39 | 253.44
JULY | 256.4 | 258.62 | 254.36
AUGUST | 257.74 | 262.01 | 255.85
SEPTEMBER | 259.23 | 262.13 | 258.9
OCTOBER | 258.93 | 261.15 | 259.11
NOVEMBER | 258.65 | 260.3 | 258.68
DECEMBER | 258.04 | 259.87 | 258.17
JANUARY | 257.19 | 259.05 | 257.46
FEBRUARY | 256.61 | 258.47 | 256.79
MARCH | 255.67 | 257.56 | 256.12
GENERATION (MU)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 48.72 | 26.39 | 36.17
MAY | 41.44 | 13.12 | 32.59
JUNE | 26.1 | 17.98 | 33.76
JULY | 18.73 | 37.36 | 46.66
AUGUST | 38.054 | 29.67 | 53.17
SEPTEMBER | 38.93 | 67.199 | 18.7
OCTOBER | 47.71 | 67.68 | 56
NOVEMBER | 24.53 | 44.53 | 25.64
DECEMBER | 27.22 | 19.81 | 23.2
JANUARY | 35.67 | 38.92 | 31.36
FEBRUARY | 22.92 | 23.05 | 27.93
MARCH | 30.88 | 38.3 | 23.12

## Exbt9
R.P.SAGAR
RESERVOIR LEVEL(on last day of the month in Mtrs.)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 345.65 | 351.82 | 352.27
MAY | 346.07 | 351.93 | 351.79
JUNE | 346.26 | 351.07 | 351.64
JULY | 347.51 | 351.58 | 351.58
AUGUST | 348.31 | 352.54 | 350.95
SEPTEMBER | 348.38 | 352.67 | 351.1
OCTOBER | 347.68 | 352.41 | 351.24
NOVEMBER | 346.3 | 350.32 | 351.68
DECEMBER | 345.54 | 347.56 | 352.24
JANUARY | 345.53 | 345.16 | 352.14
FEBRUARY | 345.63 | 344.98 | 352.07
MARCH | 345.93 | 345.15 | 351.2
GENERATION (MU)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 0 | 13.81 | 21.11
MAY | 1.31 | 0.37 | 29.12
JUNE | 1.08 | 41.55 | 58.38
JULY | 0.02 | 17.6 | 101.68
AUGUST | 0 | 2.68 | 37.76
SEPTEMBER | 0.78 | 6.04 | 49.24
OCTOBER | 16.8 | 11.54 | 52.42
NOVEMBER | 37.47 | 76.39 | 65.22
DECEMBER | 54.66 | 72.34 | 63.84
JANUARY | 31.58 | 57.64 | 71.66
FEBRUARY | 0.15 | 16.73 | 65.79
MARCH | 0 | 0.54 | 59.92

## Exbt10
GANDHI SAGAR
RESERVOIR LEVEL(on last day of the month in Mtrs.)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 382.41 | 385.76 | 392.15
MAY | 381.47 | 385.43 | 391.38
JUNE | 380.79 | 385.32 | 389.81
JULY | 386.54 | 385.88 | 389.76
AUGUST | 386.5 | 386.98 | 396.3
SEPTEMBER | 388.06 | 387.21 | 396.4
OCTOBER | 387.77 | 386.96 | 395.44
NOVEMBER | 387.12 | 385.95 | 393.95
DECEMBER | 385.47 | 385.38 | 392.18
JANUARY | 383.64 | 384.77 | 390.46
FEBRUARY | 383.27 | 383.8 | 388.62
MARCH | 382.62 | 383.35 | 387.14
GENERATION (MU)
MONTH | 2009-10 | 2008-09 | 2007-08
APRIL | 10.08 | 23.79 | 15.94
MAY | 7.93 | 3.59 | 17.13
JUNE | 5.39 | 11.22 | 39.79
JULY | 1.36 | 10.19 | 39.6
AUGUST | 10.888 | 1.66 | 41.07
SEPTEMBER | 3.77 | 0.86 | 43.33
OCTOBER | 5.46 | 3.91 | 53.62
NOVEMBER | 13.35 | 17.55 | 65.53
DECEMBER | 34.06 | 9.12 | 65.47
JANUARY | 27.06 | 9.62 | 52.51
FEBRUARY | 4.06 | 13.79 | 45.67
MARCH | 7.23 | 4.81 | 27.35

## Exbt11
={É±É¤vÉiÉÉ | Eò¨ÉÒ
DEMAND MET | % OF TIME
22000 | 100
22200 | 100
22400 | 99.6
22600 | 99.45
22800 | 99.19
23000 | 98.79
23200 | 98.52
23400 | 97.85
23600 | 97.85
23800 | 96.24
24000 | 94.89
24200 | 92.88
24400 | 91.13
24600 | 88.44
24800 | 86.42
25000 | 82.93
25200 | 80.78
25400 | 75.94
25600 | 70.7
25800 | 65.73
26000 | 61.69
26200 | 54.7
26400 | 50.27
26600 | 43.82
26800 | 37.5
27000 | 31.85
27200 | 26.08
27400 | 21.24
27600 | 16.53
27800 | 12.63
28000 | 10.22
28200 | 7.66
28400 | 5.38
28600 | 4.03
28800 | 2.82
29000 | 1.61
29200 | 1.34
29400 | 0.94
29600 | 0.67
29800 | 0.4
30000 | 0.4
30200 | 0.27
30400 | 0
30600 | 0

## Exbt12
Frequency | % of Time
48.5 | 100
48.8 | 100
49 | 98.74
49.2 | 94.01
49.5 | 66.51
50 | 12.36
50.3 | 1.71
51 | 0
0.1319
|  | <48.5 | 48.5- 48.8 | 48.8- 49 | 49-49.2 | 49.2- 49.5 | 49.5- 50 | 50-50.3 | 50.3-51 | >51.00
|  | 0 | 0 | 1.26 | 4.7268 | 27.499 | 54.1481 | 10.6516 | 1.7145 | 0